## Cover sheet
Risk Analysis M&A |  | IT-as-is Manager | Falcon PMO
|  | IT-Project Manager | IT Project Manager
- Cover Sheet - |  | PMI-Lead | Risk Owner
Information about the project and the risk analysis:
Actions are tracked in
Further information:
Participants of latest meeting/update of risk analysis:
| Participant |  | Department |  | Function
PMI-Lead
IT-Project Manager
PjQM
Technical expert from project team
The required signature of the risk analysis (PjM and PjQM) is covered by the signature of the respective QA.
Document History:
| Change |  | Version | Date | Changed by
…
The risk analysis has to be updated regularly during the whole merger duration - The different states have to be versioned -

## Analysis of project risks
Analysis of as-is operation risks | [9 empty] | RZ statistic |  | Please insert rows exclusively over button!
[10 empty] | Threshold: | 12
Risks higher than or equal to threshold:
No. | Sub- project (optional) | Entry Date of Risk | Risk category | Risk (concrete, understandable description) | Effects (corresponds with T=Sign. of effects (column I)) | Causes | W | T | RZ | Actions (preventive and counter measures) | Responsible | Deadline | Status of action | Remarks / notes [optional] (e.g., critical general conditions; already planned actions)
1 |  |  | ScR - Schedule | BGSW and JV management availability low due to carve-out overlap with daily operations | High-priority; fundamental to outcome. Mitigation plan in place. | Carve-out timing during active AI business operations; split focus between separation and continuity | 4 | 4 |  | Dedicated BGSW carve-out lead with explicit time allocation; Deputy identified; Weekly SteerCo cadence | Bosch BD/MIL PM, BGSW CIO | 15-Jun-26 | Green
2 |  |  | SR - Scope | JV legal entity setup (India MCA registration) delayed beyond QG1 target (30 Jun 2026) | Critical path item. India legal experience essential. | MCA bureaucratic delays (typical 4-8 weeks); lack of prior JV registration experience in India | 3 | 5 |  | Engage external India legal counsel immediately (May); file MCA registration within 7 days of project start | Bosch BD/MIL, Legal, Finance | 15-Jun-26 | Green
3 |  |  | BtR - Budget | Project budget grows beyond initial estimate due to underestimated India cloud/connectivity costs | Conservative estimate: +20% budget. Build contingency reserve. | India cloud pricing higher than expected; WAN circuit lead times and costs underestimated | 3 | 4 |  | Conduct detailed India cloud RFQ now (May); secure WAN quotes with firm lead times | Finance, BGSW Procurement | 15-Jun-26 | Amber
4 |  |  | ScR - Schedule | TSA exit delays beyond target (Mar 2027) due to incomplete service separation definitions | TSA is minimal. Delay extends BGSW carver costs. | TSA service catalogue not finalized in time; JV IT operations not fully ready by Day 1 | 2 | 5 |  | TSA catalogue locked at QG2 (28 Aug 2026); weekly TSA governance reviews | BGSW IT, JV IT, Bosch BD/MIL | Jan-27 | Green
5 |  |  | RR - Resource | BGSW IT team attrition or capacity loss during carve-out (9-month project) | Monitor headcount monthly. Risk accepted with mitigation in place. | Employee uncertainty about JV future; burnout risk during concurrent execution | 3 | 4 |  | Early team communication on roles post-JV; retention plan for key personnel | BGSW HR, BGSW CIO | Ongoing | Amber
6 |  |  | SR - Scope | Application migration scope expands (>20 apps) due to undiscovered dependencies | Scope is relatively small (20 apps). Hard cutoff required. | Business users request additional legacy apps not in original scope | 2 | 4 |  | Freeze application list by QG1 (30 Jun). Hard cutoff for scope additions. | WS Leads, BGSW IT PM | 15-Jun-26 | Green
7 |  |  | SR - Scope | JV cloud infrastructure (M365 / Azure) procurement delayed or incorrectly sized | JV licensing model must be clear. Pre-ordering critical. | Azure tenant provisioning underestimated; JV licensing complexity | 2 | 4 |  | Start M365/Azure pre-ordering now (May); test tenant immediately after contract | BGSW Azure Team, Bosch BD/MIL | 15-Jun-26 | Green
8 |  |  | CR - Change | Active Directory forest separation incomplete by cutover due to complexity | AD is foundational to Day 1. No backout option. Pilot critical. | AD migration tooling unavailable or untested; configuration errors | 2 | 4 |  | Start AD pilot migration in Sep 2026; lock config by QG3; run 2x dress rehearsals | BGSW AD Team | 30-Nov-26 | Green
9 |  |  | BtR - Budget | License change-of-control costs for ~20 AI applications exceed budget | 20 apps is manageable. Estimate 30-50% escalation on licenses. | ISVs demand new licensing terms; unexpected vendor lock-in clauses | 2 | 3 |  | License audit with change-of-control clause review; negotiate amendments | BGSW Procurement, Legal | 15-Jun-26 | Green
10 |  |  | LR - Legality | India regulatory compliance gaps (data residency, RBIN, tax ID) | Must plan 12+ weeks for approvals. Escalate to International Compliance. | RBIN approval cycles lengthy; tax registration delays; data localization rules | 3 | 3 |  | File RBIN waiver immediately (May); engage India tax counsel | Legal, Finance, Bosch BD/MIL | 15-Jun-26 | Amber
11 |  |  | QR - Quality | UAT (11 Nov - 20 Nov) insufficient due to late user availability | Small scope (20 apps). Plan conservatively. | Business users delayed in test case prep; incomplete regression scenarios | 2 | 3 |  | UAT plan locked by QG3; business sign-off on test cases by 1 Nov | Test Lead, Business Leads | 15-Nov-26 | Green
12 |  |  | CR - Change | Data migration incomplete or inconsistent for AI business data by Day 1 | AI data is sensitive. Zero tolerance for data loss. | Data classification incomplete; migration tooling untested; ownership unclear | 2 | 3 |  | Data ownership rules locked by QG2; pilot in Development; dress rehearsal | BGSW IT, Data Owner | 15-Nov-26 | Green
13 |  |  | RR - Resource | Help Desk / IT Ops in India understaffed or untrained at GoLive (7 Dec) | Plan 3-month lead time minimum. Exploring contractor options. | India recruitment timeline longer than expected; training lag | 2 | 3 |  | Hiring by Aug 2026; on-boarding Nov 2026; hypercare team embedded | BGSW HR, IT Ops | 01-Nov-26 | Amber
14 |  |  | SR - Scope | Buyer (TBC) acquires different AI assets/scope than originally planned | Buyer unknown = inherent uncertainty. Accept residual risk. | Buyer entity unknown; may have different strategic direction | 1 | 5 |  | Scope locked at QG1. Changes require business decision and impact analysis. | Steering Committee, Legal | 15-Jun-26 | Amber
15 |  |  | QR - Quality | Integration testing failures between AI apps and BGSW TSA services | Small scope (20 apps, 3 sites). Mitigation feasible. | Incomplete TSA definitions; mock environments not reflecting prod reality | 2 | 2 |  | TSA catalogs finalized by QG2; full integration test environment by QG3 | Test Lead, BGSW IT | 15-Nov-26 | Green
16 |  |  | ScR - Schedule | GoLive cutover (7 Dec) compressed due to earlier phase delays | Hard deadline tied to legal separation. Escalation protocol in place. | QG3 (30 Oct) slips to Nov; dress rehearsal cancelled due to time pressure | 1 | 4 |  | Schedule buffer in Phases 4-5; daily SteerCo reviews from QG3 onwards | IT PM, Steering Committee | 04-Dec-26 | Green
Note on A7: The risks are numbered sequentially.
Note on B7: Multi-Projects: Please insert the project to which the risk refers
Note on C7: Only relevant for risks identified after creation of risk analysis.
Note on D7: If needed, risks can be assigned to risk categories. The following categories can be used as well as others. BR = Business BtR = Budget CR = Customer Satisfaction QR = Quality RR = Resource ScR = Schedule SR = Scope LR = Legality SrR = Security PR = Further product risks EM = Employee
Note on F7: What are the effects once the risk/ potential failure occurs?
Note on G7: What are the causes for the risk/the failure to occur?
Note on H7: W = Probability of occurrence: 5 = very high 4 = high 3= medium 2 = low 1 = unlikley
Note on I7: T= Significance of effects: 5 = very high 4 = high 3 = medium 2 = low 1 = unlikley
Note on J7: Product of W and T; The RZ shall support the prioritisation of risks and will be calculated automatically
Note on N7: Possible values: open, in process (iP), completed (com)
Note on O7: What was planned to minimise the risk before carrying out this risk analysis? E.g.: Database overflow. Plan for a monitoring software generating alerts once data volume reaches 80% of hard disk capacity. Not all risks can be eliminated by an action.

## Explanation_History
Information about method/template
Scope of risk analysis: (Attention: Procedure partly changed compared to previous template version!) |  |  | Project risks can generally be differed by product risks (e.g. product suitability, general conditions of product) and process risks (e.g. project management; development process or process of producing the project result). In the risk analysis both has to be covered.
Update: Cycle and versions |  |  | The risk analysis has to be updated regularly during the whole project duration - at least to each QA. The different states have to be versioned - the currently latest version has to be filed with the respective QA.
Update: Procedure (Attention: Procedure partly changed compared to previous template version!) |  |  | Updating the risk analysis, existing risks will be reassessed and new risk will be listed in the overview. By reassessing existing risks, the existing values can be overwritten with the new values because previous values are saved in the different versions of the document. Therefor old versions of the risk analysis have to be archived with the project documentation.
Definition of actions (Attention: Procedure partly changed compared to previous template version!) |  |  | At least for risks whose risk figure (RZ) is higher than or equal to the threshold value of 12, an action or a reason why no action is defined has to be named. It is recommended to define actions also to risks with high significance of effects (T). The threshold can be lowered (e.g. from 12 to 9) but not increased for the single project. To every action a responsible person and deadline have to be named.
Tracking of risks and actions (Attention:Procedure partly changed compared to previous template version!) |  |  | The document in which the actions are tracked has to be named in the cover sheet. Actions have to be done on schedule (requirement of C/AU)! If an action is processed and the status is set on 'completed', the risk has to be reassessed. Therefore the old values can simply be overwritten. If an action lowers the former significance of effects (T) of the risk, not only the value of T but also the effects (verbal description column F) have to be overwritten. If a risk is still high after completion of the action, a new action has to be defined. Traceability of the actions and their completion is given by the recording of the different versions of the risk analysis.
Documentation |  |  | To ensure the traceability of the risk analysis (requirement of C/AU), - the docment history (cover sheet) and - the column " entry date of risk" (for later listed risks) have to be filled in.
If risks are escalated, this has to be definde as an action.
Information about the makros |  |  | To ensure the consistency of the template it is absolutely necessary that new lines are inserted exclusively about the button "New line".
Additional Information about risk categories |  |  | Explanation "Business Risk": Risk that the business processes of the customers do not work as needed
Risk assessment:
| W - Probability of occurrence: |  | 5 = very high 4 = high 3 = medium 2 = low 1 = unlikely
| T - Significance of effects: |  | 5 = very severe 4 = severe 3 = medium 2 = low 1 = none
| RZ - Risk figure |  | The risk figure supports the prioritization of risks and is the result of the product of W and T (RZ = W x T).
Document History Template "AS-IS operation Risk Analysis"
Version | Release Date | Author | Description of Changes
1.0 | 2022-06-13 | BD/MIL-MIA Ladenburgerr | Adaption to new BD-organisation
Changes of Content:
first version: Risk analysis template based on project risk analysis