## Info
Revision history
Document Id | <doc-id>
File Name | <file>
Project Name | <project name>
Project Id | <project id>
Document Owner | <owner>
Review Date | Reviewers |  | Changes
About this template
Risk Category | Select from categories as defined by the Risk Management Plan.
Cause | Specifically what causes the risk to become a realized issue/problem
Effect | What happens if the trigger point occurs
Owner | Risk owner.
Creation date | Date risk identified.
Source | Source of risk.
Impact | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan
Probability | Probability of risk being realized, using scales defined in the Risk Management Plan.
Matrix Score | This is calculated once you select the Impact and Probability.
Qualitative Impact | Space for further description of potential impact.
Quantitative Impact | quantitative / potential risk cost
Risk response strategy | Select from strategies as defined by the Risk Management Plan.
Status | Risk status (e.g. whether it has been triggered or not). You will need to update the values list in cells
Notes | Additional notes.
Template Version | Issue Date | Author | Changes
1.0 | 2023-12-07 | S. Hoehnel | initial template based on V5.2 of the central risk register (S. Wohlfahrt); only examples provided on top

## Risk Register
Risk Register
Risk Identification | [8 empty] | Risk Analysis | [8 empty] | Risk Response Planning |  |  | Risk Monitoring and Control
risk ID | creation date | risk category | cause(s) | event | effect(s) | risk event date | owner | source | impact |  | prob- ability |  | threat / opportunity | matrix score | qualitative impact (including period of consideration) | monetary impact [EUR] current year | monetary impact [EUR] three subsequent years | risk response strategy | measure | due date | status | reporting date | impact actual |  | prob- ability actual |  | impact (actual) | probability (actual) | matrix score (actual) | notes
1 |  | Strategy & Portfolio | Scope-creep, additional budget requirements, or delays have not been assessed against initial project-goals. |  | Problem-statement for selection of project is not fulfilled. | n.a. | XY | Other | High | 0.4 | 10% | 0.1 | threat |  |  |  | 0 | Mitigate | Request review of portfolio-assessment by responsible CI/AC with each change-request. |  | not started |  | High | 0.4 | 10% | 0.1 | 0.4 | 0.1 | 0.04
2 |  | Security & Data Protection | - Unauthorized person has access to the office rooms - There are no reception staff in building xx - Access control only via badge reader - Office entrance doors close slowly - Office entrance doors are temporarily wedged open - Cash sometimes lies around openly | Theft of employee or company property | - Financial loss - Damage to company/department reputation - Loss of employee's confidence | n.a. | XY | Other | High | 0.4 | 10% | 0.1 | threat | 0.04 | Financial loss is usually negligible, since no valuables (> 2500 EUR) are stored in the office area. Damage to reputation and loss of confidence must be counteracted with appropriate measures. Theft of data and documents is dealt with in a separate point | 2500 | 0 | Mitigate | - Develop a security and access concept and review it annually. - point out to employees that valuables are stored securely or locked away - … | 2020-10-31 | not started | 2020-07-30 | High | 0.4 | 10% | 0.1 | 0.4 | 0.1 | 0.04
3 |  | Budget | Formation of project-team is boosted by shortening forming- through norming-phases. | PIA Workshop has been leveraged to clarify scope and create commitment of project-team and -sponsors. | Project-goals and interdependencies of deliverables are known prior to realization, avoiding rework and shortening coordination-efforts. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
4 |  | Engineering | Missing approval of customer specification (LH) or insufficient communication between project and customers or sponsors | Rework of already produced and reassessment of planned deliveriables. | Scope-changes during or after realization. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
5 |  | Resources | Staffing of Resource has not been confirmed / resource has been reprioritized. | Unavailability of bottleneck-resource. | Deliverables are delayed, potentially affecting Go-Live. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
6 |  | Quality | Test-activities have not been planned correctly or require more time than initially estimated. | Test-plan does not meet test-requirements of deliverables. | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
7 |  | Schedule | Test-activities have not been planned correctly or require more time than initially estimated. | Test-plan does not meet test-requirements of deliverables. | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
8 |  | Legal & Compliance | Lack of experience to assess GDPR compliance of performance specifications during Requirements Analysis and Design. | Deliverables may not be compliant with GDPR-requirements. | Litigation activities are brought against the company (in public), resulting in financial or reputational loss. | [8 empty] | #VALUE! | [14 empty] | #VALUE!
9 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
10 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
11 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
12 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
13 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
14 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
15 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
16 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
17 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
18 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
19 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
20 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
21 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
22 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
23 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
24 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
25 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
26 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
27 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
28 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
29 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
30 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
31 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
32 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
33 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
34 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
35 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
36 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
37 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
38 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
39 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
40 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
41 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
42 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
43 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
44 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
45 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
46 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
47 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
48 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
49 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
50 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
51 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
52 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
53 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
54 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
55 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
56 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
57 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
58 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
59 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
60 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
61 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
62 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
63 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
64 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
65 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
66 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
67 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
68 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
69 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
70 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
71 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
72 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
73 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
74 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
75 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
76 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
77 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
78 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
79 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
80 | [13 empty] | #VALUE!
81 | [13 empty] | #VALUE!
82 | [13 empty] | #VALUE!
83 | [13 empty] | #VALUE!
84 | [13 empty] | #VALUE!
85 | [13 empty] | #VALUE!
86 | [13 empty] | #VALUE!
87 | [13 empty] | #VALUE!
88 | [13 empty] | #VALUE!
89 | [13 empty] | #VALUE!
90 | [13 empty] | #VALUE!
91 | [13 empty] | #VALUE!
92 | [13 empty] | #VALUE!
93 | [13 empty] | #VALUE!
94 | [13 empty] | #VALUE!
95 | [13 empty] | #VALUE!
96 | [13 empty] | #VALUE!
97 | [13 empty] | #VALUE!
98 | [13 empty] | #VALUE!
99 | [13 empty] | #VALUE!
100 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
101 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
102 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
103 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
104 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
105 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
106 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
107 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
108 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
109 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
110 | [13 empty] | #VALUE!
111 | [13 empty] | #VALUE!
112 | [13 empty] | #VALUE!
113 | [13 empty] | #VALUE!
114 | [13 empty] | #VALUE!
115 | [13 empty] | #VALUE!
116 | [13 empty] | #VALUE!
117 | [13 empty] | #VALUE!
118 | [13 empty] | #VALUE!
119 | [13 empty] | #VALUE!
120 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
121 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
122 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
123 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
124 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
125 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
126 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
127 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
128 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
129 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
130 | [13 empty] | #VALUE! | [14 empty] | #VALUE!
Insert Rows Above This Line Only
Warning: Be careful adding/removing rows in the following section - these values are used for data validation
Risk Category
Technology, R&D
Engineering
Manufacturing
Quality
Strategy & Portfolio
Budget
Schedule
Resources
Supply Chain
Market & Competitors
Customers
Raw Materials
Stakeholder Relations & Public Affairs
Intellectual Property
Legal & Compliance
Ecosystems & Ethics
Security & Data Protection
Risk Source
Formal Risk Review
SQA Audit/Review
Status Meeting
Stakeholder
Other
Impact Values
|  | Very Low | 0.05
|  | Low | 0.1
|  | Moderate | 0.2
|  | High | 0.4
|  | Very High | 0.8
Probability Values
|  | 10% | 0.1
|  | 30% | 0.3
|  | 50% | 0.5
|  | 70% | 0.7
|  | 90% | 0.9
Green/Yellow/Red Threshold Values
|  | Green - maximum score | 0.05
|  | Yellow - minimum score | 0.06
|  | Yellow - maximum score | 0.14
|  | Red - minimum score | 0.15
Risk Strategy
Avoid
Transfer
Mitigate
Accept
Exploit
Enhance
Share
Status
not started
in progress
on hold
implemented
cancelled
Note on E4: Which issues could lead to the risk event?
Note on F4: When exactly does a threat become a problem repectively an opportunity become an occasion?
Note on G4: What would be the consequences?
Note on H4: If the risk event can be linked to an exact or latest date.

## Matrix
Risk Register | [14 empty] | Matrix (initial) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS | [52 empty] | Matrix (actual) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS
Probability & Impact Matrix (initial)
Probability |  | Threats |  |  |  |  | Opportunities | [9 empty] | Green/Yellow/Red Threshold Values | [52 empty] | Green/Yellow/Red Threshold Values
| 0.9 | [16 empty] | Green - maximum score |  |  | 0.05 | [49 empty] | Green - maximum score |  |  | 0.05
| 0.7 | [16 empty] | Yellow - minimum score |  |  | 0.06 | [49 empty] | Yellow - minimum score |  |  | 0.06
| 0.5 | [16 empty] | Yellow - maximum score |  |  | 0.14 | [49 empty] | Yellow - maximum score |  |  | 0.14
| 0.3 | [16 empty] | Red - minimum score |  |  | 0.15 | [49 empty] | Red - minimum score |  |  | 0.15
| 0.1 |  |  |  | 1;2;
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
Impact
Probability & Impact Matrix (actual)
Probability |  | Threats |  |  |  |  | Opportunities
0.9
0.7
0.5
0.3
| 0.1 |  |  |  | 1;2;
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
|  | Impact | [15 empty] | P-I # threat | [24 empty] | P-I # opportunity | [27 empty] | P-I # threat | [24 empty] | P-I # opportunity
[18 empty] | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 |  |  |  | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5
|  | Risk ID | Risk Category |  | Matrix Score | Threat / Opportunity | quantitative impact [€] | risk strategy | owner | reporting date | status | Cause | Effect | Matrix Score (actual) | Impact | Probability |  | P-I # threat 4-4: 1;2; | [25 empty] | Impact (actual) | Probability (actual) | [24 empty] | 1;2;
|  | 1 | Strategy & Portfolio |  | 0 | threat | High | Mitigate | XY | 0 | not started | Scope-creep, additional budget requirements, or delays have not been assessed against initial project-goals. | Problem-statement for selection of project is not fulfilled. | 0.04 | 0.4 | 0.1 | gn | [50 empty] | 0.4 | 0.1 | gn | [23 empty] | 1; | bar: P-I # threat 4-4
|  | 2 | Security & Data Protection |  | 0.04 | threat | High | Mitigate | XY | 2020-07-30 | not started | - Unauthorized person has access to the office rooms - There are no reception staff in building xx - Access control only via badge reader - Office entrance doors close slowly - Office entrance doors are temporarily wedged open - Cash sometimes lies around openly | - Financial loss - Damage to company/department reputation - Loss of employee's confidence | 0.04 | 0.4 | 0.1 | gn | [50 empty] | 0.4 | 0.1 | gn | [23 empty] | 2; | bar: P-I # threat 4-4
|  | 3 | Budget |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Formation of project-team is boosted by shortening forming- through norming-phases. | Project-goals and interdependencies of deliverables are known prior to realization, avoiding rework and shortening coordination-efforts. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 4 | Engineering |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Missing approval of customer specification (LH) or insufficient communication between project and customers or sponsors | Scope-changes during or after realization. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 5 | Resources |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Staffing of Resource has not been confirmed / resource has been reprioritized. | Deliverables are delayed, potentially affecting Go-Live. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 6 | Quality |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Test-activities have not been planned correctly or require more time than initially estimated. | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 7 | Schedule |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Test-activities have not been planned correctly or require more time than initially estimated. | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 8 | Legal & Compliance |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Lack of experience to assess GDPR compliance of performance specifications during Requirements Analysis and Design. | Litigation activities are brought against the company (in public), resulting in financial or reputational loss. | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 9 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 10 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 11 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 12 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 13 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 14 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 15 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 16 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 17 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 18 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 19 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 20 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 21 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 22 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 23 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 24 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 25 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 26 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 27 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 28 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 29 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 30 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 31 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 32 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 33 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 34 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 35 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 36 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 37 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 38 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 39 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 40 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 41 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 42 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 43 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 44 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 45 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 46 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 47 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 48 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 49 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 50 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 51 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 52 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 53 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 54 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 55 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 56 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 57 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 58 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 59 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 60 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 61 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 62 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 63 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 64 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 65 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 66 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 67 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 68 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 69 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 70 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 71 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 72 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 73 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 74 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 75 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 76 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 77 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 78 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 79 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 80 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 81 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 82 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 83 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 84 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 85 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 86 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 87 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 88 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 89 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 90 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 91 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 92 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 93 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 94 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 95 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 96 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 97 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 98 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 99 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 100 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 101 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 102 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 103 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 104 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 105 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 106 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 107 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 108 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 109 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 110 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 111 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 112 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 113 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 114 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 115 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 116 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 117 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 118 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 119 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #VALUE! | [52 empty] | z
|  | 120 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 121 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 122 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 123 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 124 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 125 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 126 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 127 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 128 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 129 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
|  | 130 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | #VALUE! | [52 empty] | #VALUE!
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [51 empty] | 0 | 0
END OF MATRIX DATA (max 130 records)
Impact Values
| Very Low | 0.05
| Low | 0.1
| Moderate | 0.2
| High | 0.4
| Very High | 0.8
Probability Values
| Very Low | 0.1
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very High | 0.9
Green/Yellow/Red Threshold Values
| Green - maximum score | 0.05
| Yellow - minimum score | 0.06
| Yellow - maximum score | 0.14
| Red - minimum score | 0.15