I. Overview and Foundational Principles of Carve-Out/Divestiture Projects

A Carve-Out project involves a parent company separating parts of its business to a child company (often a NEWCO) with the intention of selling it, while the parent retains the remaining parts. This process necessitates the identification and provision of various IT-related components to the child company, including IT systems, applications, solutions, data, IT organization and employees, assets, contracts, IT licenses, and IT Security.

Key Characteristics and Influencing Factors:

• Uniqueness of Each Project: Every Carve-out project is inherently different, meaning there is "no standard – just guiding principles!".

• Business-Driven IT: A core principle is that "IT should follow business".

• Influencing Conditions: The Carve-out approach is heavily influenced by several general conditions:

◦ Whether it's a completely or partly business Carve-out.

◦ The type of deal: Share deal, asset deal, or a combination thereof. Definitions for share and asset deals are typically referenced from sources like Wikipedia.

◦ The extent to which processes are Shared Services or completely independent.

◦ The level of standardization and centralization of processes.

◦ The complexity of the IT landscape, including the number of systems, internal/external interfaces (e.g., EDI), and the level of system harmonization.

◦ Security premises.

◦ Clear definition of the target solution, whether internal or by an investor.

◦ Separation of infrastructure, shared buildings, and the overall location concept.

◦ The available timeframe and the policy on Transitional Service Agreements (TSAs).

◦ The definition of corporate directives (CDs) and General Framework (GF) regulations that need to be aligned, copied, or used during the project and after closing.

Common Challenges:

Carve-out projects present significant IT-related challenges across several domains:

• IT Organization & People: Managing the transition and transfer of IT personnel.

• Transitional Service Agreements (TSAs): Defining, implementing, and managing these agreements, which Bosch aims to limit.

• IT Applications, Systems, and Solutions: Separating and establishing independent application landscapes.

• IT Contracts, Assets, and Licenses: Untangling and re-establishing these for the new entity.

• IT Infrastructure & Security: Building new, independent infrastructure and robust security frameworks.

• IT Carve-out Project Management: The overall coordination and steering of these complex initiatives.

Models of Implementation:

The degree of independence the carved-out object achieves defines different basic models:

• Model 1 ("Stand Alone"): The Carve-out object aims for complete independence from the parent group. This requires building up an entirely independent process and IT landscape, optimized for a medium-sized company, and completely separating from the global application landscape and network. Examples include DC Pneumatics, SG, and PA. This model results in an "independent, separate, completely (separate), no shared services" entity.

• Model 2 ("Integration with Buyer"): The buyer of the Carve-out object takes the lead in executing the carve-out project and integrating it into their own application and system landscape. The parent company (Bosch) may provide optional access to its systems and applications during a transition phase via TSAs. Examples include DC ORA (Disposal Ober-Ramstadt) and BT – HCTM.

• Model 3-x: This represents a combination of Model 1 and Model 2, such as in the case of DC Large Gear.

The complexity of these models can be mapped against the initial state of integration at the seller, ranging from one site with less integration to multiple sites with high integration and shared services.

Typical IT Framework Conditions at Bosch:

Bosch's existing IT environment often poses specific challenges for carve-outs due to its nature:

• High Integration: IT systems and applications are highly integrated within Bosch.

• Complex Interfaces: Interfaces between systems are complex, making each carve-out unique.

• Multiple Systems for One Purpose: E.g., multiple ERP systems.

• SAP Cloning Limitations: Cloning SAP systems is often not possible or only partially possible due to proprietary processes or multiple systems.

• Non-Assignable Master Data: Master data may not be clearly assignable to the NEWCO.

• Centralized Collaboration Platforms: A single Intranet/Social Collaboration Platform for all business.

• Security and GDPR Dependencies: Security and GDPR aspects are deeply intertwined with the parent company (RB).

Special Use Cases / Scenarios for Carve-Out Execution:

Beyond the basic models, specific scenarios define the approach to IT separation:

• Pure Data Transfer (Scenario 1): Involves no handover of running IT systems. Only cleaned hardware may be transferred, but without installations. Applications and ERP/Engineering systems are not transferred, only extracted/exported data. HR data transfer is minimal. Unstructured data (file shares, SharePoint) is handed over. No licenses or contracts are transferred (only asset buyout). No new IT organization or processes are set up. This scenario is possible when a strategic decision is made, an external implementation partner is involved, and the buyer has its own target IT landscape. It suits small entities with simple, non-time-critical, or stopped businesses.

• Solution Green Field (Scenario 3): Existing hardware can be reused but requires re-imaging for the new infrastructure. Business-owned applications are reused but reinstalled. ERP systems are changed (downsized) to necessary functionality and modern technology. Operation processes are adapted (e.g., cloud-based). HR systems and processes are chosen and adapted. Unstructured data is migrated to target systems with new security concepts. Licenses and contracts are renewed. A new IT organization and new IT processes are set up. This approach is chosen when the existing infrastructure is outdated or the business needs significantly change. It requires external implementation partners with new technology expertise. It's suitable for small/midsize entities with reduced, less complex processes.

Next Step Suggestion: Given the foundational understanding, it is crucial to clearly define the overall Carve-Out target, the type of deal (e.g., share vs. asset), and the high-level strategy (e.g., Model 1 vs. Model 2) as these will dictate the subsequent IT Carve-Out approach and complexity.

--------------------------------------------------------------------------------

II. Project Scope, Target, and Organization

Defining the project scope is the first crucial step, involving the presentation of the project and its key information, as well as clarifying the objectives of the Carve-Out/Divestiture.

Key Project Data and Information Collection:

To effectively scope the project, the following data points must be collected:

• Number of Locations / Countries: A quantitative understanding of the geographical spread.

• List of Locations: A detailed inventory of all affected physical sites.

• Number of Employees: Critical for sizing IT requirements and HR considerations.

• Involved Legal Entities: Identifying all legal entities subject to the carve-out.

• Internal Information: Research internal data about the target from Bosch systems such as Master RAP, CMDB, LeanIX, and sydoku.

Project Framework and Dependencies:

Several external and internal factors establish the project's boundaries and interdependencies:

• Dependencies to RB Shared Services: Understanding reliance on central services (e.g., GS, SO, HR).

• Existing Projects: Awareness of running IT and non-IT projects that might overlap or conflict.

• Regional / Country-Specific Topics: Special considerations due to local laws, customs, or infrastructure. This includes:

◦ Military Use, Dual Use: Special classifications that may impact technology transfer or export controls.

◦ Customer-Specific Certifications: E.g., TISAX for VW platform data exchange.

◦ Country-Specific Legal Requirements: Such as unique tax laws in Brazil or specific regulations in Mexico.

◦ Local IT Solutions: E.g., specific solutions in India (RBIN).

◦ Data Protection and Privacy: Compliance with regulations like GDPR and AVV.

• External Service Providers:

◦ Involvement: Identifying and engaging external service providers/preferred suppliers (e.g., Comline, BGSW/SDS, SNP).

◦ Role of BGSW-SDS: Clarifying their role for IT services and operational responsibility (Infrastructure, Eng., Appl., etc.).

◦ Purchasing: Defining the role of central/local purchasing for IT project demands.

◦ IT Security Assessment: Checking for special IT security issues and the possibility of a 3rd party assessment (e.g., CyberCompare, KPMG, ETAS).

Defining the Future IT Organization and Processes:

A critical aspect of the scope involves designing the future state:

• Future IT Organization: Defining its structure, roles, and responsibilities.

• Transfer of IT Personnel: Planning for the movement of IT staff.

• IT Tools and Processes: Establishing the new set of tools and processes for the target entity. This definition of the Target Operating Model (TOM) and IT organization is primarily the responsibility of the target organization, with consultancy from the parent company (e.g., CI/MI).

Next Step Suggestion: Conduct a comprehensive data collection phase, leveraging tools like Master RAP and CMDB, to gather all "Project Key Data" and identify all "Project framework and dependencies" to build a detailed "as-is" picture, which is essential for any subsequent analysis and planning.

--------------------------------------------------------------------------------

III. Guiding Principles

Guiding Principles are paramount for directing the entire Carve-out project, ensuring alignment and efficient execution.

Definition and Approval Process:

• Overall Guiding Principles: These must be defined by the overall project lead (C/COA) and reconciled with all involved workstreams.

• IT Guiding Principles: These are derived from the overall principles and require agreement/approval from the overall project lead and the business unit (BV) of the Carve-out object.

• Early Definition: Principles should be defined within the first phase of the project, typically 1-2 months after the start.

• Deviation: Any deviation from the guiding principles must be commonly agreed upon.

• Initial Assessment: Every Carve-Out project should undergo an initial assessment workshop.

Overall Guiding Principles (from source 17-40):

• Target Clarity: Clear definition of the Carve-Out target, including the type of deal (Share Deal, Asset Deal, etc.).

• Schedule Clarity: A clear statement concerning the Carve-Out schedule.

• Roles & Responsibilities: Clearly defined roles and responsibilities within the overall project (triangle: overall project lead, target object management, and IT workstream).

• TSA Policy: A fixed policy for Transitional Service Agreements (TSAs). Bosch's policy is generally restrictive, providing TSAs only in exceptional cases and for a limited time.

• Foundation in Analysis: "No Carve-Out project without a study or detailed as-is analysis".

• Project Office: Build up a highly capable Project Office.

• Full-Time Project Managers: Main project roles should be covered by full-time project managers.

• Early Stakeholder Involvement: Engage all stakeholders worldwide early in the process.

• Adaptability: Expect high dynamism and be prepared to handle "moving targets" daily.

• No Optimization for Optimization's Sake: Optimization should only occur if it accelerates or simplifies the carve-out or significantly reduces costs.

• Dedicated Resources: Carve-Out Costs and Resources must be planned and assured in addition to, and outside of, Business As Usual operations.

• Data Management: Mandatory data deletion / anonymization (business, engineering, IT data) requires a defined data deletion concept, aligned with all stakeholders.

• Regulatory Compliance: Define corporate directives (CDs) and General Framework (GF) regulations that need to be aligned, copied, or used within the project duration and after Closing.

Guiding Principles for the IT Workstream:

The IT workstream operates under specific guiding principles to ensure a focused and pragmatic approach:

• Business Enablement First: "First enable the business, optimization will follow in a second step" – the mantra is "First make it work, then make it better".

• Lean Solutions: Aim for "no 100% solution, target should be as lean as possible".

• Holistic View: A "360-degree view on IT and business processes, methods and procedures is from the early beginning mandatory".

• Business Process Expertise: IT project managers must possess high business process expertise and a common understanding of the entire business model of the carved-out part.

• Day-1 Readiness: The primary focus is on achieving "stable day-1-readiness after closing".

• Target Operating Model (TOM): The Target Operating Model and IT organization must be defined, mainly by the target organization with consultation from the parent (e.g., CI/MI).

• Pragmatism over Optimization: Carve-out "does not explicitly focus on improving current processes or standards – Pragmatism is key, i.e. 'Copy & Paste' from existing processes where possible". If changes are required, the target structure should reflect the appropriate requirements of a medium-size company.

• Reuse Standard Solutions: Utilize existing standard solutions (e.g., CWP, APM with XFT, HR Carve-Out factory, GTS, SNP T-Bone for ERP systems) to reduce effort, time, and budget.

• Post-Closing & Clean-up: Define and plan post-closing activities and related clean-up tasks with sufficient lead time. These are typically the responsibility of the involved business unit (RB-GB), with support/consultation from the parent company's M&A integration team (CI/MI).

Lessons Learned in Guiding Principles:

Experiences from past projects offer valuable insights:

• Prioritize Complexity: "Make the difficult part of the project at first (complexity first, standard topics follow)."

• Long-Term View: Avoid focusing solely on "low hanging fruits for an easy success story" as carve-outs are long endeavors.

• Clear Requirements: Project teams must clearly understand their tasks at project, technology, and process levels, based on defined customer requirements.

• Migration Rule Complexity: Defining migration rules is extremely challenging due to influencing factors like deal type (share vs. asset), tax conditions, HR issues, and local laws.

• Legal Entity Alignment: No IT System (ERP) should operate without an independent legal entity, and HR rules must be followed country-by-country.

• Data Reconciliation: It must be possible to reconcile data from retained and separated businesses back to their original source, proving that separation did not alter relevant content.

Next Step Suggestion: Formalize both the overall and IT-specific guiding principles, obtaining documented approval from all relevant project leads and stakeholders, to ensure a unified direction for the project.

--------------------------------------------------------------------------------

IV. AI/Industry 4.0

The assessment of Artificial Intelligence (AI) and Industry 4.0 (I4.0) capabilities is critical for understanding the technology landscape of the target company.

Assessment Questions for AI/I4.0:

• AI Usage:

◦ Is AI currently in use at the target company?

◦ If yes, where is the AI environment located (internal, external hosted)?

◦ Is the AI environment used by other units, or is it standalone for the target?

• Industry 4.0 Related Systems and Processes:

◦ Are I4.0 related systems and processes in place at the target company?

◦ If yes, provide a detailed description of these systems, services, and processes (e.g., predictive maintenance, process automation).

• General Aspects:

◦ Provide an overview (design sketch) of the AI/I4.0 environment.

Next Step Suggestion: Conduct a dedicated workshop with relevant technical and business experts from the target company to answer these AI/I4.0 assessment questions and produce a preliminary design sketch of their environment, identifying potential interdependencies or separation challenges.

--------------------------------------------------------------------------------

V. Infrastructure

The IT Infrastructure workstream is a cornerstone of any carve-out, encompassing a wide array of services and components that need to be separated, migrated, or rebuilt.

Detailed Infrastructure Assessment Areas:

• WAN (Wide Area Network):

◦ WAN Concept.

◦ Provider Management.

◦ RAS-VPN Solution (Remote Access Service - Virtual Private Network).

• LAN (Local Area Network):

◦ LAN & Wi-Fi Concept.

◦ IP Address Concept.

◦ Network monitoring.

• NW-Services, ADS (Network Services, Active Directory Service):

◦ Active Directory Service.

◦ Domain Name System (DNS).

◦ DHCP (Dynamic Host Configuration Protocol).

◦ Group-Policies.

◦ Certificates.

◦ Proxy-Server.

◦ Firewalls, DMZ (Demilitarized Zone for Internet-facing applications).

◦ IT security governance.

• Mail:

◦ E-Mail-Server Concept.

◦ Migration Concept.

◦ E-Mail Archiving.

◦ E-Mail encryption.

• Server Storage:

◦ Data Center Concept, including definition of central data center.

◦ NAS Storage (Network Attached Storage).

◦ Server Infrastructure.

◦ ESX Systems (VMware vSphere hypervisor).

◦ Patch management.

◦ VDI / 3DVDI environments (Virtual Desktop Infrastructure / 3D VDI).

◦ Antivirus Protection.

• Client Environment:

◦ Future Client Workplace concept.

◦ Client Migration Concept.

◦ Software distribution Infrastructure.

◦ Client Application Packaging.

◦ Patch management.

◦ Antivirus Protection.

◦ Client security & Hard Disc encryption.

◦ Cloud/Virtual Workplace - User Access & Permission.

◦ IDE / IBC Clients.

• Backup:

◦ Backup Concept.

◦ Archiving.

• Telephony (Skype for Business / Public Telephony / MS Teams / PABX):

◦ Telephone Concept.

◦ Local lines (PTST - Public Switched Telephone Network).

◦ Provider management.

◦ Skype for Business Conferencing.

◦ MS Teams Implementation.

◦ PABX Management (Private Automatic Branch Exchange).

◦ Migration and Carve-Out concept.

◦ Call Center setup.

• Infrastructural Applications:

◦ Database Services (MS-SQL, Oracle).

◦ SharePoint.

◦ Print-Service.

◦ RFID Printing (Volume, Technology, Products, etc.).

◦ Scan-Service.

◦ System-Monitoring.

◦ File-Shares.

• Support Services:

◦ Service contract strategy.

◦ Hotline provision.

◦ 1st, 2nd, 3rd level support structure.

◦ User training.

◦ Identity Management - IdM / AIM.

◦ CI-CAT (asset management system) - site, SMT (Service Management Tool), printer setup.

◦ ITIL based process implementation.

◦ Chatbot solutions.

• IT Security:

◦ IT security concept (potentially externally ordered, e.g., KPMG).

◦ IT security governance.

◦ WS IT relevant aspects of the IT Security concept.

Cloud Solutions / Services (Infrastructure Focus):

This area is particularly complex and requires dedicated attention.

• Platforms Used: Identify all cloud platforms in use (e.g., Azure, AWS, Google Cloud, Bosch, IBM).

• Departmental Usage: Determine which departments use these platforms (e.g., Infrastructure, Engineering).

• Migration Strategy: Decide if cloud applications need to be migrated or if new solutions will be built.

• Application Ownership: Identify responsible parties for cloud applications.

• Bosch Service Connections: Determine if cloud applications are connected to other Bosch services.

• Overall Cloud Strategy: Assess if a "cloud-only" strategy exists.

• External Service Providers: Identify any external service providers involved in cloud migration or operation.

• Future Operation: Define who will handle future service operations.

• Azure Service Replacement: Evaluate if any services can be replaced by Microsoft Azure services (e.g., Mail encryption, Printing, Anti Virus, SCCM, Telephony).

• Backup / Archiving: Determine if a backup/archiving solution is required for cloud data.

• Microsoft Azure Specifics:

◦ Services to Migrate: Identify specific Azure services requiring migration (M365, IoT, Power Automate, Databases, AI, Web services, Printing).

◦ Subscriptions: List company subscriptions.

◦ Tenant Configuration: Define the future internet domain, identify enterprise applications used in Azure, and determine required licenses (number and type). Current Bosch security requirements must also be considered.

◦ Azure Active Directory (AAD): Identify AAD-only accounts or groups to migrate, and assess external access requirements.

◦ Exchange: Detail mailbox migration (Resource, Shared, Personal), distribution lists, data volume, and local SMTP gateway usage.

◦ Teams: Identify Teams rooms requiring migration and determine if public telephony needs to be implemented.

◦ OneDrive / SharePoint: Assess data volume for OneDrive sites and identify SharePoint Online/on-premise sites in scope. Determine if an on-prem SharePoint is still required.

◦ Intune (MDM): Determine if the company uses internet clients, identify Intune application packages to migrate, list required applications for publishing, and devices to migrate.

◦ Other Azure considerations: Hybrid infrastructure (Exchange, Azure Active Directory), Multi-Factor Authentication migration, Antivirus protection, Azure Cloud Printing, and other applications (Workflow replacement, Automation).

• Other Cloud Providers: Similar considerations for AWS and Google Cloud Services.

Next Step Suggestion: Prioritize the infrastructure components based on criticality and interdependencies, starting with WAN/LAN and core network services, to ensure foundational connectivity is established early, as these have long lead times.

--------------------------------------------------------------------------------

VI. Client Workplace (CWP)

The Client Workplace Environment assessment focuses on how end-user devices and their management will be handled in the carved-out entity.

Assessment Details:

• Client Software Management:

◦ Concept for client software management (e.g., SCCM - System Center Configuration Manager).

◦ Operating System Deployment.

◦ Client Software Application Packaging.

◦ Software Product Management (SPM As a Service).

◦ Virus Protection for Clients.

◦ Client Hard Disc Encryption (e.g., MS-Bitlocker).

◦ User & Group Validation & Synchronization.

◦ Client Migration strategy.

• Overall Information:

◦ Carve-Out Approach: Understanding the overall approach (e.g., Greenfield, Turnkey) is crucial for determining options and potential scenarios.

◦ Duration: The overall planned duration of the project in months from start until closing.

◦ Sites in Scope: The number of different sites affected influences future Client Workplace Management.

◦ Clients / IT-Users Affected: The number of clients and IT-users provides an indication of possible migration scenarios and their complexity.

• Client Hardware Devices:

◦ Hardware Models: Number of different client hardware models currently in use, as diversification affects effort for device driver integration.

◦ Out Of Support Hardware: Number of devices that will run "Out Of Support" until the planned closing, as these might need replacement during the project.

◦ Internet Based Clients: The number of "Internet Based" clients (e.g., IDE, Open Source Desktop) used, which influences the overall client workplace strategy.

• Client Software Application Packages:

◦ Number of business-specific software application packages required.

Next Step Suggestion: Based on the "Carve-Out approach" and the number of affected users, prioritize defining the future "Client Workplace Concept" and initiate planning for "Client Migration," considering hardware lifecycle management and software packaging requirements.

--------------------------------------------------------------------------------

VII. ERP Environment

The Enterprise Resource Planning (ERP) environment is typically one of the most complex areas in a carve-out due to its deep integration into business processes.

Comprehensive ERP Assessment Areas:

• Overview:

◦ As-is system landscape, including structure models.

◦ Sydocu information.

◦ Current SAP architecture of the selling legal entity.

• SAP ERP Systems - Strategic Approaches:

◦ SAP Relocation:

▪ Relocation of all dedicated target SAP systems (productive, D/Q/Test) from the parent company's data center to a new one, including connected Content Servers.

▪ Setup of new required systems.

▪ Change of server names (keeping hostname, changing domain and IP addresses).

▪ Adaptation and testing of all interfaces; defining and triggering changes in UC4 jobs.

▪ Setup of new SAP Fileserver/FTP Server and migration of users, authorizations, and jobs.

▪ Decision on keeping "Display Copies" for the parent company if required.

▪ Identification of relevant legacy SAP systems and clarification of their solution (information/access rights, relocation/migration).

▪ Replacement of existing middlewares with direct connections if required and possible.

▪ Coordination of changes in SAPLogon.ini (SAPGUI).

▪ Definition of new operational processes (incident management, change management, problem management).

▪ Handover of operation from current provider (e.g., CI) to the target entity.

◦ SAP Carve Out (System Split):

▪ Analysis of which SAP systems are involved and need splitting or from which a carve-out needs to be done.

▪ Consideration if RB India is involved, necessitating a carve-out from P47.

▪ Decision on carve-out/migration strategy per system (e.g., SNP Tool, LSMW).

▪ Clarification of SNP software license/maintenance.

▪ If ERP migration, use a rough Migration Data View.

▪ Decision on migration of historical data (which data, for how many years).

▪ Definition of target SAP platform (DB/OS), location (datacenter), operation, SIDs, and request for system IDs.

▪ Definition of target job scheduling solution (new setup or job migration from UC4).

▪ Replacement of existing middlewares with direct connections.

▪ Coordination of changes in SAPLogon.ini.

▪ Definition of new operational processes.

▪ Clarification/handover of operation to the target entity.

◦ SAP Greenfield:

▪ Feasibility assessment: How critical is ongoing business (production, delivery, ordering)? Are key users available to define, test, and release new processes? How complex are the used processes (is a simplified version possible, e.g., public cloud)?.

• Non-SAP ERP Systems:

◦ Analysis of which systems need to be changed/relocated to operate standalone.

◦ Definition of responsible user department (UD) and IT person for each system.

◦ Coordination of all relocation/change activities: relocating systems, changing server names/IPs, adapting/testing interfaces, handing over operation, defining new processes.

• Replacement of SAP Environment Systems (Central Solutions):

◦ Reporting SAP BW: Define required reporting (SAP BW or alternative), including SAP ERP internal reporting or MS SQL-Server as Data Warehouse (ETL, Power BI). Analyze Day 1 reporting requirements (prioritized, mandatory). Order support for EDL. Synchronize with the ERP/SAP project.

◦ SAP BO (Business Objects): Replace Bosch central SAP BO with a new solution (own BO), check AddOns (e.g., graphomate). Ensure system connection between BW backend and BO platform works and all existing BW backend source systems function. Implement authorization concept and create users for the new BO platform.

◦ SAP CRM: Replace Bosch central/GB SAP CRM with a new solution (own CRM Tenant), check AddOns. Ensure system connections between ERP backend and CRM platform. Implement authorization concept and create users.

◦ SAP FSM (Field Service Management): Replace Bosch central/GB SAP FSM with a new solution (own FSM Tenant), check AddOns (e.g., proaxia, middleware). Ensure system connections between ERP backend and FSM platform. Implement authorization concept and create users.

• SAP Further Tools & Systems: Assessment for systems like SAP BODS, SAP TREX, SAP EWM, SAP APO, etc..

• Replacement Central PUR Solutions (Purchasing):

◦ Replace Bosch eProcurement solutions (eCAT, BonaPARTe), Bosch SRM solutions (RB-SRM, PDM-Lookup), Bosch PUR Reporting (MCR, PICOS).

◦ Consider implementing Purchasing directly in SAP ERP or a cloud solution like Jaggaer.

• Replacement Central FIN Solutions (Finance):

◦ APM (Accounts Payable Management): Define required functions and select a future tool. Analyze/define scope per entity/system. Define new process chain. Implement AddOn on target SAP. Train user department. Setup operations/support. Cancel contracts with current providers. Inform vendors of new invoice addresses.

◦ ICR (Intercompany Reconciliation): Determine if SAP-based ICR is required (consider number of legal entities, Excel alternative). Setup ICR on target SAP and test. Connect all relevant entities. Setup operations/support. Cancel contracts.

◦ FCC (Financial Closing Cockpit): Determine if SAP FCC is required (consider legal entities, Excel solution). Setup FCC on target SAP and test. Connect all relevant target legal entities and phase out from the parent's FCC. Setup operations/support. Cancel contracts.

◦ SSF (Self Service Framework - PDX): Setup/change process for SSF tickets. Determine if SSF is used for other workflows (e.g., travel expenses).

◦ Bosch Legal Consolidation: Determine if legal consolidation is required for the target entity (consider legal entities). Select and implement a target consolidation tool (e.g., LucaNet, replacing Bosch Hyperion Enterprise).

• Replacement SAP Foreign Trade Solutions (GTS):

◦ Europe SAP GTS: Identify modules used (Compliance - Export control/SPL-Screening; Customs - Export/Import/Intrastat; Preferential Determination). Consider copying the Bosch GTS system to the future GTS system (without data). Assess if historical data of P94 is required. Implement a cloud solution (e.g., Seeburger) for connection to ATLAS (customs authority).

◦ China: Replace Bosch FTS (EasyTMS) with a FTS cloud solution (e.g., PLATIN: Amber Road cloud; SG: IEM - Import Export Management).

• Replacement SAP Solution Manager: Mandatory for SAP hosting/operation environment; all SAP systems must be connected.

• Replacement of Master Data Distribution:

◦ Prepare the as-is master data distribution landscape.

◦ Setup a new target master data distribution landscape for all relevant master data (CoA, customer, supplier, material, exchange rates).

◦ Define new master data maintenance processes with the user department.

◦ Implement the new solution. Disconnect target systems from central master data systems (PMD, EBS customizing system CU9).

• Replacement of Bosch EDI Manager:

◦ Identify all ERP systems of the target using EDI (Bosch EDI platform, SupplyOn, or others).

◦ Define a new target solution for all EDI cases, considering Axway cloud as a potential solution (no new data mapping required).

◦ Setup new solutions. Migrate all relevant Classic EDI connections from Bosch EDI-Manager and Web EDI connections from SupplyOn to the new solution.

• Replacement of Bosch Treasury:

◦ Determine if the target consists of several legal entities. Implement a treasury system landscape to support the future target treasury organization.

◦ Example: Activate SAP Standard functionality (Cash & Liquidity Management, In-house Cash Management, Treasury and Risk Management). Implement a web-based Treasury Information Platform (TIP) for financial reporting and liquidity planning.

• SAP AddOns:

◦ External AddOns: Clarify continued use. Make necessary changes for AddOns not to be used (deactivation, declaration). MANDATORY action: delete TARIS AddOn via deletion transport if present (Y65K900116, P67K900811, DGCK912366 require uninstall U61K900336). Clarify license numbers.

◦ Bosch Developments (internal): Synchronize handover with relevant internal teams (e.g., CI/DAE). Trigger legal services (C/LS) for specific wording in SPA/APA regarding use of Bosch developments (no maintenance, no warranty, no further distribution). Organize SAP repair keys for developments in the RB namespace for closing.

◦ SAP Consulting Solutions (ACS/SCM): Check if any (used or unused) are in the target system. Involve internal teams (RBEI, CI/SXL) for checks. Potentially order a system check by SAP. Define procedures for deletion or licensing.

• SAP UC4 Job Scheduling:

◦ Overview of scheduled jobs in SAP systems used by the target.

◦ Decide on target solution: within SAP/manual execution OR an own UC4 system.

◦ If Scheduling in SAP: Identify and review all jobs of the target. Move UC4 jobs to SAP job scheduling or set up manual execution.

◦ If Own UC4 System: Setup UC4 system with relevant partners (e.g., OSA/RBEI). Migrate all SAP jobs from Bosch UC4 to target UC4. Setup new job application workflows. Organize operation of target UC4.

• SAP Printing and Forms (incl. Fax/SMS):

◦ Support the Infrastructure subproject in defining the future printing environment.

◦ Identify all required SAP printers (laser, ZEBRA, Electronic Barcode, print2email). Determine if RFID labels are in use (requiring LRS or other back channel).

◦ Setup a new ADS server environment. Plan and execute switch to new printing environment.

◦ Coordinate and change all SAP forms to fit the new printing environment. Define operations/support for SAP forms in the future (roles, internal/external support), clarifying CT Forms.

◦ Identify, plan, and execute required tests (especially for critical external forms). Change forms for externalization step (closing) if required. Check for FAX or SMS requirements and test/go-live the new environment.

• SAP Archiving:

◦ Setup the SAP side for the new SAP archive solution (Content Server + Archive HW).

◦ Identify all relevant objects of the target that need to be migrated from the content server and archive.

◦ Synchronize migration with SAP data migration (if SAP split/migration is required).

◦ Migrate relevant SAP data from Bosch Opentext/Ixos to the new archive.

◦ Support AP/M subproject to adjust the scan solution. Organize migration of Non-SAP data in Bosch Opentext/Ixos (Rasterarchive, longterm.archive, others).

• SAP User- and Authorization Management:

◦ Scope includes all target ERP systems, BW systems, and others.

◦ Review current processes and regulations for all SAP systems.

◦ Define standards & rules for future stand-alone operation of SAP user- and authorization management (e.g., no IdM, no Bosch SAP roles). Update authorization concepts.

◦ Update RB-AIS on all SAP systems to the most current version (4.1.5) if it will be taken over.

◦ Implement CUA (Central User Administration) system (e.g., on Solution Manager) for all target ERP systems, including disconnection from Bosch IdM system, if required.

◦ Perform "User Cleansing" to avoid unnecessary SAP license costs.

◦ Implement all required changes to user accounts (e.g., email-address, parameters).

◦ Support other subprojects for changes to SAP authorization (e.g., GTS system, BW, new functions in existing ERP). Disconnect from Apollo (based on SAP GRC AC).

• ERP Brazil:

◦ Determine if Brazil is in scope. If so, a solution for all Brazil-specific legal applications (e.g., nota fiscal) is required. Brazil has unique and complex tax laws (1.4 new regulations/day, 60 of 92 taxes applicable, 13x more complex than Germany or USA). Country Version BR is notoriously difficult to implement, affecting the entire process chain, not just billing/financials.

• ERP Environment Interfaces:

◦ Compile a list of all AS-IS interfaces, including technical details and responsible people.

◦ Identify interfaces to be changed/tested in each step of the carve-out.

◦ Compile a list of all TO-BE interfaces, including technical details and responsible people.

Next Step Suggestion: Initiate a series of deep-dive workshops for each major ERP sub-area (e.g., Finance, HR, Supply Chain), involving business process owners and technical experts, to fully map current processes and system dependencies and to begin defining the "to-be" state and migration strategy (relocation, carve-out, or greenfield) for each.

--------------------------------------------------------------------------------

VIII. Other Applications

Beyond ERP systems, a multitude of other applications are crucial for business operations and must be identified, assessed, and planned for during a carve-out.

General Identification and Assessment Process:

1. First Identification: Make an initial identification of "TOP applications".

2. Software Development: Assess the usage of Software & Coding Repositories.

3. Cloud Usage: Obtain a general overview of all used cloud solutions.

4. Data Source Collection: Start/continue collecting potentially relevant applications based on evaluation phase results. Utilize all available technical data sources (Master RAP, LeanIX, optionally Altiris/Smart Track, GE application database).

5. Master List Generation: Generate a first master list from existing data sources.

6. Elimination of Out-of-Scope: Conduct a general review to eliminate applications clearly not in project scope (e.g., Platin: PA-ATMO).

7. Expert Input: Add applications known by target IT people and BD/MIL people.

8. Local/Regional Review: Add applications after review with local/regional IT responsible parties.

9. Clustering: Cluster applications by assigning them to "IT subproject" and "functional work stream".

10. Responsibility Assignment: Define responsible parties for remaining "other applications" within each work stream to trigger and consult functional work stream leads.

11. Functional Work Stream Review: Send application lists per work stream to functional leads with a request to review and update (delete/add/comment).

12. Scope Approval: Ask work stream leads for "official" approval of this scope.

13. Identify TOP Applications: Identify the most critical applications (by size, cost, effort, duration, business criticality).

14. Project Management Approach: Decide on the project management approach for these applications (IT-PEP: project, SIA, others).

15. Staffing & Implementation: Staff identified TOP applications as soon as possible and begin implementation.

16. "Other Applications" Team: Staff a dedicated team for "Other Applications" and assign work packages.

17. Detailed Analysis: Start analyzing each application on the list using a questionnaire.

18. Final TOP Applications: Define the final set of TOP applications.

19. Decision per Application: Assign a status for each application:

◦ No further use (no WS IT activity).

◦ No further use (WS IT activity required, e.g., to keep/copy data).

◦ Keep (WS IT responsible).

◦ Keep (User department responsible).

◦ Replace (WS IT responsible).

◦ Replace (User department responsible).

20. Documentation & Approval: Document results/decisions and obtain final approval from functional work streams.

21. New Applications: Add "new applications" that are replacing existing ones to the "Other Applications" master list.

22. Communication: Communicate decisions for all applications.

23. Conception: Define implementation/migration concept for each application on the "Other Applications" master list. Document approach and responsible person.

24. Execution: Trigger execution of implementation/migration according to the master list and review status until all are finished and approved (including user department responsible apps).

Examples of Central Bosch Applications:

• Bosch Connect: Export possible (PDF format), using tool ICXT. Input from MasterRAP.

• SharePoint: Requires migration planning, including confirmation of associated sites, responsibles, and size. Discuss migration approach: Option 1 (move to target and delete in source) or Option 2 (copy to target and keep in source). User training is recommended, possibly with RBEI and a key user structure. A test SharePoint environment is helpful.

• Intranet pages / BGN (inside.portal): Manual export by the user department.

• Docupedia: Confluence cloud is an alternative. Be aware of Bosch-specific add-ons; analyze these for spaces needing migration and identify cloud alternatives. External suppliers (e.g., k15t) may be involved.

• Other Central Systems: WorkOn, Track&Release (Jira Atlassian), IdM, Ad Hoc Data Exchange, OpenDXM ProStep, B-CEPS, ISP Audit Tool, SOCOS (SharePoint cloud alternative for Kampina), PitFM, Normmaster, Travel & Expense Reporting, etc..

Examples of General Local Applications:

• Time Management/Recording & Attendance (e.g., Kronos).

• Access Control.

• Canteen Software.

• Cashless payment.

• MES (Manufacturing Execution Systems).

• Marketing Automation (e.g., DC, email-marketing).

Regional Specific Applications:

• India: Local Application Matrix India, including contact list (RBIN/ICO2).

• Brazil, Mexico, South-Africa, Canada: Placeholder, indicating region-specific applications must be identified.

Next Step Suggestion: Form a dedicated "Other Applications" core team, which will be responsible for leading the systematic identification, categorization, and decision-making process for all non-ERP applications, initiating with a broad data collection across all available sources.

--------------------------------------------------------------------------------

IX. Engineering

The Engineering workstream focuses on the specialized software, tools, and processes used for product design, development, and manufacturing.

Overview of Engineering Software/Tool Landscape:

A pictorial overview is crucial for understanding the complex interdependencies.

Key Categories for Assessment:

• CAD Software (Computer-Aided Design):

◦ Mechanical Software: SolidWorks, AutoCAD, Creo, Inventor, AutoDesk (PjM).

◦ Electrical Software: ePlan P8, E3.

• PDM Software (Product Data Management): DBWorks, PDMlink, iPLM.

• Visualization/Virtualization: 3D-VDI (3D Virtual Desktop Infrastructure).

• Other Engineering Software:

◦ Data Management/Collaboration: Windchill, PDM (Div. Products), OpenDXM (for data exchange with externals), Vault, SharePoint.

◦ Automation: Siemens - SIMATIC, Rockwell.

◦ Documentation/Content Management: Schema ST4, Across.

◦ Requirements Management: Doors, CRS (Customer Requirement Server).

◦ Product Configuration/Sales: Product Configurators, CPQ (Configure Price Quote), Product Information Management (PIM), Media Asset Management (MAM).

◦ Testing/Quality: HP ALM (Test Management).

◦ Analysis/Simulation: MathCAD, ANSYS, MatLab, Speedmaxx.

◦ Development Operations: Azure DevOps, Versiondog, Polarion, HypX Build, BomCreator.

◦ Maintenance/Operations: Uptime, MP2, BSP, Ultimo Cloud.

◦ Communication/Legacy: HCL Notes.

• Major Interfaces:

◦ Windchill - ERP.

◦ Interfaces to Externals.

◦ Infrastructure dependencies.

◦ Common use within RB/GB.

◦ License Usage (local/central).

Next Step Suggestion: Organize a workshop specifically for engineering leads and IT support personnel to map the complete "as-is" engineering software landscape, identifying critical interdependencies, unique customizations, and license implications, particularly for systems with major interfaces to ERP or external partners.

--------------------------------------------------------------------------------

X. HR

The Human Resources (HR) workstream addresses the systems and processes related to people administration, management, and analytics within the carved-out entity.

Main Processes / Functions and RB Systems:

• People Administration:

◦ Organizational Management: COMPAS.

◦ Position.

◦ Personal Administration.

◦ Payroll.

◦ Time Management: Mainly HR Core Solutions (P70 BOPAS, PH1).

◦ Personnel Data Sheet: HR Global.

• People Management:

◦ Recruiting: Smart Recruiters.

◦ International Assignments: HR Global.

◦ Succession Planning: HR Global.

◦ Career Development Dialogue: HR Global.

◦ Talent & Associate Review: HR Global.

◦ Goal & Performance Dialogue: HR Global.

◦ Competence Management: HR Global.

◦ Training Management: HR Global.

• Services & People Analytics:

◦ BI (Business Intelligence).

◦ Shared Service Management: HR Shared Service Framework (HR SSF).

◦ e-File: XFT.

◦ Document Management: XFT.

◦ Portal: MyHR.

HR Specifics & Regional Considerations:

• Legal Entity Rules: When dealing with IT systems (like ERP) for a new legal entity, strict HR rules must be followed country by country.

• Data Protection & Privacy: High effort is required for data protection and privacy, especially concerning HR data, due to regulations like GDPR and AVV.

• India: Specific classifications for blue-collared (factory workers) and white-collared (managerial staff) employees exist. Blue-collared workers are protected by union laws, and the Ministry of Labor oversees their interests.

• North America (USA): "Employment at will" is common, allowing dismissal without warning (unless illegal). Employees are typically not under contract unless part of a labor union.

• Mexico: Setting up a business as a maquiladora offers advantages like up to 100% foreign investment and special customs treatment.

Next Step Suggestion: Collaborate closely with HR leadership to map existing HR processes against the systems identified, prioritizing solutions for core "People Administration" functions (Payroll, Time Management) to ensure day-1 operational readiness, especially considering regional legal requirements.

--------------------------------------------------------------------------------

XI. Target IT Landscape: Organization & Processes

This workstream focuses on the strategic design and implementation of the future IT organization and its operational processes for the carved-out entity.

Key Activities:

• Define Future IT Organization: This involves outlining the structure, roles, responsibilities, and reporting lines of the standalone IT department. The Target Operating Model (TOM) and IT organization definition are primarily the responsibility of the target organization, with advisory support from the parent company's IT M&A team (e.g., CI/MI).

• Transfer of IT Personnel: Plan the process for transferring IT employees from the parent company to the new entity. This includes analyzing which employees are concerned, checking for internal transfer possibilities within the parent company, and defining a transfer strategy with the relevant HR departments.

• Define IT Tools and Processes: Establish the set of IT tools and operational processes that the new IT organization will use. This extends beyond applications to cover broader IT management processes.

• Operational IT Processes and Capacity:

◦ Analyze existing IT processes and capacity as part of the overall IT project.

◦ Ensure stable operations until closing or handover.

◦ Support the definition of support specifications for selecting external providers to improve the transfer from the "as-is" to the "to-be" state.

◦ Facilitate and support the operational part of the Carve-out process/project.

◦ Consult the sub-project for IT organization and operational processes.

◦ Potentially build up a "one IT organization" in the target for IT operations/management until closing, covering operations, cost, infrastructure, and application management, as well as contracts and processes.

◦ Provide consulting for IT operations if required, as part of TSA.

• IT Management Know-How: Provide expertise on operation standards, legality, and security.

• Project Support Roles: Provide support roles in Project Execution Plan (PEP) projects, such as Operation and Quality Manager.

• Recruitment Support: Support the target organization in recruiting IT staff, including defining role and task descriptions.

Guiding Principles for Target Operating Model:

• The IT workstream emphasizes a "360-degree view on IT and business processes, methods and procedures" from the start.

• The target operating model should reflect a lean and efficient organization, tailored to the size and complexity of the carved-out perimeter.

Next Step Suggestion: Initiate the development of a detailed "Target Operating Model (TOM)" for the carved-out entity's IT department, outlining its structure, key processes (e.g., incident management, change management, problem management), and the roles of transferred and newly recruited personnel, leveraging best practices from past projects.

--------------------------------------------------------------------------------

XII. Contracts and Licenses

Managing contracts and licenses is a critical and complex workstream in carve-outs, involving meticulous review, transfer, and renegotiation to ensure legal compliance and operational continuity.

Asset Classes and Licenses to Review:

• Bosch Software Licenses: All proprietary software licenses.

• Software Subscriptions: Any subscription-based software services.

• Hardware-related Licenses: Client PC, Printer, Server and Storage, Network Infrastructure (including WAN contracts).

• Telephony: Mobile Telephony / Cell Phones (contracts and hardware), Fixed Telephony (contracts, land lines, assets, including VoIP).

Outsourcing Contracts:

• Identify and analyze all outsourcing contracts relevant to the carved-out entity.

General Contracts:

• Software Contracts: E.g., Microsoft, SAP.

• Hardware Contracts: For servers, storage, printers, telephony, conference room equipment, etc..

• WAN Contracts: Specific Wide Area Network contracts.

• MES Contracts: Manufacturing Execution Systems contracts.

• Leasing Contracts: For clients (worldwide, regional, country-specific).

• Telephony Contracts: Including conference room equipment.

• Support and Maintenance Contracts: For various IT systems and hardware.

• Dedicated IT Contracts: Any country- or region-specific IT contracts.

• External Partners: Consider involving external partners (e.g., Software One, SDS) for license and contract management.

Free and Open Source Software (FOSS):

• OSS Legality Check: A thorough check of Open Source Software (OSS) for FOSS license compliance and contractual implications is mandatory.

• Detailed OSS Assessment Questions (from DD Checklist):

◦ Is there responsibility for software (SW) or is SW distributed or is SW access granted?.

◦ Is the SW source code available?.

◦ Is the SW source code or parts of it public (e.g., internet => open source software)?.

◦ Has the SW been modified (e.g., error corrections)?.

◦ Is the SW distributed to other legal entities?.

◦ Is there a process to treat OSS legality requirements?.

IT Contracts, Assets, and Licenses Challenges:

• Splitting Contracts: Complexities arise from splitting shared contracts and licenses at the corporate level, often requiring renegotiations with suppliers/contractors.

• License Transfer: New licenses should ideally be procured by the target organization. If procured by the parent company due to contractual issues, the transfer to the target organization needs to be carefully managed.

Next Step Suggestion: Establish a dedicated sub-team focused on contracts and licenses, starting with a comprehensive inventory and legal review of all existing agreements to determine transferability, renegotiation needs, and the implications of open-source software usage.

--------------------------------------------------------------------------------

XIII. MasterRAP and Self-Service Reporting

These tools are crucial for initial data collection and project assessment, especially for understanding the complexity and sizing at an early stage.

MasterRAP (Automatisierung):

• Purpose: MasterRAP is a tool for automation and generating project reports.

• Input Parameters: To generate a project report, the MasterRAP team needs specific filter parameters:

◦ Division.

◦ Company (e.g., 'Robert Bosch Lollar Guss GmbH', 'Buderus Guss GmbH').

◦ Department (e.g., 'RBLG', 'CC-BC').

◦ CostCenter (e.g., '19B*', '140*').

◦ Location (e.g., 'Brh').

◦ TargetEmailAddress.

Self Service Reporting:

• Purpose: This refers to a collection of various Self-Service data sources available to project managers to investigate project complexity and sizing without needing project-specific permissions.

• Resource: The latest collection of these services can be found on Docupedia.

Next Step Suggestion: Utilize MasterRAP and the Self-Service Reporting tools early in the project to gather initial data on the scope, departments, and locations involved, enabling a preliminary assessment of project complexity and resource estimation.

--------------------------------------------------------------------------------

XIV. Clean-Up

Clean-up activities are essential post-closing to ensure a complete separation and tidy up remaining elements in the parent company's systems.

General Clean-Up List:

• A general clean-up list for carve-out projects is available in the MIL Project Library.

• A detailed Clean-up Package specifically for IT-Infrastructure is also available.

Specific Clean-Up Areas:

• Assets:

◦ Types: End devices (computers), Printers, Servers, Network Switches.

◦ Location: Assets are typically recorded in the CMDB (Configuration Management Database).

◦ Method: Removal is typically done via an SMT-Ticket (Service Management Tool Ticket).

• Users:

◦ Types: Internals, Externals, Fixed-Term, Resource, Test users.

◦ Location: User accounts are managed in systems like CI-CAT.

◦ Method: Clean-up involves coordination with the HR department of the relevant Division, with COMPAS serving as the leading system.

• NT-Groups:

◦ Types: Universal, Local, Global, Distribution Groups.

◦ Location: Managed in Active Directory and CI-CAT.

◦ Method: To be determined (t.b.d.) for CI-CAT universal groups.

• M365 (Microsoft 365):

◦ Teams Rooms: Deletion by specific personnel (e.g., Baaskar) in Azure Tenant.

◦ M365 Licenses: Removed with NT-Account in Azure Tenant.

◦ OneDrive Sites: Removed with NT-Account in Azure Tenant.

◦ SharePoint Online sites: To be removed by specific personnel (e.g., Gregor Lenc) in Azure Tenant.

◦ SharePoint Sites (On-Premise): To be determined (t.b.d.) by specific personnel (e.g., Chris) for On-Premise SharePoint.

◦ Conditional Access Policy Group: Clean-up by specific personnel (e.g., David) in ITSP.

◦ Mailboxes: To be determined (t.b.d.) with specific personnel (e.g., Thomas Schubert) in Azure Tenant.

Post-Closing & Clean-up Activities:

• These activities should be defined and planned with enough lead time upfront Closing.

• They are normally the responsibility of the involved parent company business unit (RB-GB), with support/consultation from the parent company's IT M&A team (CI/MI).

• Clean-up execution should follow the dedicated clean-up list if requested as a service from MIL.

Next Step Suggestion: Develop a detailed "Clean-Up Plan" well before the closing date, assigning specific owners and timelines for each asset, user, group, and M365 component, to ensure a smooth and complete disentanglement post-closing.

--------------------------------------------------------------------------------

XV. Phases and Project Management Approach

The overall Carve-out process follows distinct phases, each with specific activities and milestones, managed through a structured project management approach.

A. Selling Process / Transaction Phases:

1. Evaluation (NDA Phase / Confidential):

◦ Start: Call from C/CO, nomination of BD/MIL project lead/team and co-lead in the respective GE/BU.

◦ Information Collection: Explanation of project procedure and intention, understanding current carve-out activities, initial schedule ideas, defining carve-out strategy (share/asset deal), researching internal information (employees, locations, cost centers), and collecting data from Bosch systems (Master RAP, CMDB, LeanIX, sydoku).

◦ Rough Concept: Evaluation of a rough carve-out concept, including scope, potential costs, and timeline.

2. MI Assessment:

◦ Prepare and execute an internal review/assessment (using the Assessment Checklist).

◦ Check lessons learned from matching projects.

◦ Initiate discussions on general guiding principles and secure agreement.

◦ Conduct rough project cost calculation (IT part for GFS request).

◦ G-Approval: Milestone.

3. Preparation after G-Approval:

◦ Prepare the Overall KickOff/public announcement presentation.

◦ Clarify central project roles (Sponsor, IT Activity Manager).

◦ Clarify the IT-PEP approach for the activity.

◦ Start setting up a study for "Operational IT Carve Out" with all required subprojects, user department contact partners, and experts.

◦ Obtain agreement from sponsors and IT activity managers to start the "Study".

4. KickOff / Public Announcement: Milestone.

5. DD (Due Diligence) / Negotiation:

◦ Provision of data room and access, with overall steering by the project lead/C/CO.

◦ Prepare data from analysis for the data room.

◦ Create/prepare documents for the data room, focusing on the IT part (infrastructure, applications).

◦ Expert Meetings and Q&A Phase: Prepare and execute meetings with potential investors and follow-up Q&A sessions.

◦ Deal Decision: Prepare a DD report for the IT part.

6. TOM (Target Operating Model) / Target Organization:

◦ Define the target organization and respective roles/responsibilities.

◦ Define "Buy and Make" decisions per IT topic/cluster.

◦ Define the Target Operational Model (TOM).

◦ Human Resources: Analyze affected CI-employees, conduct internal checks for transfers, and define transfer strategy with GB-HR.

B. Operational IT Carve Out Phases (IT-PEP Focused):

1. Study / Preparation Phase:

◦ Prepare Study: Define study scope (goals), budget, timeline, resources, organization (activity charter). Reconcile with BD Portfolio Management (Planisware). Continue discussion of overall guiding principles. Staff the study team. Complete further study deliverables (according to IT-PEP milestone checklist for OA1).

◦ OA1: Milestone (according to IT-PEP).

◦ Execute Study: Start defining and gaining approval for IT guiding principles. Clarify TSA policy. Verify and complete information collected in the NDA phase (using Assessment Checklist). Develop a carve-out strategy/concept. Identify special carve-out risks and parallel projects, triggering decisions to stop/shift them. Determine the critical path of the IT carve-out. Verify feasibility of the initial carve-out timeline. Fix scope definition for each subproject. Involve BD/MIL-MIA and global teams. Complete further carve-out specific activities per subproject (from Assessment Checklist) and study deliverables (according to IT-PEP milestone checklist for OA2).

2. Prepare Program (Project/SIA): (Parallel to study execution)

◦ Initiate Program (Budget/Resources) with BD Portfolio Management (Planisware). Set up program organization (subprojects, staffing). Complete further preparation activities (according to IT-PEP milestone checklists for PA1 and QG checklist). Set up project controlling, clarify budget (external, cost center, recharging framework, rules for foreign legal entities, C/TX rules for carve-out costs), and establish regular project cost controlling. Clarify ordering/onboarding processes for external suppliers. Ensure AVV conformity. Set up handling of affected CI-employees. Request detailed location lists. Start the project handbook. Collect and contact external/internal service providers. Prepare RFP/RFQ. Create an internal project profile (one-pager).

◦ OA2, PA1/QG0: Milestones (according to IT-PEP).

3. Program Execution (Project/SIA Implementation):

◦ Start of Execution (Initial Phase): Prepare and execute Kickoff. Conduct program activities and activities per subproject (according to IT-PEP).

▪ Main Subprojects: Infrastructure, ERP Environment, Other Applications, Engineering, HR, Organization + Processes of the target IT landscape, Contracts + Licenses.

▪ Carve-Out Specific Activities: WS IT Communication concept, prepare/plan externalization phase, prepare remaining TSAs, define procedure for "handover documents," define cut-off date & procedure, prepare required cut-over plan. Clarify operational responsibility between current providers (e.g., EDL), target IT, and the parent company's IT (CI) until split/closing. Handover operation to target IT/supporting EDL per topic.

◦ Handover Documents Signed: Milestone. It is mandatory for all project deliverables of the IT workstream to be documented and signed before operation responsibility changes.

4. Separation/Cut-Off: Milestone.

◦ Stabilization of stand-alone IT operation.

◦ Start first lessons learned sessions.

◦ Execute externalization activities in IT (forms, master data, etc.).

◦ Remaining activities per subproject (e.g., stabilization, correction, activating own internet breakout, own RASVPN).

5. Closing: Milestone.

6. Post-Closing & Clean-up Activities:

◦ Post-Closing: Review stability of target IT. Agree on and track remaining stabilization topics and open items. Complete final project controlling steps. Regularly follow up on remaining TSAs and stop them according to plan.

◦ Clean-up: Execute clean-up activities according to the clean-up list if requested as a service.

◦ PA1/QG5: Milestone (according to IT-PEP).

Project Management Approaches:

The choice of project management approach (according to IT-PEP v10.3 Concession Point 2) influences how activities are structured:

• Study: A preliminary analysis and preparation phase.

• Program: Used for larger or complex projects; can encompass other activity types.

• IT Project: For small to large projects, especially with "multiple independent work streams".

• Small IT Activity: For small, simple carve-outs.

Recommendation: The preferred approach is an "IT project with multiple independent work streams." An alternative is a "Program" or a "classic IT Project".

IT Project with Multiple Independent Work Streams:

• Advantages: High budget flexibility, cost assignment per subproject, mandatory QGs only at overall project level, central document provision, flexible use of LH/PH/test plans, potential for decoupled time/project plans.

• Disadvantages: Higher formalisms at the overall project level.

Program Approach:

• Advantages: Fewer formalisms at the overall Program level, central document provision, advantageous project-level LH/PH/test plans, flexibility through own QGs and decoupled time/project plans.

• Disadvantages: Limited budget flexibility (adjustments only by Change Requests), many QGs, high administrative effort.

Phasing and Complexity:

• Start with Highly Integrated Topics: Begin with topics and tasks that are highly integrated and have long lead times (e.g., ERP, BI/BW, Engineering, WAN) to enable the carve-out efficiently.

• Address Standardized Topics Later: Work on standardized topics (e.g., Web Content Management, Mail/AD/Client, Network) as late as possible to maintain flexibility, as these might be handled externally.

Next Step Suggestion: Based on the assessed project complexity and strategic models, formally select the appropriate IT-PEP project management approach (e.g., IT Project with multiple independent work streams) and initiate the "Study" phase to refine the initial information and develop a detailed carve-out strategy.

--------------------------------------------------------------------------------

XVI. Project Costs

Understanding and managing project costs is a critical aspect of Carve-out/Divestiture projects, with a typical cost range and various influencing factors.

Approximate Cost Distribution and Per-User Costs:

• Average Cost: A full, integrated carve-out project (e.g., Azur, Münster, Stage, Platin, SAPPHIRE, Kampina, Espresso2) typically costs between €4,000 and €5,500 per user, with an accepted average of €5,000 per user. This figure generally excludes licenses, investments, and user department costs.

• Higher Costs Reasons:

◦ Scope Expansion: Frequent expansion of the scope from the business side, leading to concept revisions and implementation changes.

◦ Skill & Capacity Gaps: Low skills or limited capacity in the user department for processes and procedures, necessitating compensation with IT specialists.

◦ Short Timelines: Aggressive timelines requiring additional external resources.

◦ Additional Complexity: Projects with high complexity, such as Carve-Out/Reverse Carve-Out combinations (e.g., Kampina).

• Small Projects: Projects with fewer than 1,500 employees (e.g., SAPPHIRE, Kampina, Sumatra, Espresso2) must be considered separately.

Cost Calculation Guide:

1. Project Size Classification: Classify the project/transaction size (e.g., checking if it's >500 people).

2. Initial Calculation: Start with an initial calculation of €5,000 per user.

3. Cost Distribution: Apply the statistical percentage distribution of costs across IT areas.

4. Adjustments for Special Effects: Adjust the total amount and/or cost distribution based on:

◦ Surcharges for country-specific topics.

◦ Internationality and number of legal entities.

◦ Shared buildings and real estate.

◦ Complexity of business divergence of the transaction object.

◦ Autarky/competence in the transaction object.

◦ Availability of user department capacity (and possible need for replacement by internal or external teams).

◦ Process variance and complexity in the target organization.

◦ Specific security requirements (e.g., military use).

5. Administrative Tasks: Account for special administrative tasks, including ordering, general purchasing, and cleanup.

6. Cost Structure Elements: Separate/assign costs according to elements: One Time Effort (OTE), licenses, Machinery, Equipment, Tools (MAE), Fixed Assets (FA).

7. Budget Validation: Validate the planned budget/costs via project assessment by BD/MI.

Cost Structure – Carve-out IT Costs:

• OTE (One Time Effort):

◦ Includes costs for external companies and internal IT (e.g., CI).

◦ Typically shown in GFS approval as part of the IT Workstream budget.

◦ Covers external consulting, external PMO, implementation fees, and costs from internal service providers (e.g., RBEI).

◦ All effort must be traceable for tax purposes.

◦ Internal CI employee effort is mainly charged at an hourly rate and must be traceable.

◦ Budget is usually shown as exceptional costs for tax purposes.

• Licenses:

◦ Normally not shown in the GFS approval as part of the IT workstream budget.

◦ Should be procured by the target organization whenever possible.

◦ Procurement within the parent company (RB GmbH) only if contractual issues prevent procurement by the target, and with plans for subsequent transfer.

◦ Budgeting must be clarified upfront with the overall project lead/C/COA.

• MAE (Machinery, Equipment, Tools) – (typically HW for backend and client Infrastructure):

◦ Normally not shown in the GFS approval as part of the IT workstream budget.

◦ Should be procured by the target organization whenever possible.

◦ Existing and capitalized hardware from the parent company's IT (CI) will be sold to the carved-out object based on existing rules (e.g., from CI/CTG).

◦ Budget should reside with the target organization; clarification with the project lead/C/COA is needed.

◦ For asset transfers, rules from central directive CD 03177 (chapter 4.4.2.3.2 "Transferpreisermittlung") apply, specifying a minimum value (e.g., 10-20% of original acquisition and manufacturing costs).

• User Department Effort (Fachabteilungskosten):

◦ Normally not shown in the GFS approval as part of the IT workstream budget.

◦ Effort/costs must be covered by the business unit (GB) itself, without charging.

◦ Reported at an informational level.

◦ Agreement on the volume of effort/costs should be established.

Complexity and Cost Drivers:

• Entity-Specific Drivers:

◦ Number of affected locations and countries.

◦ Type of sites (manufacturing vs. sales offices).

◦ Number of affected users/workplaces.

◦ Integration into the parent company (Bosch) and usage of central/shared RB services (e.g., HR, Purchasing).

◦ Degree of integration into not-sold RB business (e.g., BBM).

◦ Scope of the carve-out (entire GB vs. partial sale).

◦ Legal entity split and decision on selling newCo or oldCo (reverse carve-out).

◦ Target entity not prepared for self-independence; parent company business units (GBs/Units) not prepared for carve-out.

• Carve-Out Approach Drivers:

◦ Complete carve-out / standalone business / IT upfront closing.

◦ Reverse carve-out.

◦ Carve-out after closing in the investor's IT environment.

◦ TSA approach.

• Framework Condition Drivers (from Parent Company - RB):

◦ Integration in RB shared services.

◦ GBs/Units not prepared for carve-out/independence.

◦ High integration in IT solutions and consolidated IT systems of RB.

• Complexity Drivers (leading to costs):

◦ Unclear scope ("What is part of the deal and what is not?").

◦ Business unable to define target standalone processes.

◦ Limited knowledge in areas of shared services and operations of a mid-size company.

◦ No capacity available in the new company (business or IT), and not everything can be compensated by external companies.

◦ No capacity available for one-time-effort of carve-out (specialists blocked in other projects).

◦ Dependencies on externals with no/limited parent company knowledge.

◦ Splitting of shared locations (network, telephony, plant security, common systems).

◦ Splitting of contracts and licenses at corporate level, requiring renegotiations.

◦ Centralized main IT infrastructure solutions (Mail, SfB, client software distribution) based on corporate architecture.

◦ Common usage of Intranet/Internet and social media platforms (e.g., Bosch Connect).

◦ High cost effects from central consulting companies (e.g., EY, KPMG, RolandBerger).

◦ High effort/costs for ERP split and carving-out of corporate solutions (Purchasing, Finance, HR), and consolidated ERP systems.

◦ Expensive carve-out projects in specific countries (e.g., Brazil, India) due to legal frameworks and company structures.

Next Step Suggestion: Develop a comprehensive "Project Cost Calculation" worksheet, leveraging the €5,000/user benchmark and detailing all potential complexity and cost drivers, ensuring early alignment and approval from the overall project lead and relevant financial stakeholders for OTE, licenses, MAE, and user department efforts.

--------------------------------------------------------------------------------

XVII. Transitional Service Agreements (TSAs) and Lessons Learned

TSAs are a critical component of many divestitures, providing continuity of services during the transition phase, but Bosch aims for a restrictive approach. Lessons learned from past projects offer invaluable insights into managing these complex undertakings.

Transitional Service Agreements (TSAs):

• Bosch Policy: Bosch's TSA policy is "very restrictive," to be applied "only in exceptional cases and only for a short time". A "No-TSA policy" is preferred but should not be a deal breaker if alternatives are unavailable.

• Trigger and Coordination: The IT TSA coordination process is triggered and released by specific personnel (e.g., CI/MIC-Kling).

• Roles and Responsibilities in IT TSA Process:

◦ CI/MI PrL (Project Lead): Delivers input for IT TSA content (services, period, specifics), discusses with the IT of the buyer and parent company's business unit (GB), provides feedback, and is responsible for the appendices (services, period, pricing, specifics).

◦ C/LS (Legal Services): Provides legal advice to the CI/MI PrL or ensures input is covered in the legal part of the TSA. Responsible for the final version of the IT TSA legal part.

◦ C/COA (Corporate Carve-Out Activity): Informs stakeholders in real-time (not later than signing) about TSA matters.

◦ GB (Business Unit): Delivers input to IT TSA content and engages in discussions.

◦ Buyer: Engages in IT TSA discussions with the parent company's IT.

• Documentation: The CI/MI PrL is responsible for the final version of the IT TSA appendices. Legal templates and appendices templates are available for storage.

• Platin Project Example: TSAs were only to be provided in exceptional cases and with a limited timeframe (e.g., ~6 months, not several years). They would only be used for services that could not be built up until Day-1 due to implementation time or organizational reasons.

Best Practices & Lessons Learned:

The MI-Toolkit "Divestiture" and other concept papers (e.g., from Norton Rose Fulbright, AlixPartners, EY) serve as valuable resources. Key lessons include:

• Proactive Planning: "Possible Post-Closing activities incl. related Clean-up tasks should be defined / planned with enough lead time upfront Closing".

• Stabilization: Post-closing, review the stability of the target IT and track remaining stabilization topics and open items.

• Stopping TSAs: Regularly follow up on remaining TSAs and stop them according to plan.

• Complexity First: "Make the difficult part of the project at first (complexity first, standard topics follow)". Avoid the temptation of focusing on "low hanging fruits" prematurely.

• Defined Requirements: Teams must clearly understand their tasks, requiring "Defined requirements by the customer".

• Migration Rules are Hard: "Defining migrations rules for the carve-out is the hell!" due to the multitude of influencing factors (deal type, tax, HR, local law).

• Legal Entity Independence: Emphasize that "No IT System (ERP) without a independent legal entity" and be mindful of HR rules across countries.

• Data Integrity: Ensure data reconciliation: "It must be possible to reconcile data from retained and the separated business to their original source and proof, that separation of data did not add or remove relevant content".

Next Step Suggestion: Formalize the TSA policy for the current project, clearly defining the scope, duration, and pricing of any required transitional services, and assign specific individuals to manage the TSA negotiation and execution process, ensuring strict adherence to the restrictive policy.

--------------------------------------------------------------------------------