## Cost Plan
Project Eagle - IT Carve-Out Cost Plan
Based on | Eagle_Project_Schedule.xlsx
Risk-aligned | Eagle_Risk_Register.xlsx
PMO Lead | Ho Keng Hua (BD/MIL-ICC)
Generated | 2026-04-04
Budget Status | TBC - to be approved at QG1
PMO & Governance
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
Ho Keng Hua (PMO Lead) | 300 | 120 | 2400 | EUR | 288000
Program Manager | 250 | 100 | 2000 | EUR | 200000
PMO & Governance Subtotal |  |  |  |  | 488000
Infrastructure & Network
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
Infrastructure Architect | 200 | 130 | 1600 | EUR | 208000
Infrastructure Team | 180 | 90 | 1440 | EUR | 129600
Vendor Installation (3 sites) | 80 | 110 | 640 | EUR | 70400
Infrastructure & Network Subtotal |  |  |  |  | 408000
Application Development & Integration
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
App Lead | 160 | 125 | 1280 | EUR | 160000
Integration Architect | 140 | 130 | 1120 | EUR | 145600
App Dev Team | 200 | 95 | 1600 | EUR | 152000
Application Development & Integration Subtotal |  |  |  |  | 457600
Data & Database
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
Data Architect | 150 | 130 | 1200 | EUR | 156000
DBA | 140 | 125 | 1120 | EUR | 140000
Data & Database Subtotal |  |  |  |  | 296000
Quality & Testing
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
QA Lead | 180 | 120 | 1440 | EUR | 172800
QA Team | 200 | 85 | 1600 | EUR | 136000
Quality & Testing Subtotal |  |  |  |  | 308800
Change & User Support
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
Change Lead | 200 | 110 | 1600 | EUR | 176000
Training Team | 150 | 75 | 1200 | EUR | 90000
Support Team | 180 | 80 | 1440 | EUR | 115200
Change & User Support Subtotal |  |  |  |  | 381200
Business & Functional
Resource | Total Days | Hourly Rate EUR | Total Hours | Rate Currency | Total Cost EUR
Business Analyst | 120 | 105 | 960 | EUR | 100800
Business Owner | 100 | 90 | 800 | EUR | 72000
Business & Functional Subtotal |  |  |  |  | 172800
TOTAL LABOUR COST |  |  |  |  | 2512400
CAPEX / Additional Costs (Not in Labour)
Temporary IT Contractors (Risk #3 - Jul-Dec) |  |  |  |  | 75000
ISV Licensing Change-of-Control (Risk #4) |  |  |  |  | 40000
Hypercare Extended Support Contractors (Risk #9) |  |  |  |  | 45000
Hardware Procurement & Infrastructure (Risk #8) |  |  |  |  | 60000
Contingency Reserve (10%) |  |  |  |  | 0
CAPEX / Contingency Subtotal |  |  |  |  | 220000
TOTAL PROJECT COST (Labour + CAPEX) |  |  |  |  | 2732400
Cost Breakdown by Category
PMO & Governance |  |  |  |  | 488000
Application Development & Integration |  |  |  |  | 457600
Infrastructure & Network |  |  |  |  | 408000
Change & User Support |  |  |  |  | 381200
Quality & Testing |  |  |  |  | 308800
Data & Database |  |  |  |  | 296000
Business & Functional |  |  |  |  | 172800
Labour costs are based on estimated effort allocation across 5 project phases.
CAPEX/Contingency items are derived from high-priority risks (Risk Register #3, #4, #8, #9).
Stand Alone carve-out model: No Merger Zone costs.
TSA service definition included in Phase 1 & 2; exit transition in Phase 5.
Budget baseline: TBC - to be approved at Quality Gate 1 (QG1)