## Slide 1
Eagle Project
Security Camera Business IT Carve-Out
Management Stakeholder Review
4 April 2026 | Intake Phase | On Track

## Slide 2
Project Overview
• Stand-alone IT carve-out: 3 Singapore sites | 300 users | 15+ applications
• Timeline: Jun 1, 2026 – Apr 7, 2027 (310 days) | Go-Live: Nov 7, 2026
• Budget: EUR 580–650K (labour + contingency) | CAPEX: EUR 150–200K (separate)
• TSA Hypercare: 90 days (Nov 8, 2026 – Feb 6, 2027)
• Stand-alone model enables: infrastructure independence, cloud-native migration path, vendor negotiation leverage

## Slide 3
Key Milestones & Quality Gates
• QG0 (Jun 26): Kickoff — intake complete, team mobilized
• QG1 (Aug 21): Design & Planning — architecture, procurement finalized
• QG2/3 (Oct 29): Build Complete — infrastructure, integration, SAT ready
• QG4 (Nov 1): Production Readiness — UAT pass, cutover plan finalized
• Go-Live (Nov 7): Production cutover, hypercare activation
• QG5 (Apr 7, 2027): Project Close — TSA exit, handover complete

## Slide 4
Budget Distribution & Cost Allocation
Total Labour Budget: EUR 580–650K
• Programme Management (12%) — EUR 70–78K
• Infrastructure & Operations (22%) — EUR 127–143K
• Data & Integration (20%) — EUR 116–130K
• Applications & Testing (18%) — EUR 104–117K
• Change & Training (8%) — EUR 46–52K
• Risk Contingency (10%) — EUR 58–65K

## Slide 5
Top 5 Risks & Mitigation
1. Phase 3 UAT Compression (Risk #3, P×I=30) — 27-day UAT for 300 users × 15 apps
→ Mitigation: Front-load Phase 2, automate 60% tests, risk-based testing on critical path
2. SAP Data Separation (Risk #2, P×I=25) — GL posting integrity & reconciliation
→ Mitigation: Data audit by Jun 26; ETL validation by Jul 15; dual-run procedures by Sep 15
3. SAP Licensing Change-of-Control (Risk #21, P×I=25) — MSA re-negotiation delays
→ Mitigation: Engage SAP legal by May 1; escalate to VP if blocked by Jun 15

## Slide 6
Workstream Confidence Profile
• Infrastructure & Networking: 80% (ON TRACK)
• Security & Compliance: 85% (ON TRACK)
• SAP & Data Migration: 55% (AT RISK) — data mapping complexity
• Applications & Integration: 60% (AT RISK) — 12 API touchpoints, ISV certification pending
• Testing & Quality: 40% (HIGH RISK) — UAT compression, defect escape risk
• Change & User Adoption: 50% (AT RISK) — manufacturing floor readiness

## Slide 7
Critical Success Factors
✓ On-time Go-Live Nov 7, 2026 (no delay tolerance due to Q4 manufacturing peak)
✓ UAT defect escape rate < 5% on critical path (SAP MM, GL, inventory)
✓ 90-day TSA hypercare within budget (EUR 180–220K); potential extension flagged
✓ Data reconciliation accuracy > 99% by Dec 31, 2026
✓ Buyer IT capability transfer complete by Feb 6, 2027 (TSA exit)
✓ Standalone operations documented; incident response procedures established

## Slide 8
Next 30 Days — Critical Actions & Decisions
• By May 15: ISP vendor selection & circuit provisioning SLA agreement
• By May 20: Data lineage audit complete; SAP licensing agreement signed
• By Jun 26: QG0 Gate Review — confirm budget approval, team mobilization
• DECISION REQUIRED: Hypercare staffing model (24/7 vs 12/5); budget approval
• ESCALATION NEEDED: ISV licensing negotiations if blocked by Jun 1