## Schedule
ID | Level | Task Name | Duration (days) | Start Date | Finish Date | Predecessors | Resources | Notes | Milestone
0 | 0 | Eagle - Security Camera Business Carve-out | 310 | 2026-06-01 | 2027-04-07 |  |  |  | No
1 | 1 | 0. INITIATION & QG0 | 25 | 2026-06-01 | 2026-06-26 |  |  |  | No
2 | 2 | 0.1 Project Kickoff & Governance | 5 | 2026-06-01 | 2026-06-06 |  | Ho Keng Hua + PMO |  | No
3 | 3 | 0.1.1 Establish PMO & workstreams | 3 | 2026-06-01 | 2026-06-04 |  | Ho Keng Hua |  | No
4 | 3 | 0.1.2 Define governance & forums | 2 | 2026-06-04 | 2026-06-06 | 3 | PMO + Legal |  | No
5 | 2 | 0.2 Business & IT Scope Definition | 12 | 2026-06-06 | 2026-06-18 |  | Business Analyst + IT Lead |  | No
6 | 3 | 0.2.1 Document business processes | 4 | 2026-06-06 | 2026-06-10 |  | Business Analyst |  | No
7 | 3 | 0.2.2 Inventory IT systems & data | 4 | 2026-06-06 | 2026-06-10 |  | IT Lead |  | No
8 | 3 | 0.2.3 Define separation scope | 4 | 2026-06-10 | 2026-06-14 | 6,7 | Legal + IT Lead |  | No
9 | 2 | 0.3 Stakeholder & Change Readiness | 8 | 2026-06-06 | 2026-06-14 | 4 | Change Lead |  | No
10 | 3 | 0.3.1 User readiness assessment | 4 | 2026-06-06 | 2026-06-10 | 4 | Change Lead |  | No
11 | 3 | 0.3.2 Site consultation | 4 | 2026-06-10 | 2026-06-14 | 10 | Change Lead |  | No
12 | 2 | 0.4 QG0 - Intake Approval | 1 | 2026-06-26 | 2026-06-27 | 8,11 | PMO + Steering | Project formally approved | Yes
13 | 1 | 1. CONCEPT & SCOPE PHASE | 56 | 2026-06-26 | 2026-08-21 | 12 |  |  | No
14 | 2 | 1.1 IT Architecture Baseline | 20 | 2026-06-27 | 2026-07-17 | 13 | Infrastructure Architect |  | No
15 | 3 | 1.1.1 Current state infrastructure mapping | 5 | 2026-06-27 | 2026-07-02 | 13 | Infrastructure Architect |  | No
16 | 3 | 1.1.2 Design target architecture | 10 | 2026-07-02 | 2026-07-12 | 15 | Infrastructure Architect |  | No
17 | 3 | 1.1.3 Network & security design | 5 | 2026-07-12 | 2026-07-17 | 16 | Security Architect |  | No
18 | 2 | 1.2 Application & Data Strategy | 22 | 2026-06-27 | 2026-07-19 | 13 | App Lead + Data Architect |  | No
19 | 3 | 1.2.1 Application inventory & assessment | 6 | 2026-06-27 | 2026-07-03 | 13 | App Lead |  | No
20 | 3 | 1.2.2 Data dependency mapping | 8 | 2026-07-03 | 2026-07-11 | 19 | Data Architect |  | No
21 | 3 | 1.2.3 Carve-out strategy document | 8 | 2026-07-11 | 2026-07-19 | 20 | App Lead + Data Architect |  | No
22 | 2 | 1.3 TSA & Transition Planning | 15 | 2026-07-16 | 2026-07-31 | 14,18 | IT Lead + Finance |  | No
23 | 3 | 1.3.1 Define TSA scope (Seller->Buyer) | 8 | 2026-07-16 | 2026-07-24 | 14 | IT Lead |  | No
24 | 3 | 1.3.2 Plan transition & handover | 7 | 2026-07-24 | 2026-07-31 | 23 | Finance + IT Lead |  | No
25 | 2 | 1.4 QG1 - Concept Gate | 1 | 2026-08-21 | 2026-08-22 | 17,21,24 | PMO + Steering | Concept phase approved | Yes
26 | 1 | 2. DESIGN PHASE | 45 | 2026-08-22 | 2026-10-06 | 25 |  |  | No
27 | 2 | 2.1 Infrastructure Design Details | 15 | 2026-08-23 | 2026-09-07 | 25 | Infrastructure Architect |  | No
28 | 3 | 2.1.1 Network design (3 Singapore sites) | 5 | 2026-08-23 | 2026-08-28 | 25 | Infrastructure Architect |  | No
29 | 3 | 2.1.2 Server & storage detail design | 5 | 2026-08-28 | 2026-09-02 | 28 | Infrastructure Architect |  | No
30 | 3 | 2.1.3 Security & compliance hardening | 5 | 2026-09-02 | 2026-09-07 | 29 | Security Architect |  | No
31 | 2 | 2.2 ERP & Database Design | 18 | 2026-08-23 | 2026-09-10 | 25 | ERP Lead + DBA |  | No
32 | 3 | 2.2.1 ERP separation strategy | 6 | 2026-08-23 | 2026-08-29 | 25 | ERP Lead |  | No
33 | 3 | 2.2.2 Data migration & replication design | 6 | 2026-08-29 | 2026-09-04 | 32 | Data Architect |  | No
34 | 3 | 2.2.3 Database backup & recovery plan | 6 | 2026-09-04 | 2026-09-10 | 33 | DBA |  | No
35 | 2 | 2.3 Application Carve-Out Design | 16 | 2026-08-29 | 2026-09-14 | 25 | App Lead |  | No
36 | 3 | 2.3.1 Application separation design | 6 | 2026-08-29 | 2026-09-04 | 25 | App Lead |  | No
37 | 3 | 2.3.2 API & integration points | 5 | 2026-09-04 | 2026-09-09 | 36 | Integration Architect |  | No
38 | 3 | 2.3.3 Data protection & PII handling | 5 | 2026-09-09 | 2026-09-14 | 37 | Legal + Data Privacy |  | No
39 | 2 | 2.4 Client & Endpoint Strategy | 14 | 2026-09-02 | 2026-09-16 | 25 | Client Architect |  | No
40 | 3 | 2.4.1 Endpoint OS & software assessment | 4 | 2026-09-02 | 2026-09-06 | 25 | Client Architect |  | No
41 | 3 | 2.4.2 Device imaging & deployment design | 5 | 2026-09-06 | 2026-09-11 | 40 | Imaging Lead |  | No
42 | 3 | 2.4.3 User migration plan (300 users) | 5 | 2026-09-11 | 2026-09-16 | 41 | Change Lead |  | No
43 | 2 | 2.5 Cutover & Testing Strategy | 12 | 2026-09-13 | 2026-09-25 | 34,38 | Cutover Lead |  | No
44 | 3 | 2.5.1 Cutover window definition (3 sites) | 3 | 2026-09-13 | 2026-09-16 | 34 | Cutover Lead |  | No
45 | 3 | 2.5.2 UAT & testing strategy | 5 | 2026-09-16 | 2026-09-21 | 44 | QA Lead |  | No
46 | 3 | 2.5.3 Rollback & contingency plan | 4 | 2026-09-21 | 2026-09-25 | 45 | Cutover Lead |  | No
47 | 1 | 3. BUILD & TEST PHASE | 24 | 2026-10-05 | 2026-10-29 | 43,46 |  |  | No
48 | 2 | 3.1 Infrastructure Build-Out | 12 | 2026-10-06 | 2026-10-18 | 47 | Infrastructure Team |  | No
49 | 3 | 3.1.1 Procure & deploy hardware (3 sites) | 6 | 2026-10-06 | 2026-10-12 | 47 | Procurement + Infrastructure |  | No
50 | 3 | 3.1.2 Network deployment & security | 4 | 2026-10-12 | 2026-10-16 | 49 | Infrastructure Team |  | No
51 | 3 | 3.1.3 Infrastructure testing & validation | 2 | 2026-10-16 | 2026-10-18 | 50 | Infrastructure Team |  | No
52 | 2 | 3.2 ERP Build & System Migration | 14 | 2026-10-06 | 2026-10-20 | 47 | ERP Team + DBA |  | No
53 | 3 | 3.2.1 ERP system clone/build | 5 | 2026-10-06 | 2026-10-11 | 47 | ERP Team |  | No
54 | 3 | 3.2.2 Data extraction & transformation | 4 | 2026-10-11 | 2026-10-15 | 53 | Data Architect |  | No
55 | 3 | 3.2.3 ERP configuration & testing | 3 | 2026-10-15 | 2026-10-18 | 54 | ERP Consultant |  | No
56 | 3 | 3.2.4 Data validation & reconciliation | 2 | 2026-10-18 | 2026-10-20 | 55 | ERP Lead + DBA |  | No
57 | 2 | 3.3 Application Build & Config | 12 | 2026-10-11 | 2026-10-23 | 47 | App Dev Team |  | No
58 | 3 | 3.3.1 Clone/provision applications | 5 | 2026-10-11 | 2026-10-16 | 47 | App Lead |  | No
59 | 3 | 3.3.2 Configure integrations & APIs | 4 | 2026-10-16 | 2026-10-20 | 58 | Integration Architect |  | No
60 | 3 | 3.3.3 Application testing | 3 | 2026-10-20 | 2026-10-23 | 59 | QA Team |  | No
61 | 2 | 3.4 Client Imaging & Pilot | 10 | 2026-10-14 | 2026-10-24 | 47 | Imaging & Deployment |  | No
62 | 3 | 3.4.1 Prepare images & deployment | 3 | 2026-10-14 | 2026-10-17 | 47 | Imaging Lead |  | No
63 | 3 | 3.4.2 Pilot deployment (Site 1, ~30 users) | 3 | 2026-10-17 | 2026-10-20 | 62 | Deployment Team |  | No
64 | 3 | 3.4.3 Pilot feedback & adjustments | 4 | 2026-10-20 | 2026-10-24 | 63 | Change Lead + Users |  | No
65 | 2 | 3.5 QG2&3 - Build & Test Gate | 1 | 2026-10-29 | 2026-10-30 | 51,56,60,64 | PMO + QA | Build phase complete, ready for UAT | Yes
66 | 1 | 4. FINAL UAT & CUTOVER PREP | 4 | 2026-10-29 | 2026-11-02 | 65 |  |  | No
67 | 2 | 4.1 Full UAT Execution | 2 | 2026-10-30 | 2026-10-31 | 65 | QA Lead + Business |  | No
68 | 3 | 4.1.1 Run UAT test scripts (all systems) | 1 | 2026-10-30 | 2026-10-30 | 65 | QA + Business Testers |  | No
69 | 3 | 4.1.2 Critical defect resolution | 1 | 2026-10-30 | 2026-10-31 | 68 | Dev + QA |  | No
70 | 2 | 4.2 Pre-GoLive Readiness Check | 1 | 2026-10-31 | 2026-11-01 | 69 | PMO + Tech Leads |  | No
71 | 3 | 4.2.1 Final infrastructure & system checks | 0.5 | 2026-10-31 | 2026-10-31 | 69 | Infrastructure Lead |  | No
72 | 3 | 4.2.2 Cutover rollback test | 0.5 | 2026-10-31 | 2026-11-01 | 71 | Cutover Lead |  | No
73 | 2 | 4.3 QG4 - Pre-GoLive Approval | 1 | 2026-11-01 | 2026-11-02 | 70 | PMO + Steering | QG4 gate passed; ready for final cutover checks | Yes
74 | 1 | 4b. FINAL READINESS & CUTOVER VERIFICATION | 2 | 2026-11-02 | 2026-11-04 | 73 |  |  | No
75 | 2 | 4b.1 UAT Closure & Sign-Off | 1 | 2026-11-02 | 2026-11-03 | 73 | QA Lead + Business |  | No
76 | 3 | 4b.1.1 Verify all UAT defects resolved | 0.5 | 2026-11-02 | 2026-11-02 | 73 | QA Lead |  | No
77 | 3 | 4b.1.2 UAT sign-off document | 0.5 | 2026-11-02 | 2026-11-03 | 76 | Business Owner |  | No
78 | 2 | 4b.2 Final Open Items Verification | 1 | 2026-11-03 | 2026-11-04 | 77 | PMO + Steering |  | No
79 | 3 | 4b.2.1 Confirm all action items closed | 0.5 | 2026-11-03 | 2026-11-03 | 77 | PMO |  | No
80 | 3 | 4b.2.2 Final infrastructure readiness | 0.5 | 2026-11-03 | 2026-11-04 | 79 | Infrastructure Lead |  | No
80 | 1 | 5. GOLIVE & HYPERCARE | 91 | 2026-11-07 | 2027-02-05 | 80 |  |  | No
82 | 2 | 5.1 GoLive - Day 1 Cutover | 1 | 2026-11-07 | 2026-11-08 | 81 | PMO + Ops Team | Production go-live | Yes
83 | 2 | 5.2 Hypercare & Stabilization (90 days) | 90 | 2026-11-08 | 2027-02-05 | 82 | Support Team + SMEs | 90-day post-GoLive support | No
84 | 3 | 5.2.1 24/7 L3 support & issue triage | 60 | 2026-11-08 | 2027-01-06 | 82 | L3 Support + Engineers |  | No
85 | 3 | 5.2.2 Performance tuning & hotfixes | 45 | 2026-11-08 | 2026-12-22 | 82 | Performance Engineer |  | No
86 | 3 | 5.2.3 User training & enablement | 60 | 2026-11-08 | 2027-01-06 | 82 | Training Team |  | No
87 | 3 | 5.2.4 Knowledge transfer & documentation | 30 | 2027-01-06 | 2027-02-05 | 84 | Support Lead |  | No
88 | 1 | 6. OPERATIONS TRANSITION & CLOSURE | 60 | 2027-02-06 | 2027-04-07 | 83 |  |  | No
89 | 2 | 6.1 Transition to Steady-State | 20 | 2027-02-06 | 2027-02-25 | 83 | Ops Lead + IT Manager |  | No
90 | 3 | 6.1.1 Operations runbook finalization | 5 | 2027-02-06 | 2027-02-10 | 83 | Ops Lead |  | No
91 | 3 | 6.1.2 Incident & escalation procedures | 5 | 2027-02-10 | 2027-02-15 | 90 | Ops Lead |  | No
92 | 3 | 6.1.3 Capacity planning & baseline | 5 | 2027-02-15 | 2027-02-20 | 91 | Infrastructure |  | No
93 | 3 | 6.1.4 Transition BAU support model | 5 | 2027-02-20 | 2027-02-25 | 92 | IT Manager |  | No
94 | 2 | 6.2 Finance & Benefit Realization | 20 | 2027-02-15 | 2027-03-07 | 93 | Finance + PMO |  | No
95 | 3 | 6.2.1 Financial separation & P&L | 10 | 2027-02-15 | 2027-02-25 | 93 | Finance Lead |  | No
96 | 3 | 6.2.2 Cost allocation & chargeback | 10 | 2027-02-25 | 2027-03-07 | 95 | Finance Lead |  | No
97 | 2 | 6.3 Lessons Learned & Closure | 15 | 2027-02-25 | 2027-03-12 | 96 | PMO + Team |  | No
98 | 3 | 6.3.1 Lessons learned workshop | 3 | 2027-02-25 | 2027-02-28 | 96 | PMO |  | No
99 | 3 | 6.3.2 Final project report & sign-off | 5 | 2027-02-28 | 2027-03-05 | 98 | Program Manager |  | No
100 | 3 | 6.3.3 Project artifacts archival | 5 | 2027-03-05 | 2027-03-10 | 99 | PMO |  | No
101 | 3 | 6.3.4 Final vendor settlement | 2 | 2027-03-10 | 2027-03-12 | 100 | Procurement + Finance |  | No
102 | 2 | 6.4 QG5 - Project Completion | 1 | 2027-04-07 | 2027-04-08 | 101 | PMO + Steering | Project formally closed | Yes