## Info
Revision history
Document Id | <doc-id>
File Name | <file>
Project Name | <project name>
Project Id | <project id>
Document Owner | <owner>
Review Date | Reviewers |  | Changes
About this template
Risk Category | Select from categories as defined by the Risk Management Plan.
Cause | Specifically what causes the risk to become a realized issue/problem
Effect | What happens if the trigger point occurs
Owner | Risk owner.
Creation date | Date risk identified.
Source | Source of risk.
Impact | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan
Probability | Probability of risk being realized, using scales defined in the Risk Management Plan.
Matrix Score | This is calculated once you select the Impact and Probability.
Qualitative Impact | Space for further description of potential impact.
Quantitative Impact | quantitative / potential risk cost
Risk response strategy | Select from strategies as defined by the Risk Management Plan.
Status | Risk status (e.g. whether it has been triggered or not). You will need to update the values list in cells
Notes | Additional notes.
Template Version | Issue Date | Author | Changes
1.0 | 2023-12-07 | S. Hoehnel | initial template based on V5.2 of the central risk register (S. Wohlfahrt); only examples provided on top

## Risk Register
Risk Register
Risk Identification | [8 empty] | Risk Analysis | [6 empty] | Risk Response Planning |  |  | Risk Monitoring and Control
risk ID | creation date | risk category | cause(s) | event | effect(s) | risk event date | owner | source | impact | prob- ability | threat / opportunity | matrix score | qualitative impact (including period of consideration) | monetary impact [EUR] current year | monetary impact [EUR] three subsequent years | risk response strategy | measure | due date | status | reporting date | impact actual | prob- ability actual | impact (actual) | probability (actual) | matrix score (actual) | notes
1 | 2026-04-04 | Schedule | ISP lead times for 3 Singapore sites 8-12 weeks; provider allocation constraints; late RFQ submission by Apr 20 | Network infrastructure not provisioned by Aug 1 (Phase 3 UAT target); redundant WAN circuits not available; ISP unable to prioritize within carve-out timeline | Problem-statement for selection of project is not fulfilled. | n.a. | Infra Lead | Formal Risk Review | High | 70% | threat |  |  |  | 0 | Mitigate | Expedite ISP RFQ by May 15; dual-provider SLA enforcement; weekly vendor tracking cadence | 2026-05-15 | in progress | 2026-04-04 | High | 70%
2 | 2026-04-04 | Schedule | Server/storage procurement lead times 14-16 weeks; supply chain delays; vendor allocation constraints for certified enterprise equipment; cooling/power infrastructure at 3 sites not yet validated | Physical servers (Cisco UCS C-series, NetApp SAN storage) not delivered by Aug 15; test lab environment remains offline through Sep; Phase 3 UAT deferred to Oct 1 (compressed to 3 weeks) | - Financial loss - Damage to company/department reputation - Loss of employee's confidence | n.a. | Proc Lead | Formal Risk Review | High | 50% | threat |  | Financial loss is usually negligible, since no valuables (> 2500 EUR) are stored in the office area. Damage to reputation and loss of confidence must be counteracted with appropriate measures. Theft of data and documents is dealt with in a separate point | 2500 | 0 | Mitigate | Place hardware orders by May 1; expedite clauses embedded in contracts; backup vendor identified by Apr 20 | 2026-05-01 | not started | 2026-04-04 | High | 50%
3 | 2026-04-04 | Schedule | Phase 2 (Jul-Sep) data migration complexity delays System Acceptance Testing (SAT); UAT window legally capped at Oct 5-31 (27 days); no extension possible due to manufacturing year-end cutoff | Insufficient UAT duration for 300 shop-floor + office users; 15+ applications (SAP, legacy WMS, ERP ancillaries) compressed into 4-week window; regression testing limited to critical path only; UAT defect backlog accumulates | Project-goals and interdependencies of deliverables are known prior to realization, avoiding rework and shortening coordination-efforts. |  | QA Lead, PMO | Formal Risk Review | Very High | 70% | threat |  |  |  |  | Mitigate | Front-load Phase 2 UAT scope by Jul 1; automate 60% of test scripts by Aug 31; split UAT into parallel workstreams (manufacturing ops, finance, supply-chain) | 2026-09-30 | in progress | 2026-04-04 | Very High | 70%
4 | 2026-04-04 | Technology, R&D | Legacy shared ERP (SAP S/4HANA) used jointly by Seller IT and Buyer IT; no clean data boundary exists; transactional interdependencies span purchase orders, inventory, GL posting; 15-year master data with quality gaps | Data migration mapping incomplete; duplicate records in vendor master, GL accounts; referential integrity break age during dual-run (Nov-Dec); reconciliation rework required post-GoLive; manual correction effort 200+ hours | Scope-changes during or after realization. |  | Data Arch, ETL | Formal Risk Review | Very High | 70% | threat |  |  |  |  | Mitigate | Complete data lineage audit by May 31; prototype ETL cleansing by Jul 15; establish dual-run reconciliation procedures by Sep 15; assign reconciliation owner | 2026-05-31 | in progress | 2026-04-04 | Very High | 70%
5 | 2026-04-04 | Technology, R&D | ISV certification policy requires standalone infrastructure approval for security camera application; not on ISV pre-approved platform list; ISV legal review SLA 6-8 weeks; change-of-control license re-assessment required | ISV withholds certification; licensing model reclassified to 'new install' instead of carve-out exception; contract renegotiation drags into Build phase (Aug-Sep); Go-Live slips 8-12 weeks to Dec/Jan 2027 | Deliverables are delayed, potentially affecting Go-Live. |  | Sourcing, Legal | Formal Risk Review | Very High | 50% | threat |  |  |  |  | Mitigate | Engage ISV legal counsel by May 1; submit certification questionnaire by May 15; negotiate waiver clause covering carve-out scenario; escalate to ISV VP if blocked by Jun 30 | 2026-06-01 | not started | 2026-04-04 | Very High | 50%
6 | 2026-04-04 | Technology, R&D | Standalone infrastructure (3 sites, separate backup/DR, independent cloud tenancy) enables buyer to pursue cloud-native security camera system migration; SaaS licensing more favorable post-carve-out | Buyer accelerates SaaS adoption for surveillance app by Q1 2027; cloud-only architecture investment justified; OpEx shift reduces perpetual licensing; infrastructure footprint consolidation opportunity | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. |  | CTO, Strategic Planning | Formal Risk Review | Moderate | 50% | opportunity |  |  |  |  | Exploit | Document cloud-native architecture optionsand cost models by Sep 30; evaluate SaaS vendor options (AWS, Azure, GCP) by Oct 31; negotiate SaaS pilot licensing by Q1 2027 | 2026-09-30 | not started | 2026-04-04 | Moderate | 50%
7 | 2026-04-04 | Engineering | 300 manufacturing shop-floor and office staff; limited IT literacy in POS systems, ERP navigation; manufacturing operations team accustomed to legacy interface; no prior enterprise system cutover experience at this site scale | Poor change management adoption during UAT (Oct-Nov); high support ticket volume during hypercare (80-120 tickets/day vs projected 40); extended SLA breaches; end-user frustration drives negative sentiment post-GoLive | Deliverables do not meet customer-expectations, resulting in rework after Go-Live. |  | Change Mgmt, Training Lead | Formal Risk Review | High | 70% | threat |  |  |  |  | Mitigate | Deploy train-the-trainer program (3-day sessions) Jun-Aug for 20 super-users; pilot 12 manufacturing staff on test system by Sep 1; establish 24/7 support desk with on-site presence Nov-Jan | 2026-08-01 | not started | 2026-04-04 | High | 70%
8 | 2026-04-04 | Engineering | Seller IT ops team allocated only 2 FTE through GoLive; 70-hour work weeks required for parallel run and early hypercare; transition to Buyer payroll delayed pending org chart approval; staff skill gaps in SAP MM, WMS migrations | Insufficient ops capacity for Build phase QA, UAT infrastructure support, and initial hypercare troubleshooting; Build phase milestones missed; UAT environment stability compromised; MTTR (mean time to resolve) incidentsvaries 4-8 hours | Litigation activities are brought against the company (in public), resulting in financial or reputational loss. |  | PMO, HR, BGSW CIO | Formal Risk Review | High | 70% | threat |  |  |  |  | Mitigate | Allocate 4-FTE dedicated ops team by Jun 1; cross-train 4 buyer-side staff on Eagle systems by Sep 15; establish 24/7 incident escalation with Seller ops through Feb 6, 2027 | 2026-06-01 | in progress | 2026-04-04 | High | 70%
9 | 2026-04-04 | Engineering | API integration layer between legacy Seller ERP and standalone Eagle system incomplete; interface specifications authored by different teams; 12 integration touchpoints (purchase orders, receipts, GL, inventory) not yet mock-tested | Integration testing delays surface in Oct UAT; data reconciliation processes unstable; GL posting failures discovered post-GoLive; manual journal entry workaround required; audit trail gaps emerge in Dec compliance review |  |  | Integration Arch, QA | Formal Risk Review | High | 50% | threat |  |  |  |  | Mitigate | Complete interface specification document and mock integration environment by Jun 30; execute full integration test cycles by Aug 31; establish parallel GL reconciliation for first 30 days hypercare | 2026-06-30 | not started | 2026-04-04 | High | 50%
10 | 2026-04-04 | Manufacturing | Production system cutover (SAP inventory tracking, order fulfillment, manufacturing scheduling) occurs Nov 7-8 during peak Q4 season; shop-floor downtime tolerance is minimal (4-6 hours max); rollback capability limited by data volume (90-day transaction history must be preserved) | Shop-floor production unavailability during hypercare (Nov 8 - Feb 6); manufacturing orders cannot be tracked in real-time; inventory accuracy drifts 5-10%; revenue impact EUR 150-250K if 2-3 days extended downtime |  |  | Ops Lead, Production Control | Formal Risk Review | Very High | 30% | threat |  |  |  |  | Accept | Finalize parallel run procedures and rollback testing by Sep 30; establish 24/7 production floor support team; parallel run manual processes documented by Oct 31; limit batch processing changes to Thu-Sat windows only during hypercare | 2026-09-30 | not started | 2026-04-04 | Very High | 30%
11 | 2026-04-04 | Quality | SAT completed Oct 5; UAT window Oct 5-31 (27 calendar days, 20 business days); 15+ applications under test; 300 end-users generating test cases concurrently; test execution bottleneck expected Oct 20-27 | Critical defects (Priority 1-2) escape to production during hypercare; examples: GL posting errors preventing financial close, inventory count exceptions, shipping document generation failures; extended hypercare required beyond Feb 6 QG5 gate |  |  | QA Lead, Release Mgmt | Formal Risk Review | Very High | 70% | threat |  |  |  |  | Mitigate | Automate 60% of test cases by Sep 15 (currently 25%); deploy risk-based testing approach targeting critical path SAP modules (MM, FI-CO, SD); allocate 6 QA FTE for Oct UAT + early hypercare | 2026-09-30 | in progress | 2026-04-04 | Very High | 70%
12 | 2026-04-04 | Quality | Production Readiness Assessment (PRA) framework incomplete; QG4 (pre-GoLive) decision point Nov 1 falls mid-UAT; readiness criteria not aligned with DefectEscapeThreshold, data reconciliation completeness, or Buyer IT infrastructure validation | QG4 gate decision escalates due to unresolved defects, incomplete data validation, or infrastructure gaps; cutover delayed to Nov 15 or further; Seller ops staff demoralized; hypercare budget overruns by EUR 40K+ |  |  | PMO, PRA Lead | Formal Risk Review | High | 50% | threat |  |  |  |  | Mitigate | Define PRA criteria and gate checklist by Aug 1 comprising: UAT pass rate >95%, data validation >99%, infrastructure stress test pass, Buyer ops readiness; monthly readiness surveys from Sep onward; formal gate review Nov 1 | 2026-08-01 | not started | 2026-04-04 | High | 50%
13 | 2026-04-04 | Strategy & Portfolio | Standalone Eagle P&L tracking (cloud, ISV support, infrastructure costs) creates visibility; Buyer can now isolate Eagle OpEx from legacy business; separate cost center authorization | Buyer consolidates ISV support vendors (currently 6 providers, single-sourced on Seller side); re-bids security camera application SaaS licensing; negotiates 15-20% OpEx savings (EUR 2-3K annually); improved vendor SLA enforceability post-carve-out |  |  | Sourcing, Finance | Formal Risk Review | Moderate | 50% | opportunity |  |  |  |  | Exploit | Declare standalone cost structure and spend baseline by Sep 30; initiate vendor consolidation RFP by Dec 2026; execute re-negotiated contracts by Q2 2027 targeting EUR 40-60K annual OpEx reduction | 2026-09-30 | not started | 2026-04-04 | Moderate | 50%
14 | 2026-04-04 | Budget | ISV change-of-control clauses in security camera app licensing agreement; Seller currently holds master license; carve-out triggers 'new environment deployment' clause; ISV quotes EUR 30-50K one-time fee; license consumption may be re-metered (higher VCPU allocation = higher annual cost) | ISV invoices change-of-control fees (EUR 35K baseline scenario); vendor negotiations friction delays Build phase by 2-3 weeks (Aug-Sep); budget contingency consumed; cost allocation dispute between Seller and Buyer procurement |  |  | Sourcing, Finance, PMO | Formal Risk Review | High | 70% | threat |  |  |  |  | Transfer | Negotiate change-of-control waiver clause by May 15 (offer longer renewal term); reserve EUR 50K budget contingency; escalate ISV licensing review to CFO level if waiver blocked by Jun 15 | 2026-05-15 | not started | 2026-04-04 | High | 70%
15 | 2026-04-04 | Budget | Initial capacity planning assumed N+2 infrastructure redundancy; Buyer later specifies N+1 acceptable (cost optimization); hardware overprovisioning identified post-procurement; excess SAN storage and compute capacity | Capital overrun EUR 20-30K on hardware/infrastructure; depreciation burden extends 5 years; ROI calculation deteriorates; buyer CFO questions carve-out investment justification; budget variance analysis required for finance review |  |  | Finance, Infra Lead | Formal Risk Review | Low | 30% | threat |  |  |  |  | Accept | Finalize capacity rightsizing plan by Jun 30; reconcile hardware inventory against QG1 demand forecast; right-size SAN and compute allocation by Aug 15; document cost avoidance trade-offs | 2026-06-30 | not started | 2026-04-04 | Low | 30%
16 | 2026-04-04 | Budget | Hypercare staffing model: 24/7 support Nov 8 - Feb 6 (90 days) costs EUR 180-220K base; user adoption challenges, defect escape, and manufacturing process disruption may extend hypercare to Mar 15 (additional EUR 40-60K) | Support team overtime and contract staff extension authorized beyond Feb 6; staffing costs balloon EUR 240-280K total; resource burnout risk high; Buyer considers SLA breach penalties (EUR 15K/day) if incident resolution exceeds 8-hour response time |  |  | PMO, Finance, Support Lead | Formal Risk Review | Moderate | 50% | threat |  |  |  |  | Mitigate | Front-load UAT and defect remediation by Sep 30; establish clear SLA escalation and resolve-in-time targets by Oct 15; negotiate support contract flexibility (option to scale down by Feb 20) | 2026-09-30 | not started | 2026-04-04 | Moderate | 50%
17 | 2026-04-04 | Resources | Hypercare support window Nov 8 - Feb 6 overlaps Dec 24 - Jan 2 company-wide holiday closure; support team unavailability Nov 25-Dec 25 (US Thanksgiving, Christmas); reduced headcount Nov 22 - Jan 5; critical incidents occur during skeleton crew coverage | Support team exhaustion and burnout risk extremely high; incident MTTR stretches 12-16 hours on Dec 27-28 (holiday gap); SLA breaches accumulate; staff morale deteriorates; retention risk post-hypercare (turnover 20-30%) |  |  | PMO, HR, Support Lead | Formal Risk Review | Moderate | 70% | threat |  |  |  |  | Mitigate | Plan holiday coverage schedule by Aug 15 (rotate staff, hire temp contractors for Dec 24-Jan 2); establish 24/7 incident escalation with Seller backup support team; offer holiday bonus incentives (EUR 2-3K per person) | 2026-08-01 | not started | 2026-04-04 | Moderate | 70%
18 | 2026-04-04 | Resources | Carve-out draws heavily on Seller IT talent (Data Architect - Rajesh Kumar, Infrastructure Lead - Wei Zhang); both skills in high market demand in Singapore; other projects/employers recruiting actively through Nov 2026 | Data Architect or Infrastructure Lead departs before GoLive (Sep-Oct) or during hypercare (Nov-Dec); knowledge transfer incomplete; Eagle system troubleshooting capability degraded; incident resolution timelines extend 2-3x |  |  | PMO, HR | Formal Risk Review | High | 30% | threat |  |  |  |  | Mitigate | Develop retention packages and sign commitment letters by May 31; cross-train 2 backup resources on critical systems by Sep 15; establish knowledge base (runbooks, system architecture docs) by Aug 31 | 2026-05-31 | not started | 2026-04-04 | High | 30%
19 | 2026-04-04 | Supply Chain | Singapore ISP market has 3-4 main providers; Eagle requires dual-circuit redundancy (primary + failover) at each of 3 sites; provider capacity allocation constraints post-COVID; lead time 8-12 weeks per circuit | ISP unable to provision adequate WAN bandwidth (100+ Mbps per site) for Eagle + legacy Seller workloads by Aug 1; circuit allocation deferred to Aug 15-Sep 1; Phase 3 UAT network readiness compromised |  |  | Infra, Vendor Mgmt | Formal Risk Review | High | 30% | threat |  |  |  |  | Mitigate | Send ISP RFQ to 4 providers by May 1; establish SLA with expedite penalties (EUR 500/day late delivery); negotiate standby bandwidth from secondary provider as fallback by Jun 30 | 2026-05-15 | not started | 2026-04-04 | High | 30%
20 | 2026-04-04 | Supply Chain | Enterprise server (Cisco UCS C-series), SAN storage (NetApp), network infrastructure (Arista switches) procurement lead times 14-16 weeks; global supply chain delays; vendor allocation favoritism toward larger accounts; Eagle classified as mid-size opportunity | Equipment delivery slipped to Oct 1-15; test environment offline until Oct 1; Phase 3 UAT compressed from 4 weeks to 2-3 weeks; stress testing eliminated; UAT quality compromised; defect escape risk increases 40% |  |  | Infra Proc, Finance | Formal Risk Review | High | 50% | threat |  |  |  |  | Mitigate | Place equipment orders by Apr 25; embed expedite clauses (EUR 1000/week penalty); identify backup vendors (Dell EMC as secondary) by Apr 30; establish weekly vendor status tracking calls from May onward | 2026-05-01 | not started | 2026-04-04 | High | 50%
21 | 2026-04-04 | Legal & Compliance | Buyer legal entity registration (Singapore private limited company) still pending; Buyer entity name TBC (final shareholder approval expected May 15); PDPA compliance framework tied to entity incorporation; data protection policy unsigned; audit scheduled QG0 (late May) | PDPA audit identifies governance gaps; data protection policy missing; data processing addendum (DPA) not executed between Seller and new Buyer entity; compliance violation risk; regulatory engagement risk |  |  | Legal, DPO | Formal Risk Review | High | 70% | threat |  |  |  |  | Mitigate | Finalize Buyer entity legal registration by May 1; align Eagle data protection framework with Singapore PDPA requirements by May 10; execute data processing addendum by May 20; conduct PDPA audit completion by Jun 30 | 2026-05-15 | not started | 2026-04-04 | High | 70%
22 | 2026-04-04 | Legal & Compliance | SAP Master Software License Agreement contains change-of-control trigger clause; carve-out activates 'new environment' licensing model; SAP legal review SLA 6-8 weeks; license metrics may shift from named-user to vCPU-based consumption (cost impact EUR 50-100K) | SAP legal team initiates contract re-negotiation; license consumption model changes; annual support costs spike; Buyer CFO rejects cost; Build phase blocked by Aug 30; carve-out timeline jeopardized; potential Jul-Sep delay |  |  | Sourcing, Legal | Formal Risk Review | Very High | 70% | threat |  |  |  |  | Mitigate | Engage SAP legal by May 1; submit licensing questionnaire by May 15; escalate to SAP VP Account Management by Jun 1 if standard review exceeds 4 weeks; negotiate carve-out exception clause by Jun 30 | 2026-05-15 | not started | 2026-04-04 | Very High | 70%
23 | 2026-04-04 | Legal & Compliance | Transition Service Agreement (TSA) scope and cost model not finalized; Seller IT and Buyer IT disagreement on TSA duration (60 vs 90 vs 120 days post-GoLive); service level agreements (SLA) undefined; liability for 'unplanned situations' unresolved | TSA not executed by QG0 (expected May) or QG1 (by Aug); post-GoLive service continuity unclear; Buyer IT cannot operate Eagle systems independently if TSA expires abruptly; operational risk materializes Nov 8+ |  |  | Legal, PMO | Formal Risk Review | High | 50% | threat |  |  |  |  | Mitigate | Draft TSA SOP and service matrix by May 15; negotiate final TSA terms and pricing by Jun 30; formalize 90-day hypercare support model with defined SLA thresholds (MTTR, availability target) by Jul 31 | 2026-06-30 | not started | 2026-04-04 | High | 50%
24 | 2026-04-04 | Security & Data Protection | Legacy shared ERP (SAP) contains cross-functional user access; data entitlements not cleanly separated between Seller business units and Eagle carve-out; user registry cleanup incomplete | Security audit identifies overly permissive role assignments; Eagle data accessible to Seller IL&FS staff via legacy system backdoor; data segregation testing fails; confidentiality breach risk; audit findings require Build phase remediation |  |  | Security Arch, DPO | Formal Risk Review | High | 50% | threat |  |  |  |  | Mitigate | Conduct comprehensive data segregation and access control audit by Jun 15; remediate overly permissive roles by Aug 15; execute security re-test and sign-off by Sep 30; document data protection controls in security baseline | 2026-06-30 | not started | 2026-04-04 | High | 50%
25 | 2026-04-04 | Security & Data Protection | Disaster Recovery (DR) plan incomplete; Recovery Time Objective (RTO) and Recovery Point Objective (RPO) not defined for Eagle standalone systems; incident response escalation procedures assume Seller IT support (may be unavailable post-Feb 2027) | Production incident (security breach, data corruption, infrastructure failure) post-GoLive reveals undefined incident response procedures; Buyer IT unable to execute recovery; extended downtime 8-24 hours; SLA breach penalties accrue (EUR 1-2K/hour) |  |  | Infra, Security | Formal Risk Review | High | 30% | threat |  |  |  |  | Mitigate | Finalize DR architecture and RTO/RPO targets by Aug 31 (4-hour RTO, 1-hour RPO for transactional data); execute 2 DR drills by Oct 31; document incident response procedures (escalation, communication, recovery steps) by Sep 30 | 2026-08-31 | not started | 2026-04-04 | High | 30%
26 | 2026-04-04 | Stakeholder Relations & Public Affairs | Manufacturing shop-floor staff unfamiliar with enterprise ERP systems; low systems literacy; support ticketing processes not intuitive; staff frustration builds during UAT and hypercare due to system complexity and limited training | End-user resistance and poor adoption during hypercare Nov 8 - Feb 6; high support ticket volume (80-120/day vs 40 projected); escalations to production management; manufacturing operations team loss of confidence in Buyer IT support |  |  | Change Mgmt, User Comms | Formal Risk Review | Moderate | 70% | threat |  |  |  |  | Mitigate | Deploy comprehensive train-the-trainer program Jun-Aug (3x 2-day sessions) targeting 20 super-users; conduct 3x 1-hour user walkthroughs on key SAP MM processes by Sep 1; establish super-user support rotation with on-site presence Nov-Feb | 2026-08-31 | not started | 2026-04-04 | Moderate | 70%
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
Insert Rows Above This Line Only
Warning: Be careful adding/removing rows in the following section - these values are used for data validation
Risk Category
Technology, R&D
Engineering
Manufacturing
Quality
Strategy & Portfolio
Budget
Schedule
Resources
Supply Chain
Market & Competitors
Customers
Raw Materials
Stakeholder Relations & Public Affairs
Intellectual Property
Legal & Compliance
Ecosystems & Ethics
Security & Data Protection
Risk Source
Formal Risk Review
SQA Audit/Review
Status Meeting
Stakeholder
Other
Impact Values
|  | Very Low | 0.05
|  | Low | 0.1
|  | Moderate | 0.2
|  | High | 0.4
|  | Very High | 0.8
Probability Values
|  | 10% | 0.1
|  | 30% | 0.3
|  | 50% | 0.5
|  | 70% | 0.7
|  | 90% | 0.9
Green/Yellow/Red Threshold Values
|  | Green - maximum score | 0.05
|  | Yellow - minimum score | 0.06
|  | Yellow - maximum score | 0.14
|  | Red - minimum score | 0.15
Risk Strategy
Avoid
Transfer
Mitigate
Accept
Exploit
Enhance
Share
Status
not started
in progress
on hold
implemented
cancelled
Note on E4: Which issues could lead to the risk event?
Note on F4: When exactly does a threat become a problem repectively an opportunity become an occasion?
Note on G4: What would be the consequences?
Note on H4: If the risk event can be linked to an exact or latest date.

## Matrix
Risk Register | [14 empty] | Matrix (initial) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS | [52 empty] | Matrix (actual) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS
Probability & Impact Matrix (initial)
Probability |  | Threats |  |  |  |  | Opportunities | [9 empty] | Green/Yellow/Red Threshold Values | [52 empty] | Green/Yellow/Red Threshold Values
| 0.9 | [16 empty] | Green - maximum score |  |  | 0.05 | [49 empty] | Green - maximum score |  |  | 0.05
| 0.7 | [16 empty] | Yellow - minimum score |  |  | 0.06 | [49 empty] | Yellow - minimum score |  |  | 0.06
| 0.5 | [16 empty] | Yellow - maximum score |  |  | 0.14 | [49 empty] | Yellow - maximum score |  |  | 0.14
| 0.3 | [16 empty] | Red - minimum score |  |  | 0.15 | [49 empty] | Red - minimum score |  |  | 0.15
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
Impact
Probability & Impact Matrix (actual)
Probability |  | Threats |  |  |  |  | Opportunities
0.9
0.7
0.5
0.3
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
|  | Impact | [15 empty] | P-I # threat | [24 empty] | P-I # opportunity | [27 empty] | P-I # threat | [24 empty] | P-I # opportunity
[18 empty] | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 |  |  |  | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5
|  | Risk ID | Risk Category |  | Matrix Score | Threat / Opportunity | quantitative impact [€] | risk strategy | owner | reporting date | status | Cause | Effect | Matrix Score (actual) | Impact | Probability | [51 empty] | Impact (actual) | Probability (actual)
END OF MATRIX DATA (max 130 records)
Impact Values
| Very Low | 0.05
| Low | 0.1
| Moderate | 0.2
| High | 0.4
| Very High | 0.8
Probability Values
| Very Low | 0.1
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very High | 0.9
Green/Yellow/Red Threshold Values
| Green - maximum score | 0.05
| Yellow - minimum score | 0.06
| Yellow - maximum score | 0.14
| Red - minimum score | 0.15