## Cost Plan
GAMMA PROJECT COST PLAN
Version: | Version 1.0 - Initial Baseline
Project: | Gamma ¦ Seller: Robert Bosch China ¦ Buyer: Alibaba
Scope: | 5 sites ¦ 250 users ¦ 20 applications ¦ Pure infrastructure services ¦ No SAP
Duration: | 2026-08-01 to 2027-05-31 ¦ GoLive 2027-02-01 ¦ Combination model
Based on: | Gamma_Project_Schedule.xlsx
Risk-aligned: | Gamma_Risk_Register.xlsx
Budget baseline: | Draft labour baseline - to be approved at QG1
High-risk cross-check: | Threat risks with score >= 12 reviewed: 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 15, 16, 20
CATEGORY | RESOURCE | TOTAL DAYS | TOTAL HRS | HOURLY RATE (EUR) | TOTAL COST (EUR)
PROGRAMME MANAGEMENT & GOVERNANCE
| Alibaba PMO | 16 | 128 | 100 | 12800
| EY | 372 | 2976 | 135 | 401760
| Finance | 18 | 144 | 95 | 13680
| PMO | 157 | 1256 | 95 | 119320
| Robert Bosch China PMO | 16 | 128 | 100 | 12800
| Workstream Leads | 28 | 224 | 110 | 24640
SUBTOTAL - PROGRAMME MANAGEMENT & GOVERNANCE |  |  |  |  | 585000
LEGAL, PROCUREMENT & COMPLIANCE
| Legal | 97 | 776 | 175 | 135800
| Procurement | 94 | 752 | 95 | 71440
SUBTOTAL - LEGAL, PROCUREMENT & COMPLIANCE |  |  |  |  | 207240
INFRASTRUCTURE & CLOUD
| Alibaba Cloud | 48 | 384 | 125 | 48000
| Alibaba IT | 102 | 816 | 110 | 89760
| Infrastructure Leads | 221 | 1768 | 120 | 212160
| Robert Bosch China IT | 84 | 672 | 110 | 73920
| Robert Bosch China Infrastructure | 85 | 680 | 115 | 78200
SUBTOTAL - INFRASTRUCTURE & CLOUD |  |  |  |  | 502040
SECURITY & IDENTITY
| Alibaba Security | 50 | 400 | 125 | 50000
| Robert Bosch China IT Security | 10 | 80 | 130 | 10400
| Robert Bosch China Security | 50 | 400 | 130 | 52000
| Security Leads | 37 | 296 | 120 | 35520
SUBTOTAL - SECURITY & IDENTITY |  |  |  |  | 147920
APPLICATION & DATA TRANSITION
| Application Owners | 161 | 1288 | 100 | 128800
| Data Leads | 26 | 208 | 105 | 21840
SUBTOTAL - APPLICATION & DATA TRANSITION |  |  |  |  | 150640
TESTING & BUSINESS READINESS
| Business Key Users | 17 | 136 | 80 | 10880
| Business Leads | 2 | 16 | 100 | 1600
| EY Test Lead | 17 | 136 | 125 | 17000
| Test Lead | 28 | 224 | 110 | 24640
SUBTOTAL - TESTING & BUSINESS READINESS |  |  |  |  | 54120
CHANGE, DEPLOYMENT & TRAINING
| Communications | 36 | 288 | 80 | 23040
| Deployment Lead | 45 | 360 | 100 | 36000
| HR | 36 | 288 | 80 | 23040
| Training Lead | 58 | 464 | 80 | 37120
SUBTOTAL - CHANGE, DEPLOYMENT & TRAINING |  |  |  |  | 119200
OPERATIONS & HYPERCARE
| Alibaba ITSM | 19 | 152 | 90 | 13680
| IT Operations | 192 | 1536 | 95 | 145920
| ITSM Leads | 26 | 208 | 95 | 19760
| Infrastructure Operations | 39 | 312 | 90 | 28080
| Service Desk | 148 | 1184 | 65 | 76960
SUBTOTAL - OPERATIONS & HYPERCARE |  |  |  |  | 284400
EXECUTIVE SPONSORSHIP
| Alibaba Leadership | 12 | 96 | 180 | 17280
| Robert Bosch China Leadership | 12 | 96 | 180 | 17280
| Steering Committee | 47 | 376 | 210 | 78960
SUBTOTAL - EXECUTIVE SPONSORSHIP |  |  |  |  | 113520
OVERALL PROJECT TOTAL - LABOUR ONLY |  |  |  |  | 2164080
COST BREAKDOWN BY CATEGORY
PROGRAMME MANAGEMENT & GOVERNANCE |  |  |  |  | 585000
LEGAL, PROCUREMENT & COMPLIANCE |  |  |  |  | 207240
INFRASTRUCTURE & CLOUD |  |  |  |  | 502040
SECURITY & IDENTITY |  |  |  |  | 147920
APPLICATION & DATA TRANSITION |  |  |  |  | 150640
TESTING & BUSINESS READINESS |  |  |  |  | 54120
CHANGE, DEPLOYMENT & TRAINING |  |  |  |  | 119200
OPERATIONS & HYPERCARE |  |  |  |  | 284400
EXECUTIVE SPONSORSHIP |  |  |  |  | 113520
COST BREAKDOWN BY PHASE
Phase 0 - Mobilization and confidentiality control | 2026-08-01 to 2026-09-04 |  |  |  | 313000
Phase 1 - Concept and target-state design | 2026-09-05 to 2026-10-29 |  |  |  | 464600
Phase 2 - Build and integrated testing | 2026-10-30 to 2027-01-11 |  |  |  | 497800
Phase 3 - Final readiness and GoLive | 2027-01-12 to 2027-02-01 |  |  |  | 79680
Phase 4 - Hypercare and closure | 2027-02-02 to 2027-05-31 |  |  |  | 809000
CAPEX / ADDITIONAL COSTS - EXCLUDED FROM LABOUR TOTAL
Risk Register #1 - External antitrust and JV legal reserve | External legal support for antitrust and governance scenario rework |  |  |  | 45000
Risk Register #5 - Shared infrastructure dependency assessment reserve | External specialist support for hidden shared-service separation issues |  |  |  | 60000
Risk Register #10 - Network and certificate acceleration reserve | Provider escalation, temporary routing, and certificate contingency |  |  |  | 30000
Risk Register #11 - Dual-running and transition-service reserve | Temporary duplicate environments and service continuity uplift |  |  |  | 55000
Risk Register #13 - Contract novation and licence transfer reserve | External legal and vendor charges for change-of-control approvals |  |  |  | 40000
Risk Register #16 - Final readiness and rollback contingency | Additional command-center, testing, and rollback support around QG4 |  |  |  | 35000
TOTAL CAPEX / ADDITIONAL COSTS |  |  |  |  | 265000
NOTES
Labour totals are derived from Gamma schedule resource assignments using 8 hours per day and exact resource tokens from the schedule.
CAPEX and additional cost lines are excluded from the labour total and cross-reference Gamma risk register items with score >= 12 where external spend may be required.
Combination model note: interim service continuity is assumed only where required until the jointly managed JV steady-state model is accepted.
No SAP is in scope; the cost profile is intentionally infrastructure-heavy and sized for 5 sites, 250 users, and 20 applications.