## Schedule
ID | Outline Level | Name | Duration | Start | Finish | Predecessors | Resource Names | Notes | Milestone
1 | 1 | Phase 0 - Mobilization and confidentiality control | 35 days | 2026-08-01 | 2026-09-04 |  |  | Programme launch, restricted planning model, legal perimeter, and initial inventory for the Bosch Cloud carve-out into a 50/50 JV with Alibaba. | No
2 | 2 | 0.1 Governance and restricted planning | 19 days | 2026-08-01 | 2026-08-19 |  |  |  | No
3 | 3 | Launch core programme team and initiate Gamma confidentiality controls | 3 days | 2026-08-01 | 2026-08-03 |  | EY + Robert Bosch China IT + Alibaba IT | Only the core clean team is aware during startup because the JV and antitrust due diligence remain highly confidential. | No
4 | 3 | Establish confidentiality protocol, clean-team access, and restricted stakeholder list | 10 days | 2026-08-01 | 2026-08-10 | 3 | EY + Legal + Robert Bosch China IT Security | Planning access is tightly controlled until legal allows a broader discovery group. | No
5 | 3 | Set governance cadence, RACI, steerco path, and PMO controls | 16 days | 2026-08-04 | 2026-08-19 | 3 | EY + Robert Bosch China PMO + Alibaba PMO | Governance reflects shared management of the future 50/50 JV. | No
6 | 2 | 0.2 Legal perimeter and scoped discovery | 31 days | 2026-08-04 | 2026-09-03 |  |  |  | No
7 | 3 | Confirm carve-out perimeter, 50/50 JV assumptions, and decision rights | 12 days | 2026-08-04 | 2026-08-15 | 3 | Legal + EY + Robert Bosch China Leadership + Alibaba Leadership | Combination model remains the formal carve-out model; the 50/50 JV is the post-close governance construct. | No
8 | 3 | Launch antitrust due diligence tracker, legal workplan, and planning assumptions log | 18 days | 2026-08-04 | 2026-08-21 | 3 | Legal + EY | Legal uncertainty is treated as a hard planning dependency, not only a risk note. | No
9 | 3 | Inventory 5 sites, 250 users, 20 applications, and infrastructure service towers | 18 days | 2026-08-11 | 2026-08-28 | 4,7 | EY + Robert Bosch China Infrastructure + Alibaba IT | Scope is pure infrastructure services with no SAP in scope. | No
10 | 3 | Define discovery guardrails and phased stakeholder expansion path | 17 days | 2026-08-18 | 2026-09-03 | 4,8,9 | EY + Legal + HR + Communications | Broader validation remains constrained until legal confirms what can be disclosed. | No
11 | 3 | QG0 - Mobilization approved | 1 day | 2026-09-04 | 2026-09-04 | 5,8,9,10 | Steering Committee | Restricted-planning controls active, perimeter defined, and initial inventory complete. | Yes
12 | 1 | Phase 1 - Concept and target-state design | 55 days | 2026-09-05 | 2026-10-29 |  |  | Operating model, infrastructure target state, migration design, and formal readiness criteria. | No
13 | 2 | 1.1 Operating model and transition principles | 26 days | 2026-09-05 | 2026-09-30 |  |  |  | No
14 | 3 | Define Day 1 and Day 2 scope boundaries for the JV operating model | 12 days | 2026-09-05 | 2026-09-16 | 11 | EY + Robert Bosch China IT + Alibaba IT | Scope keeps Day 1 focused on infrastructure continuity and only the 20 in-scope applications. | No
15 | 3 | Define interim service continuity, TSA needs, and exit conditions | 15 days | 2026-09-09 | 2026-09-23 | 11 | EY + Robert Bosch China IT + Alibaba IT | Seller support is defined only where required until the new JV services are stable. | No
16 | 3 | Confirm sign-off route and approval process under legal confidentiality constraints | 14 days | 2026-09-17 | 2026-09-30 | 14,15 | EY + Legal + Steering Committee | Approvals use a narrow escalation route because only limited associates can participate. | No
17 | 2 | 1.2 Infrastructure and security target design | 33 days | 2026-09-05 | 2026-10-07 |  |  |  | No
18 | 3 | Design target hosting, network, connectivity, and environment segregation | 21 days | 2026-09-05 | 2026-09-25 | 11 | Robert Bosch China Infrastructure + Alibaba Cloud + EY | Target state is infrastructure-led and excludes SAP-related architecture. | No
19 | 3 | Design identity, access, endpoint, and security operating model | 21 days | 2026-09-12 | 2026-10-02 | 18 | Robert Bosch China Security + Alibaba Security + EY | Identity and access design supports joint governance without broadening access prematurely. | No
20 | 3 | Design collaboration, service management, monitoring, and support stack | 19 days | 2026-09-19 | 2026-10-07 | 18 | Robert Bosch China Infrastructure + Alibaba ITSM + EY | Service desk, monitoring, backup, and collaboration capabilities are defined for Day 1 operations. | No
21 | 2 | 1.3 Application and migration design | 47 days | 2026-09-12 | 2026-10-28 |  |  |  | No
22 | 3 | Classify 20 applications and decide separation pattern for each | 19 days | 2026-09-12 | 2026-09-30 | 9,11 | Application Owners + EY | Each application is classified for retain, reconfigure, replace, or retire within the JV context. | No
23 | 3 | Define migration waves for applications, users, devices, and sites | 16 days | 2026-10-01 | 2026-10-16 | 19,20,22 | EY + Deployment Lead + Infrastructure Leads | Wave design is modest because the scope is 5 sites, 250 users, and 20 applications. | No
24 | 3 | Define test strategy, cutover principles, and rollback approach | 17 days | 2026-10-05 | 2026-10-21 | 19,20,22 | EY Test Lead + Infrastructure Leads | Rollback and sign-off mechanics are formalized early due to legal and confidentiality sensitivity. | No
25 | 3 | Baseline risk register, dependency log, and entry criteria for build | 17 days | 2026-10-12 | 2026-10-28 | 16,23,24 | EY + Workstream Leads | Gamma-specific risks and dependencies are captured without borrowing reference-project content. | No
26 | 3 | QG1 - Concept approved | 1 day | 2026-10-29 | 2026-10-29 | 16,19,20,23,24,25 | Steering Committee | Target-state concept, migration design, and restricted approval path are confirmed. | Yes
27 | 1 | Phase 2 - Build and integrated testing | 74 days | 2026-10-30 | 2027-01-11 |  |  | Build core services, prepare the 20-application transition set, and complete integrated testing before final readiness. | No
28 | 2 | 2.1 Core infrastructure build | 36 days | 2026-10-30 | 2026-12-04 |  |  |  | No
29 | 3 | Build landing zone, hosting, and network segmentation | 27 days | 2026-10-30 | 2026-11-25 | 26 | Robert Bosch China Infrastructure + Alibaba Cloud | Core environment for the JV is established first to unblock downstream migration tasks. | No
30 | 3 | Build identity, IAM, endpoint, and access services | 29 days | 2026-11-02 | 2026-11-30 | 26,19 | Robert Bosch China Security + Alibaba Security | Identity controls are implemented with least-privilege access due to the restricted stakeholder model. | No
31 | 3 | Build collaboration, service desk, monitoring, and backup services | 26 days | 2026-11-09 | 2026-12-04 | 20,29 | Infrastructure Operations + ITSM Leads | Day 1 support tooling and operational monitoring are completed before system integration testing. | No
32 | 2 | 2.2 Application and data separation build | 40 days | 2026-11-09 | 2026-12-18 |  |  |  | No
33 | 3 | Reconfigure 20 applications for JV target services | 40 days | 2026-11-09 | 2026-12-18 | 22,29,30 | Application Owners + Infrastructure Leads | Application work remains intentionally lean because the scope is limited and non-SAP. | No
34 | 3 | Prepare shared data and file separation plus access remediation | 26 days | 2026-11-16 | 2026-12-11 | 29,30 | Data Leads + Security Leads | Shared repositories and access rights are remediated before formal testing starts. | No
35 | 3 | Complete third-party contract, DNS, certificate, and supplier changes | 26 days | 2026-11-16 | 2026-12-11 | 15,22 | Procurement + Legal + Infrastructure Leads | Third-party dependencies are aligned with the future JV operating model and confidentiality constraints. | No
36 | 2 | 2.3 Testing and migration rehearsal | 33 days | 2026-12-07 | 2027-01-08 |  |  |  | No
37 | 3 | Execute system integration testing across infrastructure services and 20 applications | 17 days | 2026-12-07 | 2026-12-23 | 31,33,34,35 | Test Lead + Infrastructure Leads + Application Owners | Integrated validation confirms that the infrastructure-led design supports the limited application set. | No
38 | 3 | Execute UAT with restricted business representatives and clean-team approvers | 17 days | 2026-12-14 | 2026-12-30 | 37 | Business Key Users + EY | UAT uses the limited approved representative group because broad awareness is still constrained. | No
39 | 3 | Run cutover rehearsal and rollback validation | 17 days | 2026-12-21 | 2027-01-06 | 37,38 | Infrastructure Leads + EY | Rollback evidence is required before QG2 and QG3 can be passed. | No
40 | 3 | Complete site, device, user, and communications migration packages | 19 days | 2026-12-21 | 2027-01-08 | 31,34,35 | Deployment Lead + HR + Communications | All migration packages are completed before QG2 and QG3 and before the QG4 readiness window. | No
41 | 3 | QG2 and QG3 - Build and test approved | 1 day | 2027-01-11 | 2027-01-11 | 38,39,40 | Steering Committee | Build complete, integrated testing passed, and final readiness activities may begin. | Yes
42 | 1 | Phase 3 - Final readiness and GoLive | 21 days | 2027-01-12 | 2027-02-01 |  |  | Complete residual pre-GoLive work, hold QG4, run the mandatory final readiness window, and execute Day 1 cutover. | No
43 | 2 | 3.1 Pre-GoLive completion | 14 days | 2027-01-12 | 2027-01-25 |  |  |  | No
44 | 3 | Close UAT defects and QG2 and QG3 action items | 9 days | 2027-01-12 | 2027-01-20 | 41 | Test Lead + Application Owners + Infrastructure Leads | All high-priority defects must be closed before the pre-GoLive gate. | No
45 | 3 | Complete pre-GoLive user, device, and site transitions | 10 days | 2027-01-12 | 2027-01-21 | 40,41 | Deployment Lead + Infrastructure Operations | All migrations are completed before QG4 in line with the schedule rule set. | No
46 | 3 | Complete final security, operational readiness, and support staffing check | 8 days | 2027-01-15 | 2027-01-22 | 31,41,44,45 | Security Leads + IT Operations + EY | No critical alerts, unresolved access gaps, or support staffing issues may remain at gate review. | No
47 | 3 | QG4 - Pre-GoLive approved | 1 day | 2027-01-25 | 2027-01-25 | 44,45,46 | Steering Committee | GoLive is not on the same date as QG4; a mandatory final readiness window follows. | Yes
48 | 2 | 3.2 Final readiness and open item closure | 5 days | 2027-01-26 | 2027-01-30 |  |  |  | No
49 | 3 | Verify all UAT defects and QG4 action items are closed | 2 days | 2027-01-26 | 2027-01-27 | 47 | Test Lead + PMO | This is the first mandatory final-readiness activity after QG4. | No
50 | 3 | Run final infrastructure and service readiness checks | 3 days | 2027-01-26 | 2027-01-28 | 47 | Infrastructure Operations + Security Leads | Readiness checks confirm stability, no critical alerts, and support handoff readiness. | No
51 | 3 | Execute final rollback confirmation and secure business sign-off | 2 days | 2027-01-29 | 2027-01-30 | 49,50 | EY + Business Leads + Infrastructure Leads | Final approval closes the five-day readiness period between QG4 and GoLive. | No
52 | 3 | GoLive - Day 1 cutover complete | 1 day | 2027-02-01 | 2027-02-01 | 51 | Steering Committee + Infrastructure Leads | The Gamma JV environment goes live for 5 sites, 250 users, and 20 applications on the committed date. | Yes
53 | 1 | Phase 4 - Hypercare and closure | 119 days | 2027-02-02 | 2027-05-31 |  |  | Ninety-day stabilization only after GoLive, followed by formal handover and closure. | No
54 | 2 | 4.1 Hypercare stabilization only | 90 days | 2027-02-02 | 2027-05-02 |  |  |  | No
55 | 3 | Run 24x7 incident triage and L3 support | 90 days | 2027-02-02 | 2027-05-02 | 52 | IT Operations + Service Desk | Hypercare is stabilization only and lasts 90 calendar days. | No
56 | 3 | Operate hotfix-only stabilization for infrastructure and applications | 76 days | 2027-02-02 | 2027-04-18 | 52 | Infrastructure Leads + Application Owners | Bug fixes only after GoLive; no new development, migration, or architecture change is allowed. | No
57 | 3 | Deliver user enablement, knowledge transfer, and adoption support | 58 days | 2027-02-02 | 2027-03-31 | 52 | Training Lead + Service Desk + PMO | Support focuses on stabilizing the new operating model for the restricted but growing user community. | No
58 | 2 | 4.2 Transition service exit and steady-state handover | 82 days | 2027-02-15 | 2027-05-07 |  |  |  | No
59 | 3 | Retire residual seller-hosted services and confirm exit criteria | 54 days | 2027-02-15 | 2027-04-09 | 52 | Robert Bosch China IT + Alibaba IT + EY | Only residual transition services remain after GoLive and are retired in a controlled manner. | No
60 | 3 | Finalize JV runbooks, supplier handoffs, and service ownership | 68 days | 2027-02-15 | 2027-04-23 | 52 | IT Operations + Procurement + PMO | Operational ownership is formalized for the jointly managed JV steady state. | No
61 | 3 | Confirm operational KPIs and steady-state governance handover | 26 days | 2027-04-12 | 2027-05-07 | 55,56,59,60 | Steering Committee + IT Operations + EY | Readiness for steady-state operations is confirmed after hypercare evidence and service exits are complete. | No
62 | 3 | QG5 - Project completion approved | 1 day | 2027-05-10 | 2027-05-10 | 55,59,60,61 | Steering Committee | Ninety-day hypercare is complete, transition services are exited, and operational handover is accepted. | Yes
63 | 2 | 4.3 Project closure | 21 days | 2027-05-11 | 2027-05-31 |  |  |  | No
64 | 3 | Capture lessons learned and archive project artefacts | 11 days | 2027-05-11 | 2027-05-21 | 62 | PMO + Workstream Leads | Repository artefacts and handover evidence are archived after QG5 approval. | No
65 | 3 | Close financials, confirm documentation, and issue closure report | 18 days | 2027-05-11 | 2027-05-28 | 62 | Finance + PMO | Closure report finalizes the initial v1.0 Gamma package baseline. | No
66 | 3 | Closure - Gamma programme archived | 1 day | 2027-05-31 | 2027-05-31 | 64,65 | Steering Committee | Formal closure milestone aligned with the committed completion date. | Yes