## Info
Revision history
Document Id | GAM-RR-v1.0
File Name | Gamma_Risk_Register.xlsx
Project Name | Gamma - Bosch Cloud carve-out to 50/50 JV
Project Id | Gamma v1.0
Document Owner | EY
Review Date | Reviewers |  | Changes
About this template
Risk Category | Select from categories as defined by the Risk Management Plan.
Cause | Specifically what causes the risk to become a realized issue/problem
Effect | What happens if the trigger point occurs
Owner | Risk owner.
Creation date | Date risk identified.
Source | Source of risk.
Impact | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan
Probability | Probability of risk being realized, using scales defined in the Risk Management Plan.
Matrix Score | This is calculated once you select the Impact and Probability.
Qualitative Impact | Space for further description of potential impact.
Quantitative Impact | quantitative / potential risk cost
Risk response strategy | Select from strategies as defined by the Risk Management Plan.
Status | Risk status (e.g. whether it has been triggered or not). You will need to update the values list in cells
Notes | Additional notes.
Template Version | Issue Date | Author | Changes
1.0 | 2023-12-07 | S. Hoehnel | initial template based on V5.2 of the central risk register (S. Wohlfahrt); only examples provided on top

## Risk Register
Risk Register
Risk Identification | [8 empty] | Risk Analysis | [6 empty] | Risk Response Planning |  |  | Risk Monitoring and Control
risk ID | creation date | risk category | cause(s) | event | effect(s) | risk event date | owner | source | impact | prob- ability | threat / opportunity | matrix score | qualitative impact (including period of consideration) | monetary impact [EUR] current year | monetary impact [EUR] three subsequent years | risk response strategy | measure | due date | status | reporting date | impact actual | prob- ability actual | impact (actual) | probability (actual) | matrix score (actual) | notes
1 | 05/04/2026 | Strategy & Portfolio | Antitrust due diligence for the 50/50 Gamma JV between Robert Bosch China and Alibaba is still open, and legal has only allowed a restricted clean-team planning model during Phase 0 and Phase 1. | Legal confirmation on JV perimeter and approval mechanics arrives after the 29/10/2026 QG1 concept gate, forcing redesign of Day 1 scope, transition governance, and the interim service model. | Concept rework delays Phase 2 build entry by 2 - 4 weeks, pushes vendor commitments, and increases programme management cost. | 20/10/2026 | Bosch China Legal Lead | Formal Risk Review | High | 70% | threat |  | QG1 and downstream build mobilization are directly exposed to legal timing. | 180000 | 420000 | Mitigate | Run a weekly legal dependency review, maintain an assumptions log approved by legal, prepare a fallback Day 1 perimeter by 30/09/2026, and pre-draft alternate governance approvals before QG1. | 15/10/2026 | in progress | 05/04/2026 | High | 70% |  |  |  | Top strategic risk because legal uncertainty is a true schedule dependency in Gamma.
2 | 05/04/2026 | Legal & Compliance | High confidentiality and the very limited aware stakeholder group require restricted distribution of designs, inventories, and migration plans across Bosch China, Alibaba, and vendors. | Sensitive JV information is shared beyond the approved clean-team perimeter during discovery or design workshops, triggering legal escalation and an immediate freeze on collaboration sessions. | Planning pauses, trust between parties deteriorates, and the project faces reputational and compliance consequences. | 30/09/2026 | EY PMO Lead | Formal Risk Review | Very High | 50% | threat |  | A confidentiality incident would halt planning at the most sensitive stage of the programme. | 150000 | 300000 | Mitigate | Use named-access workspaces only, maintain an approved audience register, watermark pack distributions, and require legal review before any stakeholder expansion. | 01/09/2026 | in progress | 05/04/2026 | Very High | 50% |  |  |  | This risk is unique to Gamma because awareness is intentionally constrained.
3 | 05/04/2026 | Schedule | Because only a small clean team can validate assumptions, discovery across 5 sites, 250 users, and 20 applications depends on serial rather than parallel interviews and reviews. | Inventory confirmation and dependency mapping remain incomplete by 03/09/2026, causing QG0 output quality gaps and compressing the concept phase. | Schedule float is consumed before build starts, and downstream test preparation is forced into a shorter window. | 03/09/2026 | EY PMO Lead | Status Meeting | High | 70% | threat |  | Early timeline compression creates persistent pressure on QG1, QG2 and QG3, and QG4 readiness. | 90000 | 180000 | Mitigate | Lock a discovery calendar for the clean team, prioritize critical infrastructure towers first, and use staged inventory validation with weekly variance closure. | 28/08/2026 | in progress | 05/04/2026 | High | 70% |  |  |  | Gamma schedule risk is driven more by restricted access than by raw scale.
4 | 05/04/2026 | Resources | The same limited group of legal, infrastructure, and leadership staff are serving as clean-team reviewers, approvers, and subject matter experts during the first two phases. | Key clean-team members become unavailable during concept sign-off or build mobilization, leaving no approved back-up resources for decisions and validations. | Decision latency increases, rework grows, and issue resolution extends into the critical path. | 29/10/2026 | EY PMO Lead | Status Meeting | High | 50% | threat |  | A small approved resource pool creates single-person dependency risk across multiple gates. | 80000 | 160000 | Mitigate | Nominate alternates who can be pre-cleared by legal, reserve capacity for clean-team SMEs, and escalate conflicting assignments in weekly steerco. | 15/09/2026 | not started | 05/04/2026 | High | 50% |  |  |  | Resource concentration is high despite the smaller programme size.
5 | 05/04/2026 | Technology, R&D | The Bosch Cloud business relies on shared Bosch China infrastructure services, and 20 in-scope applications may still have hidden dependencies on shared network, identity, monitoring, backup, or certificates. | Previously undocumented shared service dependencies are discovered during build or SIT, requiring late redesign of the target hosting and connectivity model. | Phase 2 build expands, integration testing slips, and GoLive readiness is weakened. | 15/12/2026 | Bosch China Infrastructure Lead | Formal Risk Review | Very High | 70% | threat |  | Shared infrastructure blind spots are the largest technical threat to the Gamma build plan. | 200000 | 350000 | Mitigate | Run dependency walk-throughs by tower, require evidence for each of the 20 applications, and validate shared-service assumptions before 30/10/2026 build start. | 23/10/2026 | not started | 05/04/2026 | Very High | 70% |  |  |  | The pure infrastructure scope concentrates risk in shared platform dependencies rather than SAP complexity.
6 | 05/04/2026 | Security & Data Protection | Identity and privileged access are being redesigned while the project is still operating with restricted stakeholder access and partially shared Bosch China administration patterns. | JV users or administrators retain inherited Bosch China privileges after cutover, leaving over-entitled access to shared directories, service consoles, or operational tooling. | Unauthorized access, audit findings, and manual remediation during hypercare undermine Day 1 stability. | 01/02/2027 | Bosch China Security Lead | Formal Risk Review | Very High | 50% | threat |  | Identity leakage across the shared-to-JV boundary would create both security and operational disruption. | 160000 | 320000 | Mitigate | Define role matrices early, certify privileged access before QG2 and QG3, and execute an independent access recertification before QG4. | 15/01/2027 | not started | 05/04/2026 | Very High | 50% |  |  |  | Security design is central to Gamma because the future JV is jointly managed.
7 | 05/04/2026 | Security & Data Protection | Monitoring, logging, backups, and shared file repositories may still contain mixed Bosch China and Gamma JV operational data after separation design is approved. | Data segregation gaps are discovered in logs, backups, or archive repositories during testing or after GoLive, exposing non-Gamma records to the JV support team. | Compliance breach, emergency cleanup activity, and delayed acceptance of the target operational model. | 20/01/2027 | Data Protection Officer | Formal Risk Review | High | 50% | threat |  | Operational datasets are often missed because they sit outside core application inventories. | 120000 | 250000 | Mitigate | Include logs, backups, and archives in the inventory, define explicit segregation checks, and add data-protection sign-off to the QG4 evidence pack. | 12/01/2027 | not started | 05/04/2026 | High | 50% |  |  |  | Gamma has lower application volume but still meaningful operational data-protection exposure.
8 | 05/04/2026 | Quality | UAT is intentionally limited to a narrow set of approved representatives because broader business awareness is still constrained by legal confidentiality. | The reduced UAT group fails to cover critical business and operational scenarios across the 20 applications and the core infrastructure workflows. | Defects surface during final readiness or early hypercare, increasing incident volume and reducing user confidence in the cutover. | 30/12/2026 | EY Test Lead | Status Meeting | High | 70% | threat |  | Testing depth is constrained by confidentiality rather than by lack of planning discipline. | 95000 | 170000 | Mitigate | Expand scenario coverage through scripted walkthroughs, supplement business UAT with SME dry runs, and require defect trend review before QG2 and QG3 approval. | 18/12/2026 | not started | 05/04/2026 | High | 70% |  |  |  | This is one of the strongest links between confidentiality and delivery quality.
9 | 05/04/2026 | Customers | The Bosch Cloud business provides infrastructure services, so the 250 users and dependent service consumers have low tolerance for outages during identity, network, and application cutover. | Service continuity fails on 01/02/2027 because network, authentication, or shared tooling do not transition cleanly for the first working day in the new environment. | Customer-facing service degradation, urgent rollback pressure, and reputational damage for both JV shareholders. | 01/02/2027 | Bosch China Operations Lead | Stakeholder | Very High | 50% | threat |  | Day 1 stability is a visible business outcome and a joint reputational event for Bosch and Alibaba. | 220000 | 400000 | Mitigate | Rehearse the cutover, verify critical service chains, pre-stage command center runbooks, and maintain validated rollback criteria through the final readiness window. | 29/01/2027 | not started | 05/04/2026 | Very High | 50% |  |  |  | Customer/service continuity risk is elevated because Gamma is infrastructure service heavy.
10 | 05/04/2026 | Supply Chain | Network circuits, DNS changes, certificates, and third-party enablement for 5 sites and 20 applications still depend on external providers and approval lead times. | Provider lead times exceed plan, leaving one or more sites or shared services without the required certificates, routing, or external connectivity for integrated testing and cutover. | SIT defects remain open, pre-GoLive completion slips, and manual workarounds increase operational risk. | 11/01/2027 | Bosch China Infrastructure Lead | Status Meeting | High | 50% | threat |  | Third-party technical lead times directly influence QG2 and QG3 and QG4 readiness. | 70000 | 110000 | Mitigate | Submit provider requests early, track certificates and circuit milestones weekly, and define temporary fallback routing for priority services. | 30/11/2026 | in progress | 05/04/2026 | High | 50% |  |  |  | A smaller site count lowers volume but not dependency sensitivity.
11 | 05/04/2026 | Budget | If legal decisions or third-party approvals arrive late, Gamma may need extended dual running, extra transition services, and more PMO effort beyond the initial v1.0 baseline. | Temporary seller-hosted services and duplicated environments stay active beyond the planned build and readiness windows. | The cost plan requires an uplift, and management approval is needed for unplanned run costs during late build or hypercare. | 25/01/2027 | EY Finance Lead | Formal Risk Review | Moderate | 70% | threat |  | Budget pressure is more likely than severe because the project is smaller, but dual running can still add material cost. | 110000 | 140000 | Mitigate | Track transition-service demand monthly, define a clear exit baseline in the cost plan, and escalate any extension request through steerco within five working days. | 15/01/2027 | not started | 05/04/2026 | Moderate | 70% |  |  |  | This risk will directly inform the Gamma cost-plan contingency.
12 | 05/04/2026 | Ecosystems & Ethics | The future operating model is a 50/50 jointly managed JV, which can create split accountability and slower decisions if responsibilities are not explicit by QG1 and QG4. | Bosch China and Alibaba disagree on service ownership, priority defects, or acceptance criteria during build or final readiness. | Critical decisions stall, support ownership remains ambiguous, and the post-GoLive run model is weaker than planned. | 25/01/2027 | Gamma Steering Committee Chair | Stakeholder | High | 50% | threat |  | Joint governance ambiguity can turn minor operational issues into gate-blocking issues. | 85000 | 160000 | Mitigate | Document service ownership in the operating model, pre-approve decision rights, and require both parties to sign the final readiness acceptance matrix. | 20/01/2027 | not started | 05/04/2026 | High | 50% |  |  |  | This is a Gamma-specific governance risk driven by the 50/50 JV structure.
13 | 05/04/2026 | Legal & Compliance | Several of the 20 applications and supporting services may have contracts, licences, or processing terms that require change-of-control approval for the new JV structure. | One or more providers do not approve the transfer or require terms that are not acceptable before cutover. | Scope exceptions, delayed cutover readiness, or unplanned replacement work are required for affected services. | 12/12/2026 | Procurement Lead | Formal Risk Review | High | 50% | threat |  | A small number of blocked providers could still create a large operational gap because the application landscape is compact. | 100000 | 180000 | Mitigate | Complete contract review during concept phase, contact affected vendors by 31/10/2026, and define alternatives for any provider without timely consent. | 30/11/2026 | not started | 05/04/2026 | High | 50% |  |  |  | The smaller portfolio makes early vendor outreach feasible and essential.
14 | 05/04/2026 | Stakeholder Relations & Public Affairs | Because only limited associates are aware of the carve-out and JV plan, rumors or partial disclosures can spread without an approved narrative or response plan. | Uncontrolled internal discussion reaches broader teams, suppliers, or customers before formal communication windows are approved. | Stakeholder anxiety rises, cooperation drops, and management spends time on damage control instead of execution. | 30/11/2026 | Communications Lead | Stakeholder | Moderate | 50% | threat |  | Narrative gaps can create avoidable friction even when technical work remains on plan. | 40000 | 70000 | Mitigate | Prepare confidential Q and A packs, align response owners, and release controlled stakeholder messages in phases approved by legal. | 15/10/2026 | not started | 05/04/2026 | Moderate | 50% |  |  |  | Communication control is a management discipline risk rather than a pure technical issue.
15 | 05/04/2026 | Technology, R&D | The new JV operating model depends on monitoring, incident routing, service desk procedures, and support tooling being ready before the 01/02/2027 cutover. | Operational tooling is only partially configured by the time SIT closes, leaving alert routing, ticket triage, or backup reporting incomplete at GoLive. | Incident response slows during hypercare and early production issues take longer to diagnose and resolve. | 25/01/2027 | Operations Lead | Status Meeting | High | 50% | threat |  | Service-management immaturity would turn manageable technical issues into prolonged outages. | 90000 | 150000 | Mitigate | Treat operational tooling as a gateable deliverable, run command-center rehearsals, and include service desk proof points in the QG4 evidence pack. | 19/01/2027 | not started | 05/04/2026 | High | 50% |  |  |  | This risk aligns directly with schedule task 31 and the final readiness phase.
16 | 05/04/2026 | Schedule | Gamma has a firm GoLive on 01/02/2027 and a five-day final-readiness window after QG4, leaving limited tolerance for residual defects, unclosed actions, or incomplete migrations. | One or more QG4 prerequisites remain open on 25/01/2027, leaving insufficient time to close defects, re-run checks, and secure business sign-off before GoLive. | Management must choose between delaying GoLive or accepting elevated operational and governance risk. | 25/01/2027 | EY PMO Lead | Formal Risk Review | Very High | 50% | threat |  | This is the principal gate risk tied to the QG4 to GoLive buffer. | 140000 | 220000 | Mitigate | Run a daily readiness burn-down from 12/01/2027, freeze non-essential changes, and escalate any red item within 24 hours to steerco. | 22/01/2027 | not started | 05/04/2026 | Very High | 50% |  |  |  | Directly linked to the mandatory QG4 and final-readiness rules in the schedule skill.
17 | 05/04/2026 | Technology, R&D | Gamma has no SAP and only about 20 applications in scope, which reduces interface complexity and allows deeper engineering attention on the infrastructure and identity stack. | The smaller application footprint enables earlier completion of SIT and a lower open-defect count than planned before QG2 and QG3. | Build stabilizes sooner, QG4 readiness improves, and management gains schedule buffer for legal or supplier-driven issues. | 11/01/2027 | Bosch China Infrastructure Lead | Other | Moderate | 70% | opportunity |  | Gamma can benefit from a relatively compact application estate if execution stays disciplined. | 60000 | 120000 | Exploit | Prioritize early application classification, keep scope discipline, and redirect saved effort into security hardening and operational readiness. | 18/12/2026 | not started | 05/04/2026 | Moderate | 70% |  |  |  | First positive risk - smaller scope can create usable contingency.
18 | 05/04/2026 | Budget | The carve-out is pure infrastructure services, which creates an opportunity to standardize cloud operations, remove legacy duplications, and consolidate vendors in the new JV run model. | The project identifies vendor and platform simplifications during build and hypercare that can be locked into the Day 2 operating model without additional delivery risk. | The JV reduces recurring run cost and simplifies the support footprint in the first three years after cutover. | 07/05/2027 | EY Finance Lead | Other | Moderate | 50% | opportunity |  | A focused infrastructure scope can unlock meaningful steady-state savings if captured intentionally. | 50000 | 250000 | Enhance | Track standardization candidates during build, validate savings in hypercare, and include approved simplifications in the post-GoLive handover plan. | 30/04/2027 | not started | 05/04/2026 | Moderate | 50% |  |  |  | Second positive risk - operating-model simplification can offset part of the carve-out cost.
19 | 05/04/2026 | Intellectual Property | Bosch Cloud automation scripts, runbooks, and operational patterns may need to be shared selectively with the new JV team while confidentiality and ownership boundaries are still being defined. | Proprietary Bosch operational content is transferred to the JV without the right usage restrictions, inventory, or approval trail. | Intellectual-property exposure creates legal cleanup work, governance friction, and re-documentation effort. | 23/04/2027 | Bosch China Legal Lead | Formal Risk Review | Moderate | 30% | threat |  | The risk is narrower than in product carve-outs but still relevant because Gamma is infrastructure-led. | 45000 | 90000 | Mitigate | Classify operational artefacts, define approved sharing boundaries, and require legal approval for any proprietary automation transferred into the JV runbook set. | 31/03/2027 | not started | 05/04/2026 | Moderate | 30% |  |  |  | Gamma IP exposure is concentrated in operational know-how rather than product IP.
20 | 05/04/2026 | Resources | Because broader user exposure is delayed, training and support preparation may remain lighter than the actual demand created at GoLive across 250 users and 5 sites. | Incident and support demand in the first four weeks of hypercare exceeds plan, and the command center does not have enough skilled staff to sustain response times. | Ticket backlogs grow, user confidence drops, and the hypercare period risks extension beyond the planned 90 days. | 20/02/2027 | Operations Lead | Status Meeting | High | 50% | threat |  | Support under-capacity is a realistic early-life risk when awareness and training are intentionally constrained. | 75000 | 100000 | Mitigate | Model hypercare demand from pilot issues, reserve surge support capacity, and refresh training packs before 31/01/2027. | 25/01/2027 | not started | 05/04/2026 | High | 50% |  |  |  | Links directly to the 90-day stabilization-only phase in the schedule baseline.
Technology, R&D
Engineering
Manufacturing
Quality
Strategy & Portfolio
Budget
Schedule
Resources
Supply Chain
Market & Competitors
Customers
Raw Materials
Stakeholder Relations & Public Affairs
Intellectual Property
Legal & Compliance
Ecosystems & Ethics
Security & Data Protection
Risk Source
Formal Risk Review
SQA Audit/Review
Status Meeting
Stakeholder
Other
Impact Values
|  | Very Low | 0.05
|  | Low | 0.1
|  | Moderate | 0.2
|  | High | 0.4
|  | Very High | 0.8
Probability Values
|  | 10% | 0.1
|  | 30% | 0.3
|  | 50% | 0.5
|  | 70% | 0.7
|  | 90% | 0.9
Green/Yellow/Red Threshold Values
|  | Green - maximum score | 0.05
|  | Yellow - minimum score | 0.06
|  | Yellow - maximum score | 0.14
|  | Red - minimum score | 0.15
Risk Strategy
Avoid
Transfer
Mitigate
Accept
Exploit
Enhance
Share
Status
not started
in progress
on hold
implemented
cancelled
Note on E4: Which issues could lead to the risk event?
Note on F4: When exactly does a threat become a problem repectively an opportunity become an occasion?
Note on G4: What would be the consequences?
Note on H4: If the risk event can be linked to an exact or latest date.

## Matrix
Risk Register | [14 empty] | Matrix (initial) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS | [52 empty] | Matrix (actual) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS
Probability & Impact Matrix (initial)
Probability |  | Threats |  |  |  |  | Opportunities | [9 empty] | Green/Yellow/Red Threshold Values | [52 empty] | Green/Yellow/Red Threshold Values
| 0.9 | [16 empty] | Green - maximum score |  |  | 0.05 | [49 empty] | Green - maximum score |  |  | 0.05
| 0.7 | [16 empty] | Yellow - minimum score |  |  | 0.06 | [49 empty] | Yellow - minimum score |  |  | 0.06
| 0.5 | [16 empty] | Yellow - maximum score |  |  | 0.14 | [49 empty] | Yellow - maximum score |  |  | 0.14
| 0.3 | [16 empty] | Red - minimum score |  |  | 0.15 | [49 empty] | Red - minimum score |  |  | 0.15
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
Impact
Probability & Impact Matrix (actual)
Probability |  | Threats |  |  |  |  | Opportunities
0.9
0.7
0.5
0.3
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
|  | Impact | [15 empty] | P-I # threat | [24 empty] | P-I # opportunity | [27 empty] | P-I # threat | [24 empty] | P-I # opportunity
[18 empty] | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 |  |  |  | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5
|  | Risk ID | Risk Category |  | Matrix Score | Threat / Opportunity | quantitative impact [€] | risk strategy | owner | reporting date | status | Cause | Effect | Matrix Score (actual) | Impact | Probability | [51 empty] | Impact (actual) | Probability (actual)
END OF MATRIX DATA (max 130 records)
Impact Values
| Very Low | 0.05
| Low | 0.1
| Moderate | 0.2
| High | 0.4
| Very High | 0.8
Probability Values
| Very Low | 0.1
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very High | 0.9
Green/Yellow/Red Threshold Values
| Green - maximum score | 0.05
| Yellow - minimum score | 0.06
| Yellow - maximum score | 0.14
| Red - minimum score | 0.15