## Slide 1
Gamma
Bosch Cloud business | Combination model | Stakeholder presentation
Seller: Robert Bosch China
Buyer / JV partner: Alibaba
Report date: 05 April 2026
Baseline version: v1.0

## Slide 2
Executive Summary
Management view from the current Gamma baseline outputs
Gamma | 05 Apr 2026 | Confidential
Gamma separates the Bosch Cloud business from Robert Bosch China and establishes the Day 1 operating baseline for a 50/50 JV with Alibaba.
Scope is intentionally lean for Day 1: 5 sites, 250 users, 20 applications, and no SAP. Delivery concentration is therefore on infrastructure, identity, operations, and confidentiality control.
The current status is a pre-start baseline: the schedule, risk register, cost plan, charter, dashboards, and monthly report are complete, but execution is still dependent on legal and disclosure timing.
Executive focus remains on antitrust due diligence, clean-team governance, and early confirmation of shared-service dependencies before mobilization starts on 01 Aug 2026.

## Slide 3
Scope And Operating Model
What Gamma must deliver at Day 1
Gamma | 05 Apr 2026 | Confidential
In scope: infrastructure separation, identity and security redesign, service management readiness, transition of 20 applications, and operational handover for 250 users across 5 sites.
Out of scope: SAP, manufacturing / OT, and broad Day 2 transformation beyond the minimum viable JV operating baseline.
Combination model: the project may use interim service continuity during transition, but the target state is a jointly managed JV environment rather than a permanent shared platform.
The 50/50 governance structure requires clear decision rights before QG1 and again before QG4, because ambiguity at either gate would directly erode GoLive confidence.

## Slide 4
Timeline And Quality Gates
Milestones reconciled to the generated Gamma schedule
Gamma | 05 Apr 2026 | Confidential
Milestone | Date
QG0 - Mobilization approved | 04 Sep 2026
QG1 - Concept approved | 29 Oct 2026
QG2 and QG3 - Build and test approved | 11 Jan 2027
QG4 - Pre-GoLive approved | 25 Jan 2027
GoLive - Day 1 cutover complete | 01 Feb 2027
QG5 - Project completion approved | 10 May 2027
Closure - Gamma programme archived | 31 May 2027
Key dates: QG1 29 Oct 2026 | GoLive 01 Feb 2027 | QG5 10 May 2027

## Slide 5
Budget And Cost Structure
Labour baseline separated from risk-driven contingency
Gamma | 05 Apr 2026 | Confidential
Category | Amount
PROGRAMME MANAGEMENT & GOVERNANCE | EUR 585,000
INFRASTRUCTURE & CLOUD | EUR 502,040
OPERATIONS & HYPERCARE | EUR 284,400
LEGAL, PROCUREMENT & COMPLIANCE | EUR 207,240
Labour baseline total | EUR 2,164,080
CAPEX / additional costs | EUR 265,000
Budget anchor: Labour EUR 2,164,080 | CAPEX / additional EUR 265,000 | Draft baseline for QG1 approval

## Slide 6
Top Risks And Management Actions
Threat risks reconciled to the Gamma risk register
Gamma | 05 Apr 2026 | Confidential
Risk | Category | Score | Executive issue
#5 | Technology, R&D | 20 | Previously undocumented shared service dependencies are discovered during build or SIT, requiring late redesign of the target hosting and connectivity model.
#1 | Strategy & Portfolio | 16 | Legal confirmation on JV perimeter and approval mechanics arrives after the 29/10/2026 QG1 concept gate, forcing redesign of Day 1 scope, transition governance, and the interim service model.
#3 | Schedule | 16 | Inventory confirmation and dependency mapping remain incomplete by 03/09/2026, causing QG0 output quality gaps and compressing the concept phase.
#8 | Quality | 16 | The reduced UAT group fails to cover critical business and operational scenarios across the 20 applications and the core infrastructure workflows.
#2 | Legal & Compliance | 15 | Sensitive JV information is shared beyond the approved clean-team perimeter during discovery or design workshops, triggering legal escalation and an immediate freeze on collaboration sessions.
Risk anchors: #5 Technology, R&D (20) | #1 Strategy & Portfolio (16) | #3 Schedule (16) | #8 Quality (16) | #2 Legal & Compliance (15) | #16 Schedule (15)

## Slide 7
Decisions Required
Immediate steerco focus for a clean mobilisation
Gamma | 05 Apr 2026 | Confidential
Confirm the legal and antitrust decision path that will govern clean-team expansion and future stakeholder disclosure.
Approve the named clean-team resource pool across PMO, legal, infrastructure, security, and operations before the 01 Aug 2026 kickoff.
Approve the draft labour baseline and associated contingency reserve for QG1 so that external legal, provider, and readiness support can be activated quickly if needed.
Endorse the principle that Day 1 scope stays intentionally lean - no SAP, no broad Day 2 transformation, and no migration activity after GoLive.