## Cost Plan
Trinity-CAM (GPT) ¦ IT CARVE-OUT COST PLAN
Project | Trinity-CAM (GPT)
Seller | Johnson Controls International (JCI)
Buyer | Bosch
Business | Air conditioning business
Carve-out Model | Integration - JCI IT to merger zone to Bosch IT
Based on | Trinity-CAM (GPT)_Project_Schedule.xlsx
Risk-aligned | Trinity-CAM (GPT)_Risk_Register.xlsx
Budget Baseline | TBC - to be approved at QG1
Note | Bosch and JCI internal resource lines are tracked at zero rate for schedule traceability and excluded from the billable labour baseline. Change Request 1 confirms the approved JCI TSA extension through 31 Jul 2027 as additional delivery buffer rather than a programme-progress reset.
CATEGORY | RESOURCE | TOTAL DAYS | TOTAL HRS | HOURLY RATE (EUR) | TOTAL COST (EUR)
Bosch Internal Support - Tracked Only
Bosch Internal Support - Tracked Only | Bosch Business Lead | 75 | 600 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch HR Lead | 62 | 496 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch IT Manager | 441 | 3528 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch Legal Counsel | 35 | 280 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch Sponsor | 12 | 96 | 0 | 0
Subtotal - Bosch Internal Support - Tracked Only |  | 625 |  |  | 0
Infosys - Application and Data Delivery
Infosys - Application and Data Delivery | Infosys Application Lead | 482 | 3856 | 120 | 462720
Infosys - Application and Data Delivery | Infosys Data Migration Lead | 240 | 1920 | 125 | 240000
Infosys - Application and Data Delivery | Infosys QA Lead | 134 | 1072 | 110 | 117920
Subtotal - Infosys - Application and Data Delivery |  | 856 |  |  | 820640
Infosys - Platform, Security, and Workplace
Infosys - Platform, Security, and Workplace | Infosys Cloud Lead | 150 | 1200 | 130 | 156000
Infosys - Platform, Security, and Workplace | Infosys IAM Lead | 210 | 1680 | 125 | 210000
Infosys - Platform, Security, and Workplace | Infosys Infrastructure Architect | 242 | 1936 | 130 | 251680
Infosys - Platform, Security, and Workplace | Infosys Network Lead | 165 | 1320 | 120 | 158400
Infosys - Platform, Security, and Workplace | Infosys Security Lead | 160 | 1280 | 130 | 166400
Infosys - Platform, Security, and Workplace | Infosys Workplace Lead | 230 | 1840 | 115 | 211600
Subtotal - Infosys - Platform, Security, and Workplace |  | 1157 |  |  | 1154080
Infosys - Programme and Service Delivery
Infosys - Programme and Service Delivery | Infosys Programme Manager | 253 | 2024 | 145 | 293480
Infosys - Programme and Service Delivery | Infosys Service Delivery Lead | 539 | 4312 | 125 | 539000
Subtotal - Infosys - Programme and Service Delivery |  | 792 |  |  | 832480
Infosys - SAP Delivery
Infosys - SAP Delivery | Infosys SAP Lead | 366 | 2928 | 145 | 424560
Subtotal - Infosys - SAP Delivery |  | 366 |  |  | 424560
JCI Internal Support - Tracked Only
JCI Internal Support - Tracked Only | JCI Application Owner | 52 | 416 | 0 | 0
JCI Internal Support - Tracked Only | JCI Business Lead | 55 | 440 | 0 | 0
JCI Internal Support - Tracked Only | JCI HR Lead | 62 | 496 | 0 | 0
JCI Internal Support - Tracked Only | JCI IT Manager | 306 | 2448 | 0 | 0
JCI Internal Support - Tracked Only | JCI Legal Counsel | 85 | 680 | 0 | 0
JCI Internal Support - Tracked Only | JCI SAP Owner | 102 | 816 | 0 | 0
JCI Internal Support - Tracked Only | JCI Sponsor | 12 | 96 | 0 | 0
Subtotal - JCI Internal Support - Tracked Only |  | 674 |  |  | 0
KPMG - Architecture and Migration Advisory
KPMG - Architecture and Migration Advisory | KPMG Data Architect | 95 | 760 | 180 | 136800
KPMG - Architecture and Migration Advisory | KPMG Enterprise Architect | 227 | 1816 | 190 | 345040
KPMG - Architecture and Migration Advisory | KPMG Infrastructure Architect | 292 | 2336 | 185 | 432160
KPMG - Architecture and Migration Advisory | KPMG Security Architect | 145 | 1160 | 190 | 220400
KPMG - Architecture and Migration Advisory | KPMG Workplace Lead | 145 | 1160 | 165 | 191400
Subtotal - KPMG - Architecture and Migration Advisory |  | 904 |  |  | 1325800
KPMG - Programme Governance
KPMG - Programme Governance | KPMG Change Lead | 102 | 816 | 150 | 122400
KPMG - Programme Governance | KPMG PMO Lead | 175 | 1400 | 220 | 308000
KPMG - Programme Governance | KPMG Project Manager | 340 | 2720 | 170 | 462400
Subtotal - KPMG - Programme Governance |  | 617 |  |  | 892800
KPMG - SAP Advisory
KPMG - SAP Advisory | KPMG SAP Architect | 252 | 2016 | 210 | 423360
Subtotal - KPMG - SAP Advisory |  | 252 |  |  | 423360
KPMG - Testing, Deployment, and Readiness
KPMG - Testing, Deployment, and Readiness | KPMG Deployment Lead | 105 | 840 | 150 | 126000
KPMG - Testing, Deployment, and Readiness | KPMG Test Lead | 209 | 1672 | 155 | 259160
Subtotal - KPMG - Testing, Deployment, and Readiness |  | 314 |  |  | 385160
OVERALL PROJECT TOTAL |  |  |  |  | 6258880
Cost Breakdown by Category
Bosch Internal Support - Tracked Only |  | 625 |  |  | 0
Infosys - Application and Data Delivery |  | 856 |  |  | 820640
Infosys - Platform, Security, and Workplace |  | 1157 |  |  | 1154080
Infosys - Programme and Service Delivery |  | 792 |  |  | 832480
Infosys - SAP Delivery |  | 366 |  |  | 424560
JCI Internal Support - Tracked Only |  | 674 |  |  | 0
KPMG - Architecture and Migration Advisory |  | 904 |  |  | 1325800
KPMG - Programme Governance |  | 617 |  |  | 892800
KPMG - SAP Advisory |  | 252 |  |  | 423360
KPMG - Testing, Deployment, and Readiness |  | 314 |  |  | 385160
Cost Breakdown by Phase
Phase 0: Mobilize carve-out governance and TSA baseline | 2026-07-01 to 2026-10-01 |  |  |  | 388440
Phase 1: Discover landscape and design the merger zone | 2026-10-02 to 2027-01-31 |  |  |  | 1319320
Phase 2: Build merger zone and prepare transition factory | 2027-02-01 to 2027-07-31 |  |  |  | 2493560
Phase 3: Test, migrate to merger zone, and prepare Bosch landing | 2027-08-01 to 2027-12-10 |  |  |  | 1194440
Phase 4: Final readiness and GoLive decision | 2027-12-11 to 2028-01-01 |  |  |  | 53560
Phase 5: Hypercare, TSA exit, and Bosch handover | 2028-01-02 to 2028-04-01 |  |  |  | 809560
CAPEX / Additional Costs - Excluded from Labour Total
SAP expert support and rehearsal contingency | Risk Register R001 - external SAP carve-out support, rehearsal environment, and specialist remediation capacity. |  |  | 600,000 - 1,200,000
Merger-zone platform acceleration reserve | Risk Register R002 - additional platform engineering or temporary capacity if merger-zone build slips. |  |  | 400,000 - 900,000
Cutover command-center and rollback reserve | Risk Register R003 - final cutover defect sprint, extended command center, and rollback rehearsal support. |  |  | 250,000 - 500,000
Cyber control uplift and incident readiness | Risk Register R007 - DLP, logging, security review, and cyber readiness controls for the merger zone. |  |  | 250,000 - 500,000
Platform procurement and fallback capacity | Risk Register R012 - long-lead platform and connectivity fallback capacity. |  |  | 200,000 - 450,000
Regional hosting and legal compliance provision | Risk Register R014 - data sovereignty remediation or local hosting design changes if required. |  |  | TBC - confirm at QG1
Third-party audit and supplier-governance provision | Risk Register R020 - subcontractor audit and compliance assurance if external delivery layers expand. |  |  | 100,000 - 200,000
1. Derived from the generated schedule and aligned to the generated risk register rather than copied from any legacy project.
2. Phase names and dates match the schedule exactly: Phase 0 through Phase 5 as generated for Trinity-CAM (GPT).
3. Every schedule resource token has a matching cost line; Bosch and JCI internal roles are tracked at zero rate to preserve resource traceability without inflating the external labour baseline.
4. Integration-model note: the merger zone is a temporary operational bridge between JCI and Bosch, so platform and security contingencies are carried separately from labour totals. The approved TSA extension through 31 Jul 2027 reduces pressure on Bosch and gives Infosys more build-up time while users remain on legacy JCI.
5. High-priority risk references for contingency lines: R001, R002, R003, R007, R012, R014, and R020.
6. Budget baseline remains TBC - to be approved at QG1. The approved TSA extension is treated as schedule buffer and commercial protection, not as labour-plan progress change.