## Schedule
ID | Outline Level | Name | Duration | Start | Finish | Predecessors | Resource Names | Notes | Milestone
1 | 1 | Phase 0: Mobilize carve-out governance and TSA baseline | 92 days | 2026-07-01 | 2026-10-01 |  |  | Programme launch, TSA framing, approved extension control, partner mobilisation, and QG1 concept approval under change request version 1.1. | No
2 | 2 | 0.1 Governance and partner mobilization | 60 days | 2026-07-01 | 2026-08-30 |  |  | PMO setup with JCI, Bosch, KPMG, and Infosys. | No
3 | 3 | QG0 - Programme kickoff approved | 1 day | 2026-07-01 | 2026-07-01 |  | KPMG PMO Lead + JCI Sponsor + Bosch Sponsor | Formal launch of the carve-out starting 2026-07-01. Users continue to work in the legacy JCI environment while Infosys builds the merger zone and the approved TSA extension remains available through 2027-07-31. | Yes
4 | 3 | Stand up PMO, governance cadence, and workstream RACI | 14 days | 2026-07-01 | 2026-07-15 | 3 | KPMG PMO Lead + KPMG Project Manager | Weekly governance, steering, RAID, and reporting in place. | No
5 | 3 | Onboard Infosys for merger zone delivery and managed services | 29 days | 2026-07-02 | 2026-07-31 | 3 | KPMG PMO Lead + Infosys Programme Manager | Delivery scope confirms merger zone setup, operations, and migration execution. | No
6 | 3 | Baseline TSA towers, service owners, and exit principles | 46 days | 2026-07-15 | 2026-08-30 | 4,5 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | JCI TSA catalogue, approved extension through 2027-07-31, and exit logic defined for all in-scope IT towers. | No
7 | 2 | 0.2 Separation compliance and stakeholder alignment | 82 days | 2026-07-11 | 2026-10-01 |  |  | Legal, privacy, communications, and regional alignment. | No
8 | 3 | Define legal perimeter, contracts, and supplier dependencies | 35 days | 2026-07-11 | 2026-08-15 | 4 | KPMG Project Manager + JCI Legal Counsel + Bosch Legal Counsel | Commercial and legal separation perimeter agreed. | No
9 | 3 | Assess privacy, works council, and cross-border data constraints | 50 days | 2026-07-21 | 2026-09-09 | 8 | KPMG Data Architect + JCI Legal Counsel | Regional data transfer and employee impact constraints captured. | No
10 | 3 | Launch site change network and stakeholder communications | 62 days | 2026-07-31 | 2026-10-01 | 6,9 | KPMG Change Lead + JCI HR Lead + Bosch HR Lead | Regional comms and escalation channels activated across 48 sites. | No
11 | 3 | QG1 - Concept and transition model approved | 1 day | 2026-10-01 | 2026-10-01 | 6,9,10 | KPMG PMO Lead + JCI Sponsor + Bosch Sponsor | Concept sign-off for JCI to merger zone to Bosch integration model. | Yes
12 | 1 | Phase 1: Discover landscape and design the merger zone | 121 days | 2026-10-02 | 2027-01-31 |  |  | Detailed discovery of applications, SAP, sites, data, and target merger zone design. | No
13 | 2 | 1.1 Application, SAP, and data discovery | 87 days | 2026-10-02 | 2026-12-28 |  |  | Discovery across more than 1,800 applications including major SAP scope. | No
14 | 3 | Catalogue 1,800-plus applications and assign transition disposition | 52 days | 2026-10-02 | 2026-11-23 | 11 | KPMG Enterprise Architect + JCI Application Owner + Infosys Application Lead | Classify applications by retain, migrate, replace, retire, and TSA dependency. | No
15 | 3 | Assess SAP landscape, interfaces, and shared services exposure | 62 days | 2026-10-02 | 2026-12-03 | 11 | KPMG SAP Architect + JCI SAP Owner + Infosys SAP Lead | Identify carve-out complexity across SAP systems, interfaces, and shared master data. | No
16 | 3 | Map dependencies and define migration waves for apps and data | 35 days | 2026-11-23 | 2026-12-28 | 14,15 | KPMG Enterprise Architect + Infosys Application Lead | Wave sequencing aligns critical apps, regional apps, and local edge cases. | No
17 | 2 | 1.2 Merger zone and target-state architecture | 112 days | 2026-10-02 | 2027-01-22 |  |  | Merger zone blueprint, security, connectivity, workplace, and Bosch end-state landing. | No
18 | 3 | Design merger zone hosting, network zones, and security blueprint | 57 days | 2026-10-02 | 2026-11-28 | 11 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Target blueprint for temporary merger zone with secure JCI and Bosch connectivity. | No
19 | 3 | Design identity, Active Directory trust, and privileged access model | 55 days | 2026-10-19 | 2026-12-13 | 18 | Infosys IAM Lead + KPMG Security Architect | Trust path and identity controls support JCI to merger zone to Bosch transition. | No
20 | 3 | Design workplace, M365, collaboration, and service management stack | 65 days | 2026-10-29 | 2027-01-02 | 18 | Infosys Cloud Lead + KPMG Workplace Lead | Email, M365, Teams, endpoint management, and service desk operating design complete. | No
21 | 3 | Design Bosch landing zone integration for post-merger-zone operations | 45 days | 2026-12-08 | 2027-01-22 | 18,19,20 | Bosch IT Manager + KPMG Infrastructure Architect + Infosys Programme Manager | Bosch target interfaces, identity landing, and support integration agreed. | No
22 | 2 | 1.3 TSA, migration, and site sequencing design | 94 days | 2026-10-29 | 2027-01-31 |  |  | TSA service tower design, migration controls, and regional sequencing. | No
23 | 3 | Define TSA service towers, KPIs, and operational reporting | 35 days | 2026-10-29 | 2026-12-03 | 6,11 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | Service lines and TSA metrics defined for transition governance with the approved seller-service buffer through 2027-07-31. | No
24 | 3 | Define exit criteria, acceptance tests, and service cutover checkpoints | 35 days | 2026-12-03 | 2027-01-07 | 23 | KPMG Project Manager + Bosch IT Manager | Each tower receives explicit readiness and exit conditions. | No
25 | 3 | Define data separation controls and reconciliation approach | 45 days | 2026-11-08 | 2026-12-23 | 14,15 | KPMG Data Architect + Infosys Data Migration Lead | Controls for business data separation, validation, and audit trail agreed. | No
26 | 3 | Sequence 48 sites and 12,000 users into migration waves | 40 days | 2026-12-08 | 2027-01-17 | 16,20 | KPMG Deployment Lead + Infosys Service Delivery Lead | Regional wave plan balances business criticality and support capacity. | No
27 | 3 | Design command center, cutover, and hypercare support model | 29 days | 2027-01-02 | 2027-01-31 | 24,26 | KPMG PMO Lead + Infosys Service Delivery Lead | Pre-GoLive command center and post-GoLive stabilization model defined. | No
28 | 1 | Phase 2: Build merger zone and prepare transition factory | 180 days | 2027-02-01 | 2027-07-31 |  |  | Build core platforms, prepare migration factory, and complete test readiness for QG2 and QG3. | No
29 | 2 | 2.1 Merger zone platform build | 125 days | 2027-02-01 | 2027-06-06 |  |  | Infrastructure, security, identity, workplace, and monitoring build. | No
30 | 3 | Provision merger zone hosting, compute, storage, and base services | 70 days | 2027-02-01 | 2027-04-12 | 18,21 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Core hosting platform established for temporary operational landing zone. | No
31 | 3 | Deploy network connectivity, segmentation, and core security controls | 100 days | 2027-02-26 | 2027-06-06 | 18,19 | Infosys Network Lead + Infosys Security Lead | Connectivity enables progressive site onboarding with required security segregation. | No
32 | 3 | Build identity federation, AD services, and privileged access tooling | 90 days | 2027-02-16 | 2027-05-17 | 19 | Infosys IAM Lead + KPMG Security Architect | Core identity services ready for user migration into the merger zone. | No
33 | 3 | Stand up M365 tenant, collaboration tools, and service desk platform | 85 days | 2027-03-03 | 2027-05-27 | 20,27 | Infosys Cloud Lead + Infosys Service Delivery Lead | Workplace and support stack prepared for all migrated users. | No
34 | 3 | Implement monitoring, backup, disaster recovery, and observability | 55 days | 2027-04-12 | 2027-06-06 | 30,31,33 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Operational readiness controls active before broad migration starts. | No
35 | 2 | 2.2 SAP and application transition factory | 180 days | 2027-02-01 | 2027-07-31 |  |  | SAP carve-out build plus app migration factory and tooling. | No
36 | 3 | Prepare SAP environments, copies, and carve-out configuration path | 85 days | 2027-03-03 | 2027-05-27 | 15,25,30 | Infosys SAP Lead + KPMG SAP Architect | SAP technical path into merger zone prepared and validated. | No
37 | 3 | Execute SAP separation build, role redesign, and interface rewiring | 40 days | 2027-05-27 | 2027-07-06 | 36 | Infosys SAP Lead + KPMG SAP Architect + JCI SAP Owner | Shared services, roles, and interfaces aligned to carved-out business scope. | No
38 | 3 | Build migration factory, tooling, and automation for application moves | 85 days | 2027-02-01 | 2027-04-27 | 16,25 | Infosys Application Lead + Infosys Data Migration Lead | Migration tooling covers data movement, validation, and evidence collection. | No
39 | 3 | Build and validate wave 1 critical applications in merger zone | 65 days | 2027-04-27 | 2027-07-01 | 30,38 | Infosys Application Lead + KPMG Enterprise Architect | Critical application stack prepared first for integrated testing. | No
40 | 3 | Pre-build wave 2 standard applications and package wave 3 edge apps | 75 days | 2027-05-12 | 2027-07-26 | 38 | Infosys Application Lead + KPMG Enterprise Architect | Standard and specialist applications prepared for accelerated migration execution. | No
41 | 2 | 2.3 Site and user migration readiness | 155 days | 2027-02-26 | 2027-07-31 |  |  | Endpoint readiness, local playbooks, and pilot readiness across 48 sites. | No
42 | 3 | Build device images, enrollment policies, and endpoint packaging | 80 days | 2027-02-26 | 2027-05-17 | 20,26 | Infosys Workplace Lead + KPMG Workplace Lead | Endpoint build supports phased user migration into merger zone services. | No
43 | 3 | Prepare regional migration playbooks, floorwalker model, and logistics | 65 days | 2027-04-27 | 2027-07-01 | 26,27,42 | KPMG Deployment Lead + Infosys Service Delivery Lead | Regional cutover packs and local support rosters ready. | No
44 | 3 | Run pilot site connectivity and service desk rehearsals | 55 days | 2027-06-06 | 2027-07-31 | 31,33,43 | Infosys Service Delivery Lead + JCI IT Manager | Pilot proves merger zone onboarding process and support flows before scaled migration. | No
45 | 2 | 2.4 Test planning and go-no-go preparation | 95 days | 2027-04-27 | 2027-07-31 |  |  | Formal test planning, mock rehearsals, and readiness evidence model. | No
46 | 3 | Build SIT and UAT plans, evidence templates, and sign-off workflow | 40 days | 2027-04-27 | 2027-06-06 | 27,33 | KPMG Test Lead + Infosys QA Lead | Common evidence and defect lifecycle agreed for all workstreams. | No
47 | 3 | Run SAP mock cutover rehearsal 1 and capture rollback evidence | 30 days | 2027-06-16 | 2027-07-16 | 37,46 | Infosys SAP Lead + KPMG SAP Architect | Initial mock validates timing, dependencies, and rollback controls. | No
48 | 3 | Complete operational readiness dossier for command center launch | 55 days | 2027-06-06 | 2027-07-31 | 34,44,46,47 | KPMG PMO Lead + Infosys Programme Manager | Evidence package prepared for test-ready milestone and steering review. | No
49 | 3 | QG2 and QG3 - Build complete and test entry approved | 1 day | 2027-07-31 | 2027-07-31 | 39,40,44,47,48 | KPMG PMO Lead + JCI Sponsor + Bosch Sponsor | Merger zone build complete and programme cleared for integrated testing and migration execution. | Yes
50 | 1 | Phase 3: Test, migrate to merger zone, and prepare Bosch landing | 131 days | 2027-08-01 | 2027-12-10 |  |  | Formal testing, migration waves, Bosch operational readiness, and QG4 entry. | No
51 | 2 | 3.1 Formal testing and defect closure | 104 days | 2027-08-01 | 2027-11-13 |  |  | Integrated testing, UAT, security, performance, DR, and regression closure. | No
52 | 3 | Execute end-to-end SIT across SAP, applications, and core services | 54 days | 2027-08-01 | 2027-09-24 | 49 | Infosys QA Lead + KPMG Test Lead + Infosys SAP Lead | Full end-to-end process flows validated inside the merger zone. | No
53 | 3 | Run performance, security, and disaster recovery validation | 60 days | 2027-08-15 | 2027-10-14 | 49,34 | Infosys Security Lead + Infosys Infrastructure Architect | Capacity, resilience, and control effectiveness validated for GoLive load. | No
54 | 3 | Run UAT with business teams across all regions and site groups | 55 days | 2027-09-04 | 2027-10-29 | 46,52 | KPMG Test Lead + JCI Business Lead + Bosch Business Lead | Business users validate SAP and non-SAP journeys needed at cutover. | No
55 | 3 | Close defects, run regression, and obtain UAT closure evidence | 40 days | 2027-10-04 | 2027-11-13 | 52,53,54 | Infosys QA Lead + KPMG Test Lead | Critical and high defects resolved before final readiness stage. | No
56 | 2 | 3.2 Migration waves into merger zone | 110 days | 2027-08-15 | 2027-12-03 |  |  | Users, applications, and data move from JCI to the merger zone after the approved TSA buffer period while overall programme progress and GoLive remain unchanged. | No
57 | 3 | Migrate user waves 1 and 2 with workplace and identity cutover | 60 days | 2027-08-15 | 2027-10-14 | 44,49 | Infosys Service Delivery Lead + Infosys Workplace Lead + JCI IT Manager | First half of the user base transitions from JCI to merger zone services. | No
58 | 3 | Migrate user waves 3 and 4 and complete 48-site onboarding | 50 days | 2027-10-14 | 2027-12-03 | 57,55 | Infosys Service Delivery Lead + Infosys Workplace Lead + JCI IT Manager | All 12,000 users operate from the merger zone before QG4. | No
59 | 3 | Execute wave 1 application and data migration into merger zone | 45 days | 2027-08-15 | 2027-09-29 | 39,52 | Infosys Application Lead + Infosys Data Migration Lead | Critical application and data moves completed with reconciliation. | No
60 | 3 | Execute wave 2 application and data migration into merger zone | 40 days | 2027-09-29 | 2027-11-08 | 40,59 | Infosys Application Lead + Infosys Data Migration Lead | Standard application estate transitioned and validated. | No
61 | 3 | Execute wave 3 specialist application completion and data closure | 25 days | 2027-11-08 | 2027-12-03 | 60,55 | Infosys Application Lead + Infosys Data Migration Lead | Specialist and regional edge applications completed before QG4. | No
62 | 2 | 3.3 Bosch landing and operating model readiness | 90 days | 2027-09-04 | 2027-12-03 |  |  | Bosch acceptance of connectivity, support processes, and eventual integration path. | No
63 | 3 | Enable Bosch connectivity, identity trust, and operational acceptance | 65 days | 2027-09-04 | 2027-11-08 | 21,32,33 | Bosch IT Manager + Infosys IAM Lead + Infosys Network Lead | Bosch confirms connectivity and identity patterns for downstream integration. | No
64 | 3 | Align resolver groups, service desk, and runbooks with Bosch operations | 45 days | 2027-10-14 | 2027-11-28 | 55,63 | Infosys Service Delivery Lead + Bosch IT Manager | Support ownership model agreed for post-GoLive stabilization and later handover. | No
65 | 3 | Run final SAP cutover rehearsal and certify rollback readiness | 35 days | 2027-10-29 | 2027-12-03 | 37,55 | Infosys SAP Lead + KPMG SAP Architect | Final rehearsal confirms cutover steps and fallback timing. | No
66 | 2 | 3.4 Pre-GoLive evidence pack | 9 days | 2027-12-01 | 2027-12-10 |  |  | Final evidence pack proving all migration and readiness activities are complete. | No
67 | 3 | Reconcile all migrations and archive formal UAT sign-off | 5 days | 2027-12-01 | 2027-12-06 | 58,61,55 | KPMG PMO Lead + Infosys Programme Manager | Users, applications, and data all reconciled before gate approval. | No
68 | 3 | Finalize infrastructure, SAP, and operational readiness dossier | 6 days | 2027-12-01 | 2027-12-07 | 53,64,65 | Infosys Programme Manager + KPMG PMO Lead | Operations, security, SAP, and service evidence complete for steering. | No
69 | 3 | Prepare steering gate deck and cutover recommendation | 4 days | 2027-12-06 | 2027-12-10 | 67,68 | KPMG PMO Lead + Bosch Sponsor + JCI Sponsor | Formal gate recommendation prepared for QG4 decision. | No
70 | 3 | QG4 - Pre-GoLive gate approved | 1 day | 2027-12-10 | 2027-12-10 | 69 | KPMG PMO Lead + JCI Sponsor + Bosch Sponsor | Pre-GoLive approval granted; final readiness and open-item closure begins. | Yes
71 | 1 | Phase 4: Final readiness and GoLive decision | 21 days | 2027-12-11 | 2028-01-01 |  |  | Mandatory buffer between QG4 and GoLive for closure, checks, rollback rehearsal, and sign-off. | No
72 | 2 | 4.1 Final readiness and open item closure | 20 days | 2027-12-11 | 2027-12-31 |  |  | No migrations remain; only closure, checks, sign-offs, and command center activation. | No
73 | 3 | Resolve residual defects, confirm health checks, and secure business sign-off | 20 days | 2027-12-11 | 2027-12-31 | 70 | KPMG Test Lead + Infosys Service Delivery Lead + Bosch Business Lead | All QG4 actions closed and no critical alerts remain before cutover. | No
74 | 3 | Activate cutover command center and issue final go decision | 2 days | 2027-12-29 | 2027-12-31 | 73 | KPMG PMO Lead + Infosys Programme Manager + JCI Sponsor + Bosch Sponsor | Rollback path revalidated and final go decision issued before GoLive day 1. | No
75 | 3 | GoLive - Day 1 cutover to merger zone complete | 1 day | 2028-01-01 | 2028-01-01 | 74 | KPMG PMO Lead + Infosys Programme Manager + JCI Sponsor + Bosch Sponsor | All in-scope users and services operate from the merger zone on GoLive. | Yes
76 | 1 | Phase 5: Hypercare, TSA exit, and Bosch handover | 90 days | 2028-01-02 | 2028-04-01 |  |  | Ninety-day stabilization only; no new development or migration after GoLive. | No
77 | 2 | 5.1 Hypercare stabilization only | 90 days | 2028-01-02 | 2028-04-01 |  |  | Support, hotfixes, enablement, and operational stabilization only. | No
78 | 3 | Run 24x7 incident triage and command center support | 90 days | 2028-01-02 | 2028-04-01 | 75 | Infosys Service Delivery Lead + KPMG Project Manager | Round-the-clock stabilization support across all regions. | No
79 | 3 | Operate hotfix-only release cadence and eliminate recurring problems | 60 days | 2028-01-02 | 2028-03-02 | 75 | Infosys Application Lead + Infosys SAP Lead | Bug fixes only after GoLive; no new features or migrations. | No
80 | 3 | Provide user enablement, local floorwalking, and adoption support | 40 days | 2028-01-02 | 2028-02-11 | 75 | KPMG Change Lead + Infosys Workplace Lead | Support users in the new merger zone operating model after cutover. | No
81 | 2 | 5.2 TSA exit and Bosch operations handover | 80 days | 2028-01-12 | 2028-04-01 |  |  | Tower-by-tower TSA exit followed by Bosch operational ownership uplift. | No
82 | 3 | Execute TSA exits by service tower and confirm acceptance | 60 days | 2028-01-12 | 2028-03-12 | 75 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | JCI TSA services closed according to approved exit criteria and acceptance tests. | No
83 | 3 | Transfer knowledge, runbooks, and service ownership to Bosch operations | 65 days | 2028-01-12 | 2028-03-17 | 75,64 | Bosch IT Manager + Infosys Programme Manager + KPMG Infrastructure Architect | Bosch operations absorb merger zone support knowledge and control model. | No
84 | 3 | Transition merger zone operating model to Bosch steady-state teams | 45 days | 2028-02-11 | 2028-03-27 | 82,83 | Bosch IT Manager + Infosys Programme Manager | Operational ownership transitions from project mode to Bosch steady-state teams. | No
85 | 2 | 5.3 Governance closure and archive | 30 days | 2028-03-02 | 2028-04-01 |  |  | Closure reporting, lessons learned, and artefact archive. | No
86 | 3 | Close financials, capture lessons learned, and archive artefacts | 25 days | 2028-03-02 | 2028-03-27 | 82,83 | KPMG PMO Lead + KPMG Project Manager | Programme closure outputs completed and repository artefacts archived. | No
87 | 3 | QG5 - Project completion approved | 1 day | 2028-04-01 | 2028-04-01 | 78,84,86 | KPMG PMO Lead + JCI Sponsor + Bosch Sponsor | Ninety-day hypercare complete, TSA exited, and handover to Bosch operations complete. | Yes