## Cost Plan
TRINITY-CAM ¦ IT CARVE-OUT COST PLAN ¦ Labour Resource Plan
Project | Trinity-CAM — JCI Aircon IT Carve-out
Seller | Johnson Controls International (JCI)
Buyer | Robert Bosch GmbH
Carve-out Model | Integration (JCI IT → Merger Zone → Bosch IT)
PMO Lead | KPMG
IT Delivery | Infosys (Merger Zone Build, Operation & Migration)
GoLive | 2028-01-01
Completion | 2028-04-01 (90-day hypercare complete)
Based on | Trinity-CAM_Project_Schedule.xlsx
Risk-aligned | Trinity-CAM_Risk_Register.xlsx (25 risks)
Status | DRAFT — to be approved at QG1
CATEGORY / RESOURCE | DESCRIPTION | TOTAL DAYS | TOTAL HRS | RATE (EUR/hr) | TOTAL COST (EUR)
KPMG — PMO & Programme Management
KPMG PMO Lead |  | 400 | 3200 | 250 | 800000
KPMG Project Manager |  | 380 | 3040 | 190 | 577600
Subtotal — KPMG — PMO & Programme Management |  | 780 |  |  | 1377600
KPMG — Architecture & Technical Advisory
KPMG Infrastructure Architect |  | 290 | 2320 | 200 | 464000
KPMG Data Architect |  | 180 | 1440 | 200 | 288000
Subtotal — KPMG — Architecture & Technical Advisory |  | 470 |  |  | 752000
KPMG — SAP Advisory
KPMG SAP Architect |  | 240 | 1920 | 225 | 432000
Subtotal — KPMG — SAP Advisory |  | 240 |  |  | 432000
Infosys — Programme Management
Infosys Programme Manager |  | 560 | 4480 | 185 | 828800
Subtotal — Infosys — Programme Management |  | 560 |  |  | 828800
Infosys — Infrastructure, Network & Security
Infosys Infrastructure Architect |  | 520 | 4160 | 150 | 624000
Infosys Network Lead |  | 320 | 2560 | 140 | 358400
Infosys Cloud Lead |  | 300 | 2400 | 145 | 348000
Infosys Security Lead |  | 260 | 2080 | 150 | 312000
Subtotal — Infosys — Infrastructure, Network & Security |  | 1400 |  |  | 1642400
Infosys — Identity & Access Management
Infosys IAM Lead |  | 280 | 2240 | 140 | 313600
Subtotal — Infosys — Identity & Access Management |  | 280 |  |  | 313600
Infosys — SAP Build & Configuration
Infosys SAP Architect |  | 480 | 3840 | 165 | 633600
Infosys SAP Lead |  | 420 | 3360 | 150 | 504000
Subtotal — Infosys — SAP Build & Configuration |  | 900 |  |  | 1137600
Infosys — Application Migration
Infosys Application Lead |  | 480 | 3840 | 135 | 518400
Subtotal — Infosys — Application Migration |  | 480 |  |  | 518400
Infosys — Data Migration
Infosys Data Migration Lead |  | 360 | 2880 | 140 | 403200
Subtotal — Infosys — Data Migration |  | 360 |  |  | 403200
Infosys — Service Delivery & Hypercare Support
Infosys Service Delivery Lead |  | 450 | 3600 | 130 | 468000
Subtotal — Infosys — Service Delivery & Hypercare Support |  | 450 |  |  | 468000
OVERALL PROJECT LABOUR TOTAL |  |  |  |  | 7873600
COST BREAKDOWN BY CATEGORY
KPMG — PMO & Programme Management | 17.5% of total | 780 |  |  | 1377600
KPMG — Architecture & Technical Advisory | 9.6% of total | 470 |  |  | 752000
KPMG — SAP Advisory | 5.5% of total | 240 |  |  | 432000
Infosys — Programme Management | 10.5% of total | 560 |  |  | 828800
Infosys — Infrastructure, Network & Security | 20.9% of total | 1400 |  |  | 1642400
Infosys — Identity & Access Management | 4.0% of total | 280 |  |  | 313600
Infosys — SAP Build & Configuration | 14.4% of total | 900 |  |  | 1137600
Infosys — Application Migration | 6.6% of total | 480 |  |  | 518400
Infosys — Data Migration | 5.1% of total | 360 |  |  | 403200
Infosys — Service Delivery & Hypercare Support | 5.9% of total | 450 |  |  | 468000
COST BREAKDOWN BY PHASE
Phase 0: Project Initiation | 2026-07-01 to 2026-10-01 | 5% |  |  | 393680
Phase 1: Discovery & Architecture | 2026-10-02 to 2027-01-31 | 15% |  |  | 1181040
Phase 2: Merger Zone Build | 2027-02-01 to 2027-07-31 | 35% |  |  | 2755760
Phase 3: Testing & Migration Waves | 2027-08-01 to 2027-11-30 | 30% |  |  | 2362080
Phase 4: Pre-GoLive Readiness | 2027-12-01 to 2028-01-01 | 5% |  |  | 393680
Phase 5: Hypercare & Closure | 2028-01-02 to 2028-04-01 | 10% |  |  | 787360
CAPEX & ADDITIONAL COSTS (excluded from labour total)
ITEM | ESTIMATED COST (EUR) | NOTES / RISK REFERENCE
Merger Zone DC / Cloud Infrastructure (Infosys-managed) | TBC - to be approved at QG1 | Risk Register R002; subject to cloud-vs-hardware decision at QG1
Software Licences — M365, ITSM, IAM, Security tooling (MZ) | TBC - to be approved at QG1 | Per-user licence cost for 12,000 users; to be validated at architecture sign-off
WAN/SD-WAN Network Connectivity — 48 Sites to MZ | TBC - to be approved at QG1 | Risk Register R012; ISP circuit costs per region; include APAC/LATAM premium
SAP SE Expert Services — System Copy & Client Separation | TBC - to be approved at QG1 | Risk Register R001; SAP SE engagement for complex 1,800+ app SAP copy
Risk Contingency Reserve — SAP Delay & MZ Build | TBC - to be approved at QG1 | Risk Register R001, R002, R003; recommended 15% of total labour as contingency
Cyber Insurance — Merger Zone & Data Migration Coverage | TBC - to be approved at QG1 | Risk Register R006, R016; Infosys cyber liability insurance for MZ operations
Independent Security Audit (GDPR / ISO 27001) | TBC - to be approved at QG1 | Risk Register R006; pre-Phase 3 independent security assessment
JCI IT Staff Retention Bonus Pool | TBC - to be agreed in SPA | Risk Register R017; retention incentives for key JCI SAP and IT roles through GoLive
Travel & Expenses — 48 Sites, Multi-region (CAPEX) | TBC - to be approved at QG1 | Site visits across EMEA, APAC, LATAM for migration waves; excluded from labour total
NOTES
1. Labour-only plan; CAPEX costs (infrastructure, licences, network, travel) listed separately above.
2. JCI and Bosch internal resource effort is tracked in the schedule but not costed here.
3. All EUR figures are indicative; subject to contract negotiation and QG1 budget board approval.
4. Infosys rates are blended by role; actual contract rates to be validated at SOW signature.
5. Standard billing day = 8 hours; standard working year = 220 days.
6. Risk contingency of 15% of total labour is recommended for Risk Register items R001, R002, R003.
7. Integration model (JCI > Merger Zone > Bosch) implies no Merger Zone tear-down post-GoLive; Infosys demobilisation schedule from GoLive +90 days.
8. Based on: Trinity-CAM_Project_Schedule.xlsx (118 tasks, 2026-07-01 to 2028-04-01).
9. Risk-aligned: Trinity-CAM_Risk_Register.xlsx (25 risks; top threat R001 SAP Complexity score=20).