## Schedule
ID | Outline Level | Name | Duration | Start | Finish | Predecessors | Resource Names | Notes | Milestone
1 | 1 | Phase 0: Project Initiation & Governance | 92 days | 2026-07-01 | 2026-10-01 |  |  | PMO mobilisation, governance, Infosys onboarding, legal, QG1 approval | No
2 | 2 | 0.1 Project Governance & PMO Setup | 46 days | 2026-07-01 | 2026-08-16 |  |  | KPMG PMO, steering, RACI, Infosys onboarding | No
3 | 3 | QG0 - Programme Kickoff & Mobilisation | 0 days | 2026-07-01 | 2026-07-01 |  | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | Programme officially started; all workstream leads mobilised; Infosys contractually engaged | Yes
4 | 3 | Establish KPMG PMO & Project Management Office | 14 days | 2026-07-01 | 2026-07-15 | 3 | KPMG PMO Lead + KPMG Project Manager | PMO governance tools active; reporting cadence; SharePoint site live | No
5 | 3 | Appoint Project Steering Committee (JCI + Bosch + KPMG) | 10 days | 2026-07-01 | 2026-07-11 | 3 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | Steering committee chartered; meeting calendar confirmed | No
6 | 3 | Define RACI & IT Workstream Structure | 14 days | 2026-07-12 | 2026-07-26 | 5 | KPMG Project Manager + KPMG PMO Lead | RACI approved; nine workstreams defined: Infrastructure, SAP, Applications, Identity, End-User Workplace, Data Migration, Security/GDPR, TSA Exit/HR/Legal, Programme Control | No
7 | 3 | Onboard Infosys as IT Delivery Partner (Merger Zone) | 45 days | 2026-07-02 | 2026-08-16 | 3 | KPMG PMO Lead + Infosys Programme Manager | Infosys Statement of Work executed; MZ scope confirmed; delivery team onsite | No
8 | 3 | Stakeholder Communication Plan (JCI / Bosch / Infosys / 48 Sites) | 14 days | 2026-07-16 | 2026-07-30 | 4 | KPMG Project Manager + KPMG PMO Lead | Comms plan approved; escalation path; change management approach | No
9 | 3 | Initial Risk & Issue Register Baseline | 21 days | 2026-07-23 | 2026-08-13 | 8 | KPMG Project Manager | Risk register v1.0 baselined; top 25 risks scored and owned (24 threats, 1 opportunity) | No
10 | 2 | 0.2 Legal & Regulatory Compliance Framework | 71 days | 2026-07-11 | 2026-09-20 |  |  | GDPR, legal entity separation, competition law | No
11 | 3 | GDPR & Data Privacy Assessment (12,000 Users - 48 Sites) | 46 days | 2026-07-11 | 2026-08-26 | 6 | KPMG Project Manager + JCI Legal Counsel | Privacy impact assessment; data residency; cross-border transfer rules | No
12 | 3 | Legal Entity Separation & Carve-out Structure | 46 days | 2026-07-11 | 2026-08-26 | 6 | KPMG Project Manager + JCI Legal Counsel + Bosch Legal Counsel | NewCo SPA; legal entity readiness; Integration model structures confirmed | No
13 | 3 | Regulatory & Competition Law Review (Multi-jurisdiction) | 46 days | 2026-07-31 | 2026-09-15 | 11 | KPMG Project Manager + JCI Legal Counsel | Multi-jurisdiction clearance tracking; antitrust filings; no blocking conditions | No
14 | 3 | QG1 - Concept Approval | 0 days | 2026-10-01 | 2026-10-01 | 9,13 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | Project concept approved; Infosys scope confirmed; proceed to Discovery & Architecture | Yes
15 | 1 | Phase 1: Discovery & Architecture Design | 122 days | 2026-10-01 | 2027-01-31 |  |  | App inventory 1800+, MZ architecture, TSA catalogue, data strategy | No
16 | 2 | 1.1 Application Landscape Assessment (1,800+ Applications) | 111 days | 2026-10-01 | 2027-01-20 |  |  | SAP analysis, non-SAP inventory, dependency mapping, wave planning | No
17 | 3 | SAP System Landscape Analysis (Full SAP Scope) | 45 days | 2026-10-01 | 2026-11-15 | 14 | KPMG SAP Architect + Infosys SAP Lead + JCI SAP Owner | SAP component list; modules in scope; interface inventory; carve-out complexity | No
18 | 3 | Non-SAP Application Inventory & Classification (1,800+ Apps) | 60 days | 2026-10-01 | 2026-11-30 | 14 | KPMG Data Architect + Infosys Application Lead + JCI IT Manager | Full app inventory; ownership; migration classification: Keep/Retire/Replace/Re-host | No
19 | 3 | Application Dependency Mapping & Interface Analysis | 35 days | 2026-11-15 | 2026-12-20 | 17 | KPMG Data Architect + Infosys Application Lead | Cross-app and SAP dependencies; integration interface inventory; circular deps flagged | No
20 | 3 | Application Migration Wave Planning (Waves 1-3) | 31 days | 2026-12-20 | 2027-01-20 | 18,19 | KPMG Data Architect + KPMG PMO Lead + Infosys Application Lead | Wave 1: ~400 critical apps; Wave 2: ~800 standard; Wave 3: ~600 local/specialist | No
21 | 2 | 1.2 Infrastructure & Network Assessment (48 Sites) | 77 days | 2026-10-01 | 2026-12-17 |  |  | JCI network, DC/cloud, segregation design, device estate | No
22 | 3 | JCI Network Architecture Review (48 Sites) | 30 days | 2026-10-01 | 2026-10-31 | 14 | KPMG Infrastructure Architect + Infosys Network Lead + JCI IT Manager | WAN, LAN, SD-WAN, firewall topology per site; bandwidth baseline | No
23 | 3 | Data Centre & Cloud Inventory (JCI Hosted Assets) | 31 days | 2026-10-01 | 2026-11-01 | 14 | KPMG Infrastructure Architect + JCI IT Manager | Primary & secondary DC; cloud workloads; contracts; hosting obligations | No
24 | 3 | Network Segregation Design (48 Sites to Merger Zone) | 46 days | 2026-11-01 | 2026-12-17 | 22,23 | KPMG Infrastructure Architect + Infosys Network Lead | Site-by-site network separation design; MZ connectivity model; SD-WAN approach | No
25 | 3 | End-User Device Estate Assessment (12,000 Users) | 45 days | 2026-10-01 | 2026-11-15 | 14 | KPMG Infrastructure Architect + JCI IT Manager | Device inventory by site; OS; age; refresh plan; Intune/SCCM readiness | No
26 | 2 | 1.3 Merger Zone Architecture Design (Infosys-led) | 84 days | 2026-10-01 | 2026-12-24 |  |  | MZ blueprint, AD design, core services architecture | No
27 | 3 | Merger Zone Infrastructure Blueprint (Infosys) | 61 days | 2026-10-01 | 2026-12-01 | 22,23 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | MZ DC/cloud topology; compute; storage; network zones; security perimeter | No
28 | 3 | Identity & Active Directory Design (Merger Zone) | 46 days | 2026-10-01 | 2026-11-16 | 25 | KPMG Infrastructure Architect + Infosys IAM Lead | MZ AD forest design; trust model with JCI and Bosch; federation approach | No
29 | 3 | Core Services Architecture (Email, M365, Collaboration, Security) | 61 days | 2026-10-24 | 2026-12-24 | 27 | KPMG Infrastructure Architect + Infosys Cloud Lead | MZ M365 tenant architecture; Teams; security tooling; ITSM platform selection | No
30 | 2 | 1.4 TSA Service Catalogue & Exit Plan | 92 days | 2026-10-01 | 2027-01-01 |  |  | JCI TSA services catalogued; SLA agreed; exit criteria defined | No
31 | 3 | TSA Service Definition & SLA Agreement per Service Line | 31 days | 2026-10-01 | 2026-11-01 | 14 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | All JCI services to continue under TSA catalogued; SLA and KPI per service line | No
32 | 3 | TSA Governance & Transition Reporting Framework | 30 days | 2026-11-01 | 2026-12-01 | 31 | KPMG Project Manager + JCI IT Manager | Monthly TSA service reports; escalation path; service exit trigger criteria | No
33 | 3 | TSA Exit Criteria per Service Line | 31 days | 2026-12-01 | 2027-01-01 | 32 | KPMG Project Manager + KPMG PMO Lead | Exit criteria defined per service; acceptance testing approach; sign-off process | No
34 | 2 | 1.5 Data Segregation & Migration Strategy | 101 days | 2026-10-01 | 2027-01-10 |  |  | Data classification, migration approach JCI > MZ > Bosch | No
35 | 3 | Data Classification & Ownership (JCI Aircon Business) | 46 days | 2026-10-01 | 2026-11-16 | 14 | KPMG Data Architect + JCI Data Owner + Bosch Data Owner | PII, IP, regulated data identified; data ownership matrix approved | No
36 | 3 | Data Migration Approach: JCI to Merger Zone to Bosch | 55 days | 2026-11-16 | 2027-01-10 | 35 | KPMG Data Architect + Infosys Data Migration Lead | Tooling selection; ETL methodology; data validation; SAP non-selective approach | No
37 | 2 | 1.6 HR & People Transition Planning | 92 days | 2026-10-01 | 2027-01-01 |  |  | 12,000-user mapping; multi-jurisdiction employment; comms plan | No
38 | 3 | Employee Mapping: JCI Aircon to Carve-out Entity (12,000 Users) | 45 days | 2026-10-01 | 2026-11-15 | 14 | KPMG Project Manager + JCI HR Director + Bosch HR Director | User list by site; role mapping; TUPE and transfer rules per jurisdiction | No
39 | 3 | People Communication Plan (Multi-region, 48 Sites) | 47 days | 2026-11-15 | 2027-01-01 | 38 | KPMG Project Manager + JCI HR Director | Phased comms per wave; change management; union consultation plans | No
40 | 1 | Phase 2: Merger Zone Build & Configuration (Infosys) | 180 days | 2027-02-01 | 2027-07-31 |  |  | MZ infrastructure build, IAM, core IT, SAP system copy, app wave 1 | No
41 | 2 | 2.1 Infrastructure Build - Merger Zone (Infosys) | 121 days | 2027-02-01 | 2027-06-02 |  |  | DC/cloud, network, security, backup/DR | No
42 | 3 | Merger Zone DC / Cloud Environment Setup (Infosys) | 60 days | 2027-02-01 | 2027-04-02 | 29,27 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Primary and secondary MZ hosting environments provisioned and validated | No
43 | 3 | Network Connectivity: All 48 Sites to Merger Zone (Infosys) | 91 days | 2027-03-03 | 2027-06-02 | 24 | Infosys Network Lead + KPMG Infrastructure Architect + JCI IT Manager | Site-by-site WAN/SD-WAN activation; phased rollout; all 48 sites connected to MZ | No
44 | 3 | Security Architecture & Firewall Implementation (Merger Zone) | 60 days | 2027-02-16 | 2027-04-17 | 29 | Infosys Security Lead + KPMG Infrastructure Architect | MZ perimeter security; DLP; endpoint protection; SOC integration; IDS/IPS | No
45 | 3 | Backup, Disaster Recovery & Business Continuity Setup | 45 days | 2027-04-02 | 2027-05-17 | 44 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | DR test plan; RPO/RTO targets defined and validated; backup cadence confirmed | No
46 | 2 | 2.2 Identity & Access Management (Merger Zone) | 90 days | 2027-02-01 | 2027-05-02 |  |  | AD forest, identity federation, PAM, MFA | No
47 | 3 | Active Directory Forest Setup (Merger Zone) | 43 days | 2027-02-01 | 2027-03-16 | 28 | Infosys IAM Lead + KPMG Infrastructure Architect | MZ AD forest live; OU structure; delegation model; trust relationships | No
48 | 3 | Identity Federation: JCI to Merger Zone (SSO) | 46 days | 2027-03-16 | 2027-05-01 | 47 | Infosys IAM Lead + KPMG Infrastructure Architect | Federation live; ADFS/Azure AD Connect; JCI users authenticate to MZ services | No
49 | 3 | Privileged Access Management (PAM) Setup | 30 days | 2027-03-17 | 2027-04-16 | 47 | Infosys Security Lead + KPMG Infrastructure Architect | PAM tooling deployed; all admin accounts vaulted; session recording active | No
50 | 3 | MFA & Security Policy Enforcement (12,000 Users) | 30 days | 2027-04-02 | 2027-05-02 | 49 | Infosys Security Lead + KPMG Infrastructure Architect | MFA enrolled for all 12,000 users; conditional access; security baselines enforced | No
51 | 2 | 2.3 Core IT Services Build (Merger Zone) | 121 days | 2027-02-01 | 2027-06-02 |  |  | Email/M365, SharePoint, Teams, ITSM service desk | No
52 | 3 | Email & M365 Tenant Setup (Merger Zone) | 60 days | 2027-02-01 | 2027-04-02 | 29 | Infosys Cloud Lead + KPMG Infrastructure Architect | MZ M365 tenant provisioned; mail flow validated; DNS prepared for cutover | No
53 | 3 | SharePoint & OneDrive Migration Tooling Setup | 45 days | 2027-04-02 | 2027-05-17 | 52,42 | Infosys Cloud Lead + KPMG Infrastructure Architect | Migration tooling configured and tested; user data migration pipeline validated | No
54 | 3 | Collaboration Tools: Teams & VOIP (Merger Zone) | 46 days | 2027-04-02 | 2027-05-18 | 52 | Infosys Cloud Lead + KPMG Infrastructure Architect | Teams provisioned; VOIP platform migrated; telephony operational for MZ users | No
55 | 3 | Service Desk & ITSM Tool Configuration (Infosys) | 61 days | 2027-03-03 | 2027-05-03 | 29 | Infosys Service Delivery Lead + KPMG Project Manager | ITSM platform live; service catalogue; SLA monitoring; L1/L2 support model | No
56 | 2 | 2.4 SAP Build & Configuration (Infosys SAP Team) | 180 days | 2027-02-01 | 2027-07-31 |  |  | SAP system copy, client sep, interface rewiring, security, data prep | No
57 | 3 | SAP System Copy: JCI to Merger Zone | 60 days | 2027-04-02 | 2027-06-01 | 20,42 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | Full SAP landscape replication into MZ environment; technical validation complete | No
58 | 3 | SAP Client Separation & Carve-out Configuration | 30 days | 2027-06-01 | 2027-07-01 | 57 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | Aircon business data separated; shared client access revoked; configuration validated | No
59 | 3 | SAP Interface Rewiring: JCI to Merger Zone Endpoints | 30 days | 2027-07-01 | 2027-07-31 | 58 | Infosys SAP Architect + KPMG SAP Architect | All outbound/inbound SAP interfaces rewired to MZ endpoints; EDI remapped | No
60 | 3 | SAP Security Role Redesign & Authorization Model | 30 days | 2027-06-01 | 2027-07-01 | 57 | Infosys SAP Architect + KPMG SAP Architect | Role matrix redesigned; SoD rules applied; SAP GRC configured for MZ | No
61 | 3 | SAP Data Migration Preparation (Technical Setup) | 75 days | 2027-02-01 | 2027-04-17 | 36 | Infosys Data Migration Lead + KPMG Data Architect | Migration tooling; data mapping; extraction rules; transformation logic; test datasets | No
62 | 2 | 2.5 Non-SAP Application Migration - Wave 1 (~400 Critical Apps) | 176 days | 2027-02-01 | 2027-07-27 |  |  | Prioritization, setup in MZ, data migration, smoke testing | No
63 | 3 | Wave 1 Application Prioritization & Scope Finalization | 30 days | 2027-02-01 | 2027-03-03 | 20 | KPMG Data Architect + Infosys Application Lead | Wave 1 app list frozen; business criticality confirmed; migration sequence defined | No
64 | 3 | Wave 1 Application Setup in Merger Zone | 46 days | 2027-04-02 | 2027-05-18 | 63,42 | Infosys Application Lead + KPMG Infrastructure Architect | All Wave 1 apps installed and configured in MZ; integration points validated | No
65 | 3 | Wave 1 Data Migration Execution | 45 days | 2027-05-18 | 2027-07-02 | 64 | Infosys Data Migration Lead + KPMG Data Architect | Data extracted from JCI; transformed; loaded into MZ; integrity checks passed | No
66 | 3 | Wave 1 Application Smoke Testing & Validation | 25 days | 2027-07-02 | 2027-07-27 | 65 | Infosys Application Lead + KPMG Infrastructure Architect + JCI IT Manager | Functional smoke tests passed; business owners sign-off Wave 1 app readiness | No
67 | 3 | QG2&3 - Build Complete & Test Ready | 0 days | 2027-07-31 | 2027-07-31 | 59,60,66 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | MZ infrastructure live; SAP interfaces rewired; Wave 1 apps validated; proceed to testing | Yes
68 | 1 | Phase 3: Testing & Migration Waves | 122 days | 2027-08-01 | 2027-12-01 |  |  | SIT, UAT, 12k user migrations, app waves 2-3, SAP cutover rehearsal | No
69 | 2 | 3.1 Systems Integration Testing | 62 days | 2027-08-01 | 2027-10-02 |  |  | E2E, performance, security pen test, DR test | No
70 | 3 | End-to-End Integration Test: SAP & Non-SAP (Wave 1) | 46 days | 2027-08-01 | 2027-09-16 | 67 | Infosys SAP Architect + KPMG SAP Architect + KPMG Infrastructure Architect | Full E2E flows across SAP, Wave 1 apps, MZ services; defects logged and resolved | No
71 | 3 | Performance & Load Testing (12,000 Concurrent Users) | 47 days | 2027-08-01 | 2027-09-17 | 67 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Peak load simulation; 12,000 concurrent users; MZ performance baselines met | No
72 | 3 | Security Penetration Testing (Merger Zone & Applications) | 30 days | 2027-08-25 | 2027-09-24 | 67 | Infosys Security Lead + KPMG Infrastructure Architect | External and internal pen test; critical findings remediated; security report signed | No
73 | 3 | Disaster Recovery Failover Test | 30 days | 2027-08-25 | 2027-09-24 | 45 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | Full DR failover executed; RTO/RPO targets validated; runbook confirmed | No
74 | 2 | 3.2 User Acceptance Testing (UAT) | 109 days | 2027-08-01 | 2027-11-18 |  |  | UAT planning, execution, defect resolution, sign-off | No
75 | 3 | UAT Planning & Test Case Design (All Workstreams) | 31 days | 2027-08-01 | 2027-09-01 | 67 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | Test scenarios per workstream; 48-site scope covered; business testers briefed | No
76 | 3 | UAT Execution: All User Groups (12,000 Users, Phased) | 46 days | 2027-09-01 | 2027-10-17 | 75,70 | KPMG Project Manager + Infosys Service Delivery Lead + JCI IT Manager | Phased UAT across all 48 sites; SAP transactions; Wave 1 apps; collaboration tools | No
77 | 3 | UAT Defect Triage & Resolution | 31 days | 2027-10-01 | 2027-11-01 | 76 | Infosys Application Lead + Infosys SAP Architect + KPMG Project Manager | All critical and high defects resolved; regression tested; defect log shows zero blocking | No
78 | 3 | UAT Sign-off by Business & IT Owners (All Sites) | 15 days | 2027-11-01 | 2027-11-16 | 77 | KPMG PMO Lead + JCI IT Manager + Bosch IT Manager | Formal UAT sign-off received; go-forward confirmation from all 48 sites | No
79 | 2 | 3.3 User Migration Waves (12,000 Users - 48 Sites) | 119 days | 2027-08-01 | 2027-11-28 |  |  | Four waves covering all 12,000 users across 48 sites - completed pre-QG4 | No
80 | 3 | User Migration Wave 1: Sites 1-12 (3,000 Users) | 32 days | 2027-08-16 | 2027-09-17 | 67 | Infosys Service Delivery Lead + KPMG Infrastructure Architect + JCI IT Manager | Wave 1 users migrated to MZ; devices enrolled; M365 mailboxes cut; service desk live | No
81 | 3 | User Migration Wave 2: Sites 13-24 (3,000 Users) | 31 days | 2027-09-17 | 2027-10-18 | 80 | Infosys Service Delivery Lead + KPMG Infrastructure Architect + JCI IT Manager | Wave 2 sites migrated; L1/L2 support cover maintained throughout window | No
82 | 3 | User Migration Wave 3: Sites 25-36 (3,000 Users) | 23 days | 2027-10-18 | 2027-11-10 | 81 | Infosys Service Delivery Lead + KPMG Infrastructure Architect + JCI IT Manager | Wave 3 complete; all APAC and EMEA tail sites on MZ services | No
83 | 3 | User Migration Wave 4: Sites 37-48 (3,000 Users) | 18 days | 2027-11-10 | 2027-11-28 | 82 | Infosys Service Delivery Lead + KPMG Infrastructure Architect + JCI IT Manager | All 12,000 users migrated to Merger Zone; JCI user access fully transitioned | No
84 | 2 | 3.4 Non-SAP Application Migration - Wave 2 (~800 Standard Apps) | 92 days | 2027-08-01 | 2027-11-01 |  |  | Wave 2 app migration and data migration - completed pre-QG4 | No
85 | 3 | Wave 2 Application Migration & Integration Testing | 46 days | 2027-08-01 | 2027-09-16 | 67 | Infosys Application Lead + KPMG Data Architect | Wave 2 apps migrated to MZ; integration tests passed; business sign-off | No
86 | 3 | Wave 2 Data Migration Execution | 46 days | 2027-09-16 | 2027-11-01 | 85 | Infosys Data Migration Lead + KPMG Data Architect | Wave 2 data extracted, transformed, loaded; integrity validated; reconciliation done | No
87 | 2 | 3.5 Non-SAP Application Migration - Wave 3 (~600 Specialist Apps) | 61 days | 2027-10-01 | 2027-12-01 |  |  | Wave 3 app and data migration - completed pre-QG4 | No
88 | 3 | Wave 3 Application Migration & Integration Testing | 46 days | 2027-10-01 | 2027-11-16 | 86 | Infosys Application Lead + KPMG Data Architect | Wave 3 specialist/regional apps migrated; integration validated; defects resolved | No
89 | 3 | Wave 3 Data Migration Execution | 29 days | 2027-11-01 | 2027-11-30 | 86 | Infosys Data Migration Lead + KPMG Data Architect | Wave 3 data migration complete; all 1,800+ app data in MZ; no outstanding items | No
90 | 2 | 3.6 SAP Production Cutover Planning & Rehearsal | 86 days | 2027-09-01 | 2027-11-26 |  |  | SAP cutover run book, two mock cutovers - completed pre-QG4 | No
91 | 3 | SAP GoLive Cutover Strategy & Run Book | 45 days | 2027-09-01 | 2027-10-16 | 61 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | Detailed run book; cutover sequence; rollback plan; timing and resources confirmed | No
92 | 3 | SAP Mock Cutover Exercise 1 (Full Dry Run) | 20 days | 2027-10-16 | 2027-11-05 | 91 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | Full dry run; timing measured; issues logged; rollback tested successfully | No
93 | 3 | SAP Mock Cutover Exercise 2 (Final Rehearsal) | 21 days | 2027-11-05 | 2027-11-26 | 92 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | Issues from Mock 1 corrected; cutover timing confirmed; go/no-go criteria met | No
94 | 1 | Phase 4: Pre-GoLive Readiness | 31 days | 2027-12-01 | 2028-01-01 |  |  | QG4 preparation, final readiness checks, GoLive cutover | No
95 | 2 | 4.1 QG4 Gate Preparation | 7 days | 2027-12-01 | 2027-12-08 |  |  | All migration verification, infrastructure and SAP readiness, rollback plan | No
96 | 3 | All Migration Waves Completed & Verified (Users + Apps + Data) | 6 days | 2027-12-01 | 2027-12-07 | 83,89,93,78 | KPMG PMO Lead + Infosys Programme Manager | 12,000 users migrated; all 1,800+ apps on MZ; all data reconciled; UAT signed off | No
97 | 3 | Infrastructure Readiness Sign-off (Infosys + KPMG) | 6 days | 2027-12-01 | 2027-12-07 | 73,50 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | MZ infrastructure fully operational; DR validated; security cleared; monitoring active | No
98 | 3 | SAP Production Readiness Confirmed | 6 days | 2027-12-01 | 2027-12-07 | 93 | Infosys SAP Architect + KPMG SAP Architect + JCI SAP Owner | SAP production environment validated; interfaces live; authorization model approved | No
99 | 3 | Cutover Rollback Plan Approved | 6 days | 2027-12-01 | 2027-12-07 | 91 | KPMG PMO Lead + Infosys Programme Manager | Rollback plan reviewed and approved by steering; go/no-go criteria documented | No
100 | 3 | QG4 - Pre-GoLive Gate Approval | 0 days | 2027-12-08 | 2027-12-08 | 96,97,98,99 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | All workstreams ready; QG4 approved; proceed to Final Readiness & GoLive preparation | Yes
101 | 2 | 4.2 Final Readiness & Open Item Closure | 21 days | 2027-12-09 | 2027-12-30 |  |  | Mandatory: UAT defects, infra checks, rollback test, steering sign-off | No
102 | 3 | All UAT Defects Resolved - QA Sign-off | 8 days | 2027-12-09 | 2027-12-17 | 100 | KPMG Project Manager + Infosys Service Delivery Lead | Zero blocking defects; QA formally signs off UAT closure; test evidence archived | No
103 | 3 | Final Infrastructure & Systems Health Checks (No Critical Alerts) | 12 days | 2027-12-09 | 2027-12-21 | 100 | Infosys Infrastructure Architect + KPMG Infrastructure Architect | All MZ components green; no open P1 tickets; capacity validated for GoLive load | No
104 | 3 | Cutover Rollback Test Executed (Production-like) | 10 days | 2027-12-10 | 2027-12-20 | 100 | Infosys SAP Architect + KPMG Project Manager | Full rollback test completed; rollback timing confirmed within window; approved | No
105 | 3 | Business & Steering Committee Sign-off (GoLive Authorisation) | 7 days | 2027-12-22 | 2027-12-29 | 102,103,104 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | Formal steering approval to proceed to GoLive; all action items closed; date confirmed | No
106 | 3 | GoLive - Merger Zone Day 1 Cutover (2028-01-01) | 0 days | 2028-01-01 | 2028-01-01 | 105 | KPMG PMO Lead + Infosys Programme Manager + JCI Programme Sponsor + Bosch Programme Sponsor | All 12,000 users live on Merger Zone; SAP production activated; 1,800+ apps operational; 24/7 support active | Yes
107 | 1 | Phase 5: Hypercare & Project Closure | 90 days | 2028-01-02 | 2028-04-01 |  |  | 90-day hypercare, Bosch integration handover, TSA exit, PMO closure | No
108 | 2 | 5.1 Hypercare Support (90 Days - Stabilisation Only) | 90 days | 2028-01-02 | 2028-04-01 |  |  | 24/7 L3 support, hotfixes, user enablement, Bosch knowledge transfer | No
109 | 3 | 24/7 L3 Support & Incident Triage (Infosys) | 90 days | 2028-01-02 | 2028-04-01 | 106 | Infosys Service Delivery Lead + KPMG Project Manager | Round-the-clock L3 support; P1/P2 hotline; daily ops standups all regions | No
110 | 3 | Hotfix Release Management (Critical Bug Fixes Only) | 60 days | 2028-01-02 | 2028-03-02 | 106 | Infosys Application Lead + Infosys SAP Architect | Bug fixes only; no new features; change freeze enforced; release cadence weekly | No
111 | 3 | User Enablement & Adoption Programs (12,000 Users) | 45 days | 2028-01-02 | 2028-02-16 | 106 | KPMG Project Manager + Infosys Service Delivery Lead + JCI IT Manager | Self-service guides; regional training; adoption dashboards; help desk KPIs tracked | No
112 | 3 | Knowledge Transfer to Bosch IT Operations | 60 days | 2028-01-16 | 2028-03-16 | 106 | KPMG Infrastructure Architect + Infosys Infrastructure Architect + Bosch IT Manager | Run books; architecture docs; SAP operational guides; ITSM transition to Bosch team | No
113 | 2 | 5.2 Bosch Integration Handover & Project Closure | 76 days | 2028-01-16 | 2028-04-01 |  |  | TSA exit, Bosch IT handover, documentation, lessons learned | No
114 | 3 | JCI TSA Service Exit Execution | 46 days | 2028-01-16 | 2028-03-02 | 106 | KPMG Project Manager + JCI IT Manager + Bosch IT Manager | JCI services formally exited per TSA exit criteria; acceptance tests passed; contracts closed | No
115 | 3 | Bosch IT Systems Integration Handover | 56 days | 2028-02-01 | 2028-03-28 | 112 | Infosys Programme Manager + KPMG Infrastructure Architect + Bosch IT Manager | MZ services formally handed to Bosch IT operations; Infosys role concluded; ITSM transferred | No
116 | 3 | Documentation & Runbook Finalization (All Workstreams) | 44 days | 2028-02-01 | 2028-03-16 | 112 | KPMG PMO Lead + Infosys Programme Manager | Architecture docs; SAP guides; operational runbooks; security playbooks; all archived | No
117 | 3 | Lessons Learned & PMO Closure Report (KPMG) | 31 days | 2028-03-01 | 2028-04-01 | 115,116 | KPMG PMO Lead + KPMG Project Manager | Lessons learned workshop; final PMO report; project artifacts archived; team debrief | No
118 | 3 | QG5 - Project Completion | 0 days | 2028-04-01 | 2028-04-01 | 109,117 | KPMG PMO Lead + JCI Programme Sponsor + Bosch Programme Sponsor | 90-day hypercare complete; JCI TSA fully exited; Bosch IT operations live; programme closed | Yes