## Info
Revision history
Document Id | TCM-RR-001
File Name | Trinity-CAM_Risk_Register.xlsx
Project Name | Trinity-CAM
Project Id | TCM-2026
Document Owner | KPMG PMO Lead
Review Date | Reviewers |  | Changes
About this template
Risk Category | Select from categories as defined by the Risk Management Plan.
Cause | Specifically what causes the risk to become a realized issue/problem
Effect | What happens if the trigger point occurs
Owner | Risk owner.
Creation date | Date risk identified.
Source | Source of risk.
Impact | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan
Probability | Probability of risk being realized, using scales defined in the Risk Management Plan.
Matrix Score | This is calculated once you select the Impact and Probability.
Qualitative Impact | Space for further description of potential impact.
Quantitative Impact | quantitative / potential risk cost
Risk response strategy | Select from strategies as defined by the Risk Management Plan.
Status | Risk status (e.g. whether it has been triggered or not). You will need to update the values list in cells
Notes | Additional notes.
Template Version | Issue Date | Author | Changes
1.0 | 2023-12-07 | S. Hoehnel | initial template based on V5.2 of the central risk register (S. Wohlfahrt); only examples provided on top

## Risk Register
Risk Register
Risk Identification | [8 empty] | Risk Analysis | [6 empty] | Risk Response Planning |  |  | Risk Monitoring and Control
risk ID | creation date | risk category | cause(s) | event | effect(s) | risk event date | owner | source | impact | prob- ability | threat / opportunity | matrix score | qualitative impact (including period of consideration) | monetary impact [EUR] current year | monetary impact [EUR] three subsequent years | risk response strategy | measure | due date | status | reporting date | impact actual | prob- ability actual | impact (actual) | probability (actual) | matrix score (actual) | notes
R001 | 04.04.2026 | Technology, R&D | JCI Aircon SAP landscape includes >1,800 applications with deep SAP integration; over 500 custom Z-programs identified; multiple country-specific payroll and financial configurations; SAP system copy from JCI to Merger Zone at this scale has not been performed previously within JCI; Infosys SAP team has limited JCI environment context at project start. | SAP system copy from JCI to Merger Zone takes longer than planned or fails initial technical validation; SAP client separation reveals unexpected shared data dependencies in Finance, HR, and Logistics modules requiring re-work; QG2&3 milestone (2027-07-31) at risk; SAP Mock Cutover 1 delayed past Oct 2027 target. | Phase 3 Integration Testing (Aug 2027) cannot start on schedule; SAP production readiness not confirmed by QG4 (2027-12-08); GoLive (2028-01-01) postponed; JCI business plan impact and extended MZ dual-run costs EUR 500K/month. | 2027-07-31 | KPMG SAP Architect | Formal Risk Review | Very High | 70% | threat |  | SAP build and system copy are on the critical path; any delay cascades to UAT, mock cutovers, and GoLive; business disruption and cost overrun risk is high. | 3000000 | 1500000 | Mitigate | Conduct SAP technical pre-assessment and Z-program inventory by 2026-11-01; engage SAP SE expert services for system copy support; plan 2 rehearsal copies before production copy; include 4-week buffer in SAP build schedule; weekly SAP progress KPI dashboard from Phase 2 start. | 2026-11-01 | not started | 04.04.2026 | Very High | 70% |  |  |  | Top Priority - on critical path to GoLive
R002 | 04.04.2026 | Technology, R&D | Infosys is the sole responsible vendor for Merger Zone DC/cloud setup, 48-site network connectivity, and IT service platform build; complex multi-cloud architecture across global regions; Infosys resource mobilisation at required scale (>50 FTE) in Phase 2 is subject to bench availability and competing Infosys engagements; no alternative MZ vendor is contractually identified. | Merger Zone DC environment not ready by 2027-02-01 target (Phase 2 start); network connectivity to key manufacturing and office sites delayed beyond Sep 2027; core IT services (AD, M365, ITSM) not available for Phase 3 user migration waves; QG2&3 gate (2027-07-31) fails. | Phase 3 testing cannot start; user migration waves delayed; SAP system copy blocked by absence of MZ target environment; programme milestone slip of 3-6 months; extended Infosys contract cost and JCI TSA extension costs. | 2027-07-31 | Infosys Programme Manager | Formal Risk Review | High | 50% | threat |  | Single-vendor dependency on Infosys for MZ delivery creates a critical programme risk; escalation path and contractual remedies must be defined pre-Phase 2. | 2000000 | 500000 | Mitigate | Establish weekly Infosys delivery KPI dashboard from Phase 2 start; link milestone payments to MZ DC readiness by 2027-02-28; identify fallback cloud hosting (Azure/AWS) option approved by QG1 (2026-10-01); KPMG infrastructure architect embedded in Infosys weekly build review. | 2026-10-01 | not started | 04.04.2026 | High | 50% |  |  |  | Contractual remedies to be agreed by QG1
R003 | 04.04.2026 | Schedule | SAP Mock Cutover 1 planned end Oct 2027; Mock Cutover 2 planned end Nov 2027 (target 2027-11-21); QG4 gate is 2027-12-08; recovery window between Mock 2 end and QG4 is only 17 calendar days; any critical SAP cutover defects found in Mock 2 (GL posting failures, interface errors, data load timing overruns) require immediate resolution within this window. | Critical SAP cutover defects discovered in Mock 2 cannot be fully resolved by QG4 (2027-12-08); QG4 gate deferred; GoLive postponed beyond 2028-01-01; JCI TSA contractually expired; no JCI IT support coverage available; Aircon business runs without stable IT systems for extended period. | GoLive delay of 4-8 weeks; extended MZ dual-run costs EUR 500K/month; JCI TSA emergency extension required at premium rate; business operations disrupted; Bosch integration timeline delayed; board-level escalation. | 2027-12-08 | KPMG PMO Lead | Formal Risk Review | Very High | 50% | threat |  | 17-day recovery window between Mock 2 and QG4 is insufficient for complex SAP cutover defects; pre-defining escalation and rollback criteria is essential. | 3000000 | 1000000 | Mitigate | Conduct Mock Cutover 1 with strict issue timer: all P1 issues resolved within 5 days; pre-define QG4 go/no-go criteria (zero P1, less than 5 P2 SAP defects); negotiate JCI TSA emergency extension clause (30 days) in SPA; identify GoLive postponement date no later than 2028-02-01 as fallback; reserve post-Mock-2 defect sprint team (Infosys SAP lead x3). | 2027-09-01 | not started | 04.04.2026 | Very High | 50% |  |  |  | TSA extension clause must be in SPA signed before deals close
R004 | 04.04.2026 | Resources | Infosys delivery model relies on named SAP Architects, Infrastructure Leads, and Data Migration Leads; high M&A market demand for Infosys SAP and cloud talent; 18-month engagement creates staff rotation and attrition risk; Infosys HR model rotates staff every 12-15 months; no contractual named-resource commitment at project start. | Key Infosys SAP Architect or MZ Infrastructure Lead rotates off project during Phase 2 (Feb-Jul 2027) or Phase 3 (Aug-Dec 2027); replacement requires 6-8 week onboarding; critical knowledge of JCI SAP environment and MZ configuration is lost; SAP build and MZ integration timeline impacted by 4-6 weeks. | QG2&3 gate delayed; SAP integration testing quality reduced; defect rates in Phase 3 increase; programme PMO must escalate to Infosys leadership; additional cost for accelerated onboarding. | 2027-07-31 | KPMG PMO Lead | Formal Risk Review | High | 50% | threat |  | Resource continuity on 18-month complex programme is a standard delivery risk; mitigation must be built into Infosys contractual terms. | 500000 | 0 | Mitigate | Contract Infosys for named resource commitment with 90-day minimum notice and replacement approval by KPMG; require living knowledge base (Confluence/SharePoint) updated weekly by each Infosys workstream lead; designate KPMG shadow for each Infosys lead role; conduct mid-project (Phase 2 end) resource continuity review. | 2026-08-01 | not started | 04.04.2026 | High | 50% |  |  |  | Named-resource clause to be in Infosys SOW
R005 | 04.04.2026 | Legal & Compliance | 12,000 JCI Aircon employees in 48 jurisdictions are subject to differing TUPE and transfer of undertaking legislation; Germany and France require 30-90 day employee consultation periods before IT system changes affecting roles; China requires local labour authority notification; some APAC jurisdictions have data localisation laws affecting how user data is migrated. | Employment law non-compliance in key jurisdictions deletes user migration schedule for Wave 1 or Wave 2 sites; injunctions or regulatory actions in Germany or France block planned migration execution in Aug-Sep 2027; affected 3,000+ users cannot be migrated to Merger Zone until legal clearance obtained. | User migration wave schedule disrupted; 3,000+ users cannot access MZ services on schedule; customer-facing systems at risk of outage; GoLive (2028-01-01) with partial user base; compliance fines and legal costs EUR 1-3M. | 2027-08-15 | JCI Legal Counsel | Formal Risk Review | Very High | 30% | threat |  | Multi-jurisdiction employment law is a high-impact risk for a 12,000-user carve-out across 48 sites; must be addressed in Phase 1 before migration planning is finalised. | 1500000 | 500000 | Avoid | Engage local legal counsel in top 10 user-count jurisdictions by QG1 (2026-10-01); map TUPE triggers per country against wave migration schedule; integrate legal clearance gates into wave migration plan; begin works council/union consultation in Germany, France, Netherlands by 2026-11-01; obtain KPMG legal sign-off on migration schedule before Phase 3 start. | 2026-10-01 | not started | 04.04.2026 | Very High | 30% |  |  |  | German works council consultation is on critical path for Wave 1
R006 | 04.04.2026 | Security & Data Protection | 12,000 users personal data (PII) and Aircon business IP are migrating across JCI infrastructure to Infosys-managed Merger Zone across 18 months; data-in-transit security depends on end-to-end encryption and DLP controls not all implemented at Phase 2 start; Infosys holds privileged elevated access to both JCI and MZ environments during dual-run period; 48 cross-border data flows. | Unauthorized access or data exfiltration event during migration window; GDPR breach notification required within 72 hours of discovery to DPA; regulatory fines up to EUR 20M or 4% of global turnover; EU regulator may impose processing stop affecting all EU user migrations; reputational damage affecting deal valuation. | Deal at risk if data breach during carve-out triggers regulatory investigation; migration halted for EU 15+ sites; remediation cost EUR 5-20M; 3-6 month programme pause while security audit completed. | 2028-01-01 | Infosys Security Lead | Formal Risk Review | Very High | 30% | threat |  | GDPR breach during a high-profile cross-border M&A migration would attract maximum regulatory scrutiny; risk must be managed through architectural controls and insurance. | 5000000 | 2000000 | Transfer | Mandate ISO 27001 certification for MZ environment before Phase 3; require Infosys cyber liability insurance covering data breach during migration; implement CASB and DLP on all migration data flows from Phase 2 start; conduct penetration test before Phase 3 (target Aug 2027); appoint independent GDPR Data Protection Officer; encrypt all data at rest and in transit; DPA notification procedure rehearsed before GoLive. | 2027-02-01 | not started | 04.04.2026 | Very High | 30% |  |  |  | Infosys cyber liability insurance must be in place before Phase 2
R007 | 04.04.2026 | Technology, R&D | 1,800+ applications built for JCI domain, Active Directory, and on-premise hosting; Wave 2 (~800 apps) and Wave 3 (~600 apps) include legacy, custom-coded, and third-party applications; re-pointing to Merger Zone AD, M365, and ITSM requires application-by-application compatibility testing; some apps require code changes for MZ compatibility; legacy apps may have no vendor support. | Wave 2 and Wave 3 applications show higher-than-forecast incompatibilities with MZ environment during Phase 3 (Aug-Dec 2027); remediation backlog grows beyond capacity; Wave 2 and Wave 3 migrations slip past QG4 deadline (2027-12-08); GoLive proceeds with incomplete application estate; user productivity impacted. | 12,000 users have degraded productivity post-GoLive due to missing applications; business operations partially dependent on JCI systems post-GoLive requiring emergency TSA extension; cost of application remediation over budget. | 2027-11-30 | Infosys Application Lead | Formal Risk Review | High | 50% | threat |  | 1,800+ app migration carries inherent compatibility risk; Wave 2/3 are the highest-risk waves due to legacy and specialist applications. | 2000000 | 500000 | Mitigate | Complete application compatibility pre-assessment for top 250 apps by QG1; build 15% schedule buffer into Wave 2 and Wave 3 plans; establish 3-tier remediation: quick-config (target 2 days), re-configure (target 2 weeks), retire/replace (plan in Phase 1); Wave 1 dry run to validate MZ compatibility approach before Wave 2 starts. | 2026-10-01 | not started | 04.04.2026 | High | 50% |  |  |  | App pre-assessment results must feed into Wave 2/3 schedule at QG1
R008 | 04.04.2026 | Budget | Infosys MZ delivery contract may have underestimated scope; 48-site connectivity, 1,800+ app migration, and SAP system copy at this scale carry high uncertainty; scope creep from Bosch IT change requests or JCI data quality issues could inflate MZ contract value; change control process not yet established at project start. | Infosys raises change requests in Phase 2/3 totalling more than 15% of contracted MZ delivery cost; steering board approval for additional spend takes 4-6 weeks; Infosys slows delivery pending approval; Phase 2/3 delivery impacted; total programme budget overrun. | Programme cost overrun of EUR 3-5M; Bosch procurement approval required; Phase 2/3 delivery paused during approval process; schedule impact of 4-6 weeks per unresolved change request. | 2027-06-30 | Bosch Programme Sponsor | Formal Risk Review | High | 50% | threat |  | Fixed-price IT delivery contracts at this scale frequently experience cost overrun; proactive change control governance is the primary mitigation. | 3000000 | 0 | Mitigate | Establish change control board (KPMG + Bosch + Infosys) with 10-business-day SLA on all change requests; ring-fence 15% budget contingency for MZ changes; conduct QG1 scope validation with Infosys before full contract signature; monthly spend-to-plan dashboard reviewed by steering from Phase 2 start. | 2026-10-01 | not started | 04.04.2026 | High | 50% |  |  |  | Change control board charter to be agreed with Infosys at QG1
R009 | 04.04.2026 | Schedule | 12,000 users across 4 migration waves covering 48 sites must complete by QG4 (2027-12-08); Wave 3 (Sites 25-36) and Wave 4 (Sites 37-48) include challenging APAC sites (China, India) and LATAM sites (Mexico, Brazil) with ISP lead times of 8-16 weeks; local IT field support availability at tail sites is limited; network circuit delivery is on the critical path for Wave 3/4 start. | Wave 3 (target Aug-Oct 2027) or Wave 4 (target Oct-Nov 2027) delayed by network circuit failures or local IT resource unavailability; 3,000+ users for those waves not migrated by QG4 (2027-12-08); GoLive scope incomplete; JCI emergency TSA extension required. | GoLive with partial user migration; business disruption for unmigrated users; TSA emergency extension cost EUR 200-500K/month; programme steering board escalation; GoLive scope exception needed. | 2027-12-08 | Infosys Service Delivery Lead | Status Meeting | Moderate | 50% | threat |  | APAC and LATAM network circuits are on the critical path for Wave 3/4; early ISP engagement is the key mitigation action. | 500000 | 0 | Mitigate | Pre-qualify ISPs at APAC and LATAM sites during Phase 1 (Oct 2026); issue ISP purchase orders for long-lead APAC sites before Phase 2 start; contract local IT field support at tail sites by 2027-03-01; build 2-week buffer between Wave 4 end target and QG4; define GoLive-with-exceptions policy for fewer than 50 residual users. | 2026-10-01 | not started | 04.04.2026 | Moderate | 50% |  |  |  | ISP RFQs for APAC sites must be issued in Phase 1 discovery phase
R010 | 04.04.2026 | Quality | JCI SAP system has 20+ years of accumulated data with known quality issues: duplicate vendor master records, inactive cost center allocations, unmapped GL accounts from legacy acquisitions, and inconsistent material master data across countries; non-selective SAP copy approach will migrate dirty data to Merger Zone; data clean-up requires active JCI business team cooperation during Phase 1 and 2. | SAP data migration dry runs (Phase 2/3, Apr-Aug 2027) reveal significant data quality failures in financial and logistics data; business validation team rejects migration output; additional data cleansing sprints of 6-8 weeks required; SAP Mock Cutover 1 and 2 delayed; QG4 target (2027-12-08) at risk. | SAP production readiness cannot be confirmed by QG4; GoLive delayed; post-GoLive financial reporting accuracy at risk; statutory reporting in key countries (Germany, US) delayed; audit qualification risk. | 2027-10-31 | JCI SAP Owner | Formal Risk Review | High | 50% | threat |  | SAP data quality is a known risk in all JCI-scale separations; early data assessment and business engagement is essential. | 1000000 | 500000 | Mitigate | Commission SAP data quality pre-assessment by Phase 1 end (2027-01-31); establish JCI-led data cleansing sprint Oct-Dec 2026 with weekly KPMG review; define data acceptance criteria per module before SAP copy in Phase 2; KPMG data architect validates all extraction outputs; reject-and-retry mechanism built into SAP copy run book. | 2026-11-01 | not started | 04.04.2026 | High | 50% |  |  |  | JCI finance team engagement critical for data quality sign-off
R011 | 04.04.2026 | Stakeholder Relations & Public Affairs | JCI is divesting the Aircon business; after deal financial close, JCI has reduced commercial incentive to prioritize IT carve-out support; JCI IT staff assigned to the programme may be affected by JCI corporate restructuring or redundancy programmes post-deal; JCI programme sponsor focus may shift to other JCI business units. | JCI IT cooperation declines in Phase 2 (Feb 2027) or Phase 3 (Aug 2027); access to JCI production SAP system for copy and monitoring is restricted; JCI data quality clean-up tasks de-prioritized; Infosys blocked from progressing without JCI system credentials and context; KPMG PMO cannot enforce deliverables. | SAP system copy blocked; application inventory gaps discovered late; Wave 1 user migration delayed; overall programme milestone slip of 4-8 weeks; KPMG must escalate to JCI board level. | 2027-06-30 | Bosch Programme Sponsor | Formal Risk Review | High | 30% | threat |  | JCI co-operation is a mandatory dependency for all six workstreams; contractual obligations and financial incentives are the primary mitigations. | 1500000 | 0 | Mitigate | Embed JCI IT cooperation obligations with named deliverable commitments in SPA and TSA before financial close; KPMG PMO tracks JCI deliverable completion weekly with RAG status; escalate to joint steering if JCI deliverable SLA breached; negotiate JCI IT retention bonus linked to programme milestones (QG1, QG2, GoLive); KPMG shadow of key JCI roles from Phase 1 for knowledge capture. | 2026-08-01 | not started | 04.04.2026 | High | 30% |  |  |  | JCI deliverable obligations must be contractually binding in SPA
R012 | 04.04.2026 | Technology, R&D | 48 sites in multiple regions require SD-WAN/WAN connectivity to Merger Zone; ISP lead times: China 12-16 weeks, LATAM (Mexico, Brazil) 8-12 weeks, Eastern Europe 8-10 weeks, Middle East 6-8 weeks; Infosys network team starts formal procurement in Phase 2 (Feb 2027) which may be too late for APAC circuits needed for Wave 3 (Aug 2027). | Network circuits for 8-12 APAC and LATAM sites not activated by Phase 3 user migration start (Aug 2027); 2,000+ users at affected sites cannot be migrated to Merger Zone; wave schedule disrupted; GoLive with sites still on JCI network. | User migration Waves 3/4 scope reduced; JCI TSA extension required for unmigrated sites; GoLive with partial estate; ongoing cost of maintaining split IT environment between JCI and MZ. | 2027-08-01 | Infosys Network Lead | Formal Risk Review | High | 30% | threat |  | Network connectivity is on the critical path for all user migration waves; APAC and LATAM ISP lead times require pre-Phase 2 procurement actions. | 500000 | 200000 | Mitigate | Initiate ISP RFQs for all APAC and LATAM sites during Phase 1 (Oct-Dec 2026) before official Phase 2 start; identify China-specific ISP immediately; evaluate SD-WAN overlay as interim connectivity for tail sites during ISP delay; network circuit delivery tracked in weekly MZ build dashboard; all APAC POs issued by 2026-12-01. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | China ISP selection is on critical path - start in Phase 1
R013 | 04.04.2026 | Legal & Compliance | Merger Zone potentially hosted in data centres outside country of origin for JCI Aircon data; 12,000 users across 48 countries include EU (GDPR, Schrems II), China (PIPL, data localisation law), and US (state privacy laws); Aircon product IP and R&D data may have export control restrictions (ITAR/EAR) under US law; MZ architecture design in Phase 1 must address these requirements. | Data sovereignty analysis in Phase 1 (Oct-Dec 2026) reveals MZ hosting design is non-compliant for China (PIPL requires local data storage) or EU users (Schrems II invalidation of data transfers); Infosys MZ architecture requires redesign to add regional nodes; Phase 2 start delayed 4-8 weeks; additional MZ hosting cost EUR 1-2M. | Phase 2 delayed; MZ architecture change impacts SAP copy timing; overall programme schedule pushed 6-8 weeks; regulatory sanctions if data sovereignty non-compliance proceeds to production. | 2027-02-01 | JCI Legal Counsel | Formal Risk Review | High | 30% | threat |  | Data sovereignty is a prerequisite for MZ architecture; must be resolved in Phase 1 before Infosys finalises MZ blueprint. | 1000000 | 300000 | Avoid | Conduct comprehensive data sovereignty assessment in Phase 1 (target 2026-11-01); require Infosys MZ blueprint to include China-local and EU-local hosting nodes; engage Chinese legal counsel for PIPL compliance before MZ design finalised; review US export control (ITAR/EAR) applicability for Aircon IP data flows; MZ architecture approved by KPMG legal and privacy team before QG1. | 2026-11-01 | not started | 04.04.2026 | High | 30% |  |  |  | China PIPL assessment is priority - must inform MZ blueprint
R014 | 04.04.2026 | Schedule | QG4 gate (2027-12-08) requires zero blocking defects across all workstreams: SAP production readiness, 12,000 user migration completion, 1,800+ app Wave 2/3 completion, network connectivity all 48 sites, infrastructure readiness, and DR test passed; six workstreams must all achieve green status simultaneously in a 6-day pre-gate check window; any late-breaking critical defect causes gate failure. | QG4 gate assessment fails on 2027-12-08 due to open P1/P2 defects in SAP, network connectivity gaps at tail sites, or user migration Wave 4 incomplete; gate deferred to 2028-01-15; GoLive pushed from 2028-01-01 to 2028-02-01; JCI business plan Aircon separation delayed. | GoLive delayed 4-6 weeks; Bosch acquisition integration delayed; MZ extended operational cost EUR 500K/month; JCI TSA extension at premium; board-level visibility required. | 2027-12-08 | KPMG PMO Lead | Formal Risk Review | Very High | 30% | threat |  | QG4 is the single gate controlling GoLive; all six workstreams must achieve simultaneous green status; rolling defect management from Phase 3 is critical. | 3000000 | 1000000 | Mitigate | Implement rolling defect triage from UAT week 1 (Aug 2027); track defect burn-down daily from Oct 2027; pre-define QG4 go/no-go criteria explicitly: zero P1 defects, fewer than 5 P2 defects, all Wave 2/3 apps live, all 48 sites network-connected, 12,000 users migrated; hold bi-weekly QG4 readiness review from 2027-09-01; reserve 30-day GoLive buffer (max GoLive 2028-02-01) with steering approval. | 2027-09-01 | not started | 04.04.2026 | Very High | 30% |  |  |  | QG4 go/no-go criteria must be approved by steering before Phase 3 start
R015 | 04.04.2026 | Budget | Merger Zone is a transient environment running operational costs including Infosys management fees, cloud hosting, software licences, and support; MZ operational burn rate estimated EUR 400-600K/month during Phase 2/3/4 dual-run period; any schedule delay directly extends dual-run costs; exact MZ annual budget not yet approved beyond Phase 2 start. | Programme schedule slips 3+ months due to SAP, network, or QG4 issues; MZ dual-run operational spend increases by EUR 1.2-1.8M per 3-month delay; Bosch budget authority required for additional spend; steering board escalation required; project month-end close delayed. | Budget overrun of EUR 1.5-3M impacting Bosch acquisition business case; procurement escalation process delays delivery further; Bosch CFO visibility required. | 2027-12-31 | Bosch Programme Sponsor | Formal Risk Review | High | 30% | threat |  | MZ dual-run costs compound with any schedule delay; schedule adherence is the most cost-effective risk control. | 1500000 | 0 | Mitigate | Pre-approve 3-month MZ extension budget contingency at QG1 board decision; review schedule risk and MZ cost exposure monthly from Phase 2; phase-down MZ non-essential services within 30 days of GoLive; Infosys contract includes demobilisation schedule triggered by GoLive confirmation. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | 3-month extension budget approval to be included in QG1 financial decision
R016 | 04.04.2026 | Security & Data Protection | Merger Zone is a new, complex IT environment operated by Infosys with privileged access to JCI production systems during dual-run; Phase 2 build period (Feb-Jul 2027) is highest risk window as security controls are not fully hardened; Aircon business is a high-value target: 12,000 user credentials, SAP financial data, product IP, and M&A transaction details are accessible via MZ infrastructure; Infosys supply chain access increases attack surface. | Ransomware attack targets Merger Zone infrastructure in Phase 2/3; SAP data or app migration data encrypted; DR test environment must be activated under incident conditions; SAP build timeline set back 4-8 weeks; personal data of 12,000 users potentially exfiltrated; GDPR breach notification triggered. | Programme delay of 4-8 weeks; SAP data re-extraction required; GDPR breach notification to DPA with potential EUR 20M fine; reputational damage to JCI, Bosch, and Infosys; cyber incident response cost EUR 2-5M. | 2027-07-31 | Infosys Security Lead | Formal Risk Review | Very High | 10% | threat |  | Low probability but very high impact; zero-trust and immutable backup architecture are essential pre-conditions for MZ build. | 5000000 | 0 | Transfer | Implement zero-trust network architecture in MZ from Phase 2 start (Feb 2027); mandatory 24/7 SOC monitoring by Infosys security team; cyber insurance covering MZ environment and data breach response; immutable backup strategy for all SAP data with air-gapped copy; penetration test of MZ before any JCI production data migrated; incident response playbook rehearsed before Phase 3. | 2027-02-01 | not started | 04.04.2026 | Very High | 10% |  |  |  | Infosys cyber insurance must be confirmed with KPMG before Phase 2 start
R017 | 04.04.2026 | Resources | JCI Aircon IT staff (SAP Basis team, network architects, application owners) are aware of carve-out and potential redundancy; JCI has limited financial incentive to retain staff beyond deal close; key individuals (JCI SAP Basis lead, JCI IT Manager) carry critical tacit knowledge of JCI systems configuration, SAP authorizations, and network topology across 48 sites. | Key JCI SAP Basis lead departs during Phase 2 (Feb-Jul 2027); SAP system access credentials and environment knowledge unavailable; Infosys and KPMG cannot proceed SAP copy without JCI Basis team; SAP build timeline extends 4-6 weeks while JCI provides a replacement. | SAP copy and interface rewiring delayed; QG2&3 gate at risk; KPMG PMO must escalate to JCI board to force resource replacement; programme cost of delay EUR 500K. | 2027-06-30 | JCI Programme Sponsor | Status Meeting | High | 30% | threat |  | JCI key staff retention is a standard risk in distressed-seller carve-outs; retention financial incentives and knowledge documentation are key controls. | 500000 | 0 | Mitigate | Negotiate JCI IT staff retention bonus pool covering SAP Basis, Network Architect, and IT Manager roles through GoLive (2028-01-01); KPMG shadow programme for all key JCI roles from Oct 2026; document JCI IT system access procedures and credentials in secure KPMG vault; contingency plan for each key JCI role identified and approved by QG1. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | JCI retention terms to be in SPA before deal financial close
R018 | 04.04.2026 | Manufacturing | JCI Aircon business operates manufacturing facilities for air conditioning equipment; OT/SCADA/MES systems at these facilities are integrated with JCI IT applications and SAP (production orders, quality management); OT systems have long revalidation timelines (6-12 months post-change) and regulatory certification requirements; OT environments not yet included in the 1,800 app inventory at project start. | Wave 3 specialist applications (target Oct-Nov 2027) include OT/SCADA-connected systems not compatible with Merger Zone without factory revalidation; factory revalidation timelines push Wave 3 completion past QG4 (2027-12-08); manufacturing continuity risk during OT-IT separation window. | Wave 3 OT applications not migrated by GoLive; factories dependent on split IT/OT environment post-GoLive; risk of production disruption; regulatory certification gap in manufacturing quality systems; GoLive exception required with OT remediation plan. | 2027-11-30 | JCI IT Manager | Formal Risk Review | High | 30% | threat |  | OT/SCADA systems are often forgotten in IT carve-outs until too late; early identification and separate migration track are essential. | 1000000 | 500000 | Mitigate | Identify all OT-connected applications in Phase 1 app inventory by 2026-11-01; commission OT-IT separation technical assessment by KPMG/Infosys by 2027-01-31; plan OT systems on a separate migration track with factory approval gates; engage Bosch OT team (as future owner) in MZ architecture design from Phase 1; Wave 3 OT migrations scheduled before QG4 with 4-week factory validation buffer. | 2026-11-01 | not started | 04.04.2026 | High | 30% |  |  |  | OT inventory must be completed in Phase 1 app assessment by Nov 2026
R019 | 04.04.2026 | Quality | Merger Zone is an Infosys-designed environment; performance benchmarks are based on architecture estimates and comparable projects; actual 12,000-user concurrent load during performance testing (Phase 3, Aug-Sep 2027) may reveal bottlenecks in MZ compute, storage, or SAP application server capacity; Infosys contracts performance SLAs but may not have designed for peak M&A workloads across 48 sites. | Performance test results in Aug-Sep 2027 show MZ cannot sustain 12,000 concurrent users at required response times (target <3 sec for SAP transactions); infrastructure scaling requires additional hardware procurement of 6-8 weeks; retest required; Phase 3 schedule impacted; QG4 at risk. | Phase 3 bottleneck resolves after hardware remediation but consumes the QG4 buffer; performance defects carry into QG4 check; Infosys remediation cost EUR 500K+ not budgeted. | 2027-09-30 | Infosys Infrastructure Architect | Formal Risk Review | High | 30% | threat |  | Performance issues discovered late in Phase 3 are expensive and schedule-critical; contractual SLAs and early incremental testing are key controls. | 500000 | 0 | Mitigate | Define performance SLAs contractually with Infosys pre-Phase 2 (Feb 2027): SAP response time <3 sec for standard transactions at 12,000 users; conduct incremental load testing starting at 2,000, then 6,000, then 12,000 users; Infosys obligated to remediate performance failures within 4-week SLA at no cost; performance test plan approved by KPMG architect before testing starts. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | Performance SLAs must be in Infosys contract before Phase 2
R020 | 04.04.2026 | Strategy & Portfolio | Post-GoLive integration of MZ services into Bosch IT is an Integration model deliverable not fully scoped at project start; Bosch IT may request additional data migrations, system integrations, architecture changes, or Bosch-standard tooling that was not anticipated in the original carve-out scope; Bosch IT organisation is not a primary stakeholder during Phase 2/3 build. | Bosch IT requests significant MZ re-architecture or additional integration deliverables during hypercare (Jan-Apr 2028) not covered in programme scope; Infosys and KPMG scope extensions not budgeted; QG5 closure gate (2028-04-01) delayed; programme extends beyond planned completion. | Programme continues past QG5 date; post-GoLive integration costs not budgeted; Infosys contract extension required; KPMG engagement extended; Bosch IT leadership alignment required. | 2028-04-01 | Bosch Programme Sponsor | Status Meeting | Moderate | 30% | threat |  | Scope creep in the integration phase is common in Integration-model carve-outs; defining a clear handover boundary is essential. | 1000000 | 0 | Avoid | Define Bosch IT integration scope in transition agreement by QG1; scope freeze: all Bosch post-GoLive integration work requiring new delivery against separate Bosch IT budget from Day 91 of hypercare; hypercare scope strictly limited to stabilisation and hotfixes (no new features); run off-programme strategy session with Bosch IT in Phase 1 to identify integration requirements and budget accordingly. | 2026-10-01 | not started | 04.04.2026 | Moderate | 30% |  |  |  | Bosch integration scope definition must be tabled at QG1
R021 | 04.04.2026 | Supply Chain | MZ infrastructure requires significant server, storage, and network hardware; global hardware supply chain disruptions and semiconductor shortages create 16-20 week procurement lead times; Infosys formal hardware procurement starting Phase 2 (Feb 2027) may be too late for some long-lead components needed for MZ DC readiness by Apr 2027. | Critical MZ hardware (compute servers, storage arrays, network switches) not delivered by MZ DC setup target (2027-04-02); Infosys cannot complete MZ environment build on schedule; SAP system copy start delayed from Jun 2027; QG2&3 gate (2027-07-31) at risk. | Phase 2 milestone delayed 4-8 weeks; SAP build and app setup on MZ deferred; cascade to Phase 3 start delay; programme milestone slip of 2-3 months. | 2027-04-15 | Infosys Infrastructure Architect | Formal Risk Review | High | 30% | threat |  | Hardware procurement timelines are fixed by market conditions; early procurement decision before Phase 2 is the only reliable mitigation. | 300000 | 0 | Mitigate | Trigger hardware procurement decisions at QG1 (2026-10-01) with Bosch budget approval; issue Infosys POs for all long-lead hardware items by 2026-11-01; evaluate and prefer Azure/AWS cloud-first (IaaS) MZ design to eliminate physical hardware dependency; Infosys hardware tracker reviewed weekly from QG1 with KPMG oversight. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | Hardware or cloud decision at QG1 is a critical scheduling dependency
R022 | 04.04.2026 | Customers | JCI Aircon serves external customers (building contractors, HVAC systems buyers, field service engineers) through customer portals, order management, and field service applications that are included in the 1,800+ app scope; these customer-facing applications are mission-critical and must maintain 24/7 uptime during migration; Wave 1 includes most critical customer-facing apps. | Customer-facing Wave 1 applications (order portal, service portal, dealer portal) experience outages or degraded performance during migration cutover window (Phase 2/3, May-Oct 2027); Aircon customers unable to place orders or access service management; SLA breach for field service contracts; customer NPS impact. | Aircon revenue loss estimated EUR 500K-2M per week of customer portal outage; field service SLA penalties; customer attrition; reputational damage during M&A transition period; contractual penalty clauses triggered. | 2027-08-31 | JCI IT Manager | Formal Risk Review | High | 30% | threat |  | Customer-facing systems require zero-downtime migration planning; standard wave approach must be enhanced for customer portal stack. | 1500000 | 500000 | Mitigate | Flag all customer-facing applications in Phase 1 app inventory by 2026-11-01; require zero-downtime migration plan (blue-green deployment) for top 10 customer-critical apps; conduct extended parallel-run of 2 weeks for customer portals before DNS cut; test customer portals with 500-user pilot before general cutover; customer impact communication plan approved by JCI commercial team before Wave 1. | 2026-11-01 | not started | 04.04.2026 | High | 30% |  |  |  | Zero-downtime requirement must be flagged to Infosys app team before Wave 1 design
R023 | 04.04.2026 | Intellectual Property | JCI Aircon has proprietary HVAC designs, patents, and product roadmap data managed in PLM (Product Lifecycle Management) and document management systems integrated with JCI corporate infrastructure; post-deal IP ownership transfers to Bosch but JCI may retain inadvertent read-access if segregation is incomplete; PLM system not yet confirmed as in Wave 1 scope. | IP segregation in PLM and document management systems incomplete at GoLive (2028-01-01); JCI retains read-access to Bosch-owned Aircon IP in shared systems post-deal; Bosch legal discovers gap during integration audit; or conversely, Aircon employees unable to access product designs in MZ causing engineering disruption. | Intellectual property dispute between JCI and Bosch post-deal; legal remediation cost EUR 500K+; product development continuity interrupted for engineering teams; potential deal impairment if IP ownership is contested. | 2028-01-01 | JCI Legal Counsel | Formal Risk Review | High | 30% | threat |  | IP segregation is a legal obligation for clean carve-out; PLM and document management must be explicitly included in scope. | 500000 | 200000 | Avoid | Include PLM and all document management systems in Wave 1 migration scope by QG1; conduct IP segregation audit jointly by JCI and Bosch legal teams by 2027-01-31; JCI read-access to Aircon IP systems revoked within 30 days post-GoLive; Bosch IP counsel signs off IP segregation completeness at QG4; independent IP audit report commissioned before GoLive. | 2026-10-01 | not started | 04.04.2026 | High | 30% |  |  |  | PLM scope confirmation required in Phase 1 app inventory
R024 | 04.04.2026 | Ecosystems & Ethics | Infosys may use subcontractors in low-cost regions for MZ infrastructure build and data migration components; subcontractors may have access to sensitive JCI Aircon SAP production data, 12,000 user credentials, and M&A transaction details; ethical data handling standards and background screening requirements may not match Bosch Supplier Code of Conduct; subcontractor list not disclosed at project start. | Infosys subcontractor mishandles sensitive Aircon IP or SAP credentials; information security incident traced to subcontractor access; Bosch and JCI contractual data protection obligations breached; regulatory investigation triggered; deal completion risk if breach is material. | Infosys primary contract liability but reputational risk for Bosch; regulatory investigation cost EUR 1-3M; potential programme pause pending security audit; Bosch board-level disclosure required. | 2027-12-31 | KPMG PMO Lead | Formal Risk Review | High | 10% | threat |  | Subcontractor supply chain risk is increasingly scrutinised by regulators; contractual and audit controls on Infosys supply chain are essential. | 1000000 | 0 | Transfer | Require Infosys to disclose full subcontractor list before Phase 2 start; subcontractor vetting per Bosch Supplier Code of Conduct enforced by Infosys; data processing agreements (DPA) signed with all subcontractors handling personal data or SAP credentials; KPMG audit rights over Infosys supply chain contractually secured; annual subcontractor compliance review built into governance calendar. | 2026-10-01 | not started | 04.04.2026 | High | 10% |  |  |  | Subcontractor disclosure is a pre-condition to Infosys contract signature
R025 | 04.04.2026 | Technology, R&D | MZ infrastructure build provides an architectural fresh start free from JCI technical debt; Infosys has strong Azure and AWS expertise; migrating 1,800+ JCI on-premise applications and SAP to MZ creates a unique opportunity to architect for cloud-native from the outset rather than replicating the JCI on-premise model in MZ. | Structured cloud migration review during Phase 1 architecture identifies 300-400 JCI on-premise workloads suitable for Azure/AWS cloud-native design within MZ; cloud MZ reduces hardware procurement risk; Bosch ultimately inherits a modern cloud estate rather than on-premise MZ. | Cloud-native MZ reduces long-term Bosch operational cost by EUR 3-5M/year post-integration; eliminates hardware procurement lead-time risk; accelerates Bosch cloud strategy; positions Aircon business as cloud-ready at GoLive. | 2027-02-01 | Infosys Cloud Lead | Formal Risk Review | High | 50% | opportunity |  | Cloud-first MZ design is a strategic opportunity to modernise the Aircon IT estate at zero additional effort cost during the mandatory migration programme. | 0 | 5000000 | Exploit | Mandate cloud suitability flag in Phase 1 application inventory; Infosys cloud architect to design MZ with Azure-first architecture from QG1; present cloud ROI business case at QG1 for Bosch steering approval; pilot cloud MZ with Wave 1 non-SAP apps; target 300+ apps on cloud-native by GoLive; decommission physical MZ hardware within 6 months post-GoLive. | 2026-10-01 | not started | 04.04.2026 | High | 50% |  |  |  | Cloud-first decision must be made at QG1 to influence MZ hardware procurement
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
Insert Rows Above This Line Only
Warning: Be careful adding/removing rows in the following section - these values are used for data validation
Risk Category
Technology, R&D
Engineering
Manufacturing
Quality
Strategy & Portfolio
Budget
Schedule
Resources
Supply Chain
Market & Competitors
Customers
Raw Materials
Stakeholder Relations & Public Affairs
Intellectual Property
Legal & Compliance
Ecosystems & Ethics
Security & Data Protection
Risk Source
Formal Risk Review
SQA Audit/Review
Status Meeting
Stakeholder
Other
Impact Values
|  | Very Low | 0.05
|  | Low | 0.1
|  | Moderate | 0.2
|  | High | 0.4
|  | Very High | 0.8
Probability Values
|  | 10% | 0.1
|  | 30% | 0.3
|  | 50% | 0.5
|  | 70% | 0.7
|  | 90% | 0.9
Green/Yellow/Red Threshold Values
|  | Green - maximum score | 0.05
|  | Yellow - minimum score | 0.06
|  | Yellow - maximum score | 0.14
|  | Red - minimum score | 0.15
Risk Strategy
Avoid
Transfer
Mitigate
Accept
Exploit
Enhance
Share
Status
not started
in progress
on hold
implemented
cancelled
Note on E4: Which issues could lead to the risk event?
Note on F4: When exactly does a threat become a problem repectively an opportunity become an occasion?
Note on G4: What would be the consequences?
Note on H4: If the risk event can be linked to an exact or latest date.

## Matrix
Risk Register | [14 empty] | Matrix (initial) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS | [52 empty] | Matrix (actual) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS
Probability & Impact Matrix (initial)
Probability |  | Threats |  |  |  |  | Opportunities | [9 empty] | Green/Yellow/Red Threshold Values | [52 empty] | Green/Yellow/Red Threshold Values
| 0.9 | [16 empty] | Green - maximum score |  |  | 0.05 | [49 empty] | Green - maximum score |  |  | 0.05
| 0.7 | [16 empty] | Yellow - minimum score |  |  | 0.06 | [49 empty] | Yellow - minimum score |  |  | 0.06
| 0.5 | [16 empty] | Yellow - maximum score |  |  | 0.14 | [49 empty] | Yellow - maximum score |  |  | 0.14
| 0.3 | [16 empty] | Red - minimum score |  |  | 0.15 | [49 empty] | Red - minimum score |  |  | 0.15
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
Impact
Probability & Impact Matrix (actual)
Probability |  | Threats |  |  |  |  | Opportunities
0.9
0.7
0.5
0.3
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
|  | Impact | [15 empty] | P-I # threat | [24 empty] | P-I # opportunity | [27 empty] | P-I # threat | [24 empty] | P-I # opportunity
[18 empty] | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 |  |  |  | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5
|  | Risk ID | Risk Category |  | Matrix Score | Threat / Opportunity | quantitative impact [€] | risk strategy | owner | reporting date | status | Cause | Effect | Matrix Score (actual) | Impact | Probability | [51 empty] | Impact (actual) | Probability (actual)
END OF MATRIX DATA (max 130 records)
Impact Values
| Very Low | 0.05
| Low | 0.1
| Moderate | 0.2
| High | 0.4
| Very High | 0.8
Probability Values
| Very Low | 0.1
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very High | 0.9
Green/Yellow/Red Threshold Values
| Green - maximum score | 0.05
| Yellow - minimum score | 0.06
| Yellow - maximum score | 0.14
| Red - minimum score | 0.15