## Slide 1: Project Trinity-CAM
Management Stakeholder Presentation
JCI Aircondition Carve-Out into Robert Bosch GmbH
Integration Model | Report Date: 05 Apr 2026

## Slide 2: Executive Summary
Trinity-CAM — Programme Status Overview | Integration Model
Programme formally commenced 1 Jul 2026. KPMG PMO mobilised. Infosys SOW signed.
Scope: 48 sites, 12,000 users, 1,800+ applications including major SAP landscape.
Integration Model: JCI IT assets migrate to Infosys-operated Merger Zone, then Bosch IT.
Overall RAG: AMBER. SPI 1.00 / CPI 1.00 at QG0 baseline. No schedule or cost overrun.
Key risk R001 (SAP landscape complexity, score 20) requires response plan by Aug 2026 SteerCo.
GoLive target confirmed: 1 January 2028. JCI TSA expired 30 Jun 2026 — no extension.
GoLive
1 Jan 2028
Overall RAG
AMBER
Top Risk
Score 20 (SAP)

## Slide 3: Scope & Integration Model
What is in scope and the two-hop migration path
Migration path: JCI IT (source) → Merger Zone, Infosys-operated (transient) → Bosch IT (target).
In scope: 12,000 users, all devices, M365 tenant, 1,800+ applications, full SAP landscape.
Infrastructure: New Merger Zone DC/cloud (Infosys build); SD-WAN to 48 global sites.
SAP: Full system copy JCI → MZ; client separation; 2 mock cutovers before GoLive.
3 application migration waves + dedicated SAP track; GDPR-compliant 48-jurisdiction data transfers.
Out of scope: Bosch standard platform harmonisation; SAP feature changes; hardware refresh.
Sites
48 Global
Users
12,000
Applications
1,800+

## Slide 4: Programme Timeline & Quality Gates
Jul 2026 — Apr 2028 | 6 gates | Integration model milestone plan
QG0
1 Jul 26
QG1
1 Oct 26
QG2&3
31 Jul 27
QG4
8 Dec 27
GoLive
1 Jan 28
QG5
1 Apr 28
Ph1 Initiation
Ph2 MZ Build
Ph3 Test & Migrate
Ph4 Final Ready
Ph5 Hypercare
QG0 Jul 2026: PMO + Infosys mobilised. Initiation phase kickoff.
QG1 Oct 2026: Concept approved. App inventory, MZ arch, CAPEX budget signed off.
QG2&3 Jul 2027: Merger Zone DC live. SAP copy done. Wave 1 (~400 apps) validated.
QG4 Dec 2027: All 12,000 users + 1,800+ apps on MZ. SAP Mock 2 passed. UAT signed.
GoLive Jan 2028: Day 1 cutover. MZ live. TSA dependencies fully exited. Hypercare active.
QG5 Apr 2028: 90-day hypercare complete. Bosch IT handover. Programme closed.
GoLive
1 Jan 2028
Duration
21 months
Gates
QG0-QG5

## Slide 5: Workstream Status & Readiness
9 workstreams across KPMG and Infosys delivery
GREEN: Programme Control (KPMG PMO), End-User Workplace, Identity & Access, Data Migration.
AMBER: MZ Infrastructure (MZ arch pending QG1), SAP Migration (R001 response in progress).
AMBER: Application Migration (1,800+ inventory 85% complete), Security & GDPR (DPIAs in progress).
AMBER: TSA Exit & HR/Legal (TUPE works council notifications filed in DE; FR Aug 2026).
Overall readiness: 12% (Initiation phase). Target 100% at QG4 (8 Dec 2027).
No RED workstreams at programme baseline. Monitoring R001 SAP and R006 GDPR.
GREEN WS
4/9
AMBER WS
5/9
RED WS
0/9

## Slide 6: Budget Overview
Labour cost plan | CAPEX TBC at QG1
Total Labour Budget: EUR 7,873,600 (KPMG + Infosys). Contingency +15%: EUR 9,054,640.
CAPEX (MZ infrastructure, M365 licences, 48-site SD-WAN): TBC at QG1 — Infosys to submit.
KPMG share (PMO + Architecture + SAP Advisory): EUR 2,562,400 (32.5% of labour).
Infosys share (PM, Infra, IAM, SAP, Apps, Data, Service): EUR 5,311,200 (67.5% of labour).
Phase 2 MZ Build: EUR 2.76M (35% of total) — largest programme phase by cost.
CPI 1.00 at QG0 baseline. No variance to date. Budget release gate: QG1 approval.
Labour Total
EUR 7.87M
Contingency
EUR 1.18M
CAPEX
TBC QG1

## Slide 7: Top Risks & Mitigations
From Trinity-CAM Risk Register — 25 risks (24 threats, 1 opportunity)
R001 SAP Complexity (score 20 — HIGH): System copy delay risk. Response plan tabled Aug 2026 SteerCo.
R003 SAP Mock Cutover 2 timing (score 15 — HIGH): Mock 1 (Jul 2027) validates remediation window.
R002 Infosys MZ delivery delay (score 12): Cloud fallback option being assessed; procurement at QG1.
R006 GDPR breach exposure (score 10): DPIA active across 48 jurisdictions; legal counsel engaged.
R005 TUPE non-compliance DE/FR (score 10): Works council Germany notified; France EWC Aug 2026.
R025 OPPTY: MZ cloud modernisation (score 12): EUR 3-5M/yr Bosch OPEX saving; Infosys cloud lead.
High risks
2 (R001, R003)
Med risks
22 open
Opportunity
1 (R025)

## Slide 8: Management Decisions Required
Actions required from Bosch Steering Committee and JCI
DECISION 1: Approve QG1 CAPEX envelope (MZ infrastructure, M365, SD-WAN) — target vote Oct 2026.
DECISION 2: Formally adopt Infosys cloud fallback option into MZ architecture (risk R002 mitigation).
DECISION 3: Confirm Bosch-side IT integration scope and resources to be ready post-GoLive (Jan 2028).
DECISION 4: Mandate JCI senior IT cooperation SLA for application inventory and data quality.
DECISION 5: Approve August 2026 SteerCo date to review R001 SAP risk response plan.
DECISION 6: Confirm GoLive date 1 Jan 2028 as hard business deadline — no further flex.
Decisions open
6
Next SteerCo
Aug 2026
GoLive confirm
1 Jan 2028