## Cost Plan
Trinity-CAM (GPT) ¦ IT CARVE-OUT COST PLAN
Project | Trinity-CAM (GPT)
Seller | Johnson Controls International (JCI)
Buyer | Bosch
Business | Air conditioning business
Carve-out Model | Integration - JCI IT to merger zone to Bosch IT
Based on | Trinity-CAM (GPT)_Project_Schedule.xlsx
Risk-aligned | Trinity-CAM (GPT)_Risk_Register.xlsx
Budget Baseline | TBC - to be approved at QG1
Note | Bosch and JCI internal resource lines are tracked at zero rate for schedule traceability and excluded from the billable labour baseline.
CATEGORY | RESOURCE | TOTAL DAYS | TOTAL HRS | HOURLY RATE (EUR) | TOTAL COST (EUR)
Bosch Internal Support - Tracked Only
Bosch Internal Support - Tracked Only | Bosch Business Lead | 75 | 600 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch HR Lead | 62 | 496 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch IT Manager | 441 | 3528 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch Legal Counsel | 35 | 280 | 0 | 0
Bosch Internal Support - Tracked Only | Bosch Sponsor | 12 | 96 | 0 | 0
Subtotal - Bosch Internal Support - Tracked Only |  | 625 |  |  | 0
Infosys - Application and Data Delivery
Infosys - Application and Data Delivery | Infosys Application Lead | 482 | 3856 | 120 | 462720
Infosys - Application and Data Delivery | Infosys Data Migration Lead | 240 | 1920 | 125 | 240000
Infosys - Application and Data Delivery | Infosys QA Lead | 134 | 1072 | 110 | 117920
Subtotal - Infosys - Application and Data Delivery |  | 856 |  |  | 820640
Infosys - Platform, Security, and Workplace
Infosys - Platform, Security, and Workplace | Infosys Cloud Lead | 150 | 1200 | 130 | 156000
Infosys - Platform, Security, and Workplace | Infosys IAM Lead | 210 | 1680 | 125 | 210000
Infosys - Platform, Security, and Workplace | Infosys Infrastructure Architect | 242 | 1936 | 130 | 251680
Infosys - Platform, Security, and Workplace | Infosys Network Lead | 165 | 1320 | 120 | 158400
Infosys - Platform, Security, and Workplace | Infosys Security Lead | 160 | 1280 | 130 | 166400
Infosys - Platform, Security, and Workplace | Infosys Workplace Lead | 230 | 1840 | 115 | 211600
Subtotal - Infosys - Platform, Security, and Workplace |  | 1157 |  |  | 1154080
Infosys - Programme and Service Delivery
Infosys - Programme and Service Delivery | Infosys Programme Manager | 253 | 2024 | 145 | 293480
Infosys - Programme and Service Delivery | Infosys Service Delivery Lead | 539 | 4312 | 125 | 539000
Subtotal - Infosys - Programme and Service Delivery |  | 792 |  |  | 832480
Infosys - SAP Delivery
Infosys - SAP Delivery | Infosys SAP Lead | 366 | 2928 | 145 | 424560
Subtotal - Infosys - SAP Delivery |  | 366 |  |  | 424560
JCI Internal Support - Tracked Only
JCI Internal Support - Tracked Only | JCI Application Owner | 52 | 416 | 0 | 0
JCI Internal Support - Tracked Only | JCI Business Lead | 55 | 440 | 0 | 0
JCI Internal Support - Tracked Only | JCI HR Lead | 62 | 496 | 0 | 0
JCI Internal Support - Tracked Only | JCI IT Manager | 306 | 2448 | 0 | 0
JCI Internal Support - Tracked Only | JCI Legal Counsel | 85 | 680 | 0 | 0
JCI Internal Support - Tracked Only | JCI SAP Owner | 102 | 816 | 0 | 0
JCI Internal Support - Tracked Only | JCI Sponsor | 12 | 96 | 0 | 0
Subtotal - JCI Internal Support - Tracked Only |  | 674 |  |  | 0
KPMG - Architecture and Migration Advisory
KPMG - Architecture and Migration Advisory | KPMG Data Architect | 95 | 760 | 180 | 136800
KPMG - Architecture and Migration Advisory | KPMG Enterprise Architect | 227 | 1816 | 190 | 345040
KPMG - Architecture and Migration Advisory | KPMG Infrastructure Architect | 292 | 2336 | 185 | 432160
KPMG - Architecture and Migration Advisory | KPMG Security Architect | 145 | 1160 | 190 | 220400
KPMG - Architecture and Migration Advisory | KPMG Workplace Lead | 145 | 1160 | 165 | 191400
Subtotal - KPMG - Architecture and Migration Advisory |  | 904 |  |  | 1325800
KPMG - Programme Governance
KPMG - Programme Governance | KPMG Change Lead | 102 | 816 | 150 | 122400
KPMG - Programme Governance | KPMG PMO Lead | 175 | 1400 | 220 | 308000
KPMG - Programme Governance | KPMG Project Manager | 340 | 2720 | 170 | 462400
Subtotal - KPMG - Programme Governance |  | 617 |  |  | 892800
KPMG - SAP Advisory
KPMG - SAP Advisory | KPMG SAP Architect | 252 | 2016 | 210 | 423360
Subtotal - KPMG - SAP Advisory |  | 252 |  |  | 423360
KPMG - Testing, Deployment, and Readiness
KPMG - Testing, Deployment, and Readiness | KPMG Deployment Lead | 105 | 840 | 150 | 126000
KPMG - Testing, Deployment, and Readiness | KPMG Test Lead | 209 | 1672 | 155 | 259160
Subtotal - KPMG - Testing, Deployment, and Readiness |  | 314 |  |  | 385160
OVERALL PROJECT TOTAL |  |  |  |  | 6258880
Cost Breakdown by Category
Bosch Internal Support - Tracked Only |  | 625 |  |  | 0
Infosys - Application and Data Delivery |  | 856 |  |  | 820640
Infosys - Platform, Security, and Workplace |  | 1157 |  |  | 1154080
Infosys - Programme and Service Delivery |  | 792 |  |  | 832480
Infosys - SAP Delivery |  | 366 |  |  | 424560
JCI Internal Support - Tracked Only |  | 674 |  |  | 0
KPMG - Architecture and Migration Advisory |  | 904 |  |  | 1325800
KPMG - Programme Governance |  | 617 |  |  | 892800
KPMG - SAP Advisory |  | 252 |  |  | 423360
KPMG - Testing, Deployment, and Readiness |  | 314 |  |  | 385160
Cost Breakdown by Phase
Phase 0: Mobilize carve-out governance and TSA baseline | 2026-07-01 to 2026-10-01 |  |  |  | 388440
Phase 1: Discover landscape and design the merger zone | 2026-10-02 to 2027-01-31 |  |  |  | 1319320
Phase 2: Build merger zone and prepare transition factory | 2027-02-01 to 2027-07-31 |  |  |  | 2493560
Phase 3: Test, migrate to merger zone, and prepare Bosch landing | 2027-08-01 to 2027-12-10 |  |  |  | 1194440
Phase 4: Final readiness and GoLive decision | 2027-12-11 to 2028-01-01 |  |  |  | 53560
Phase 5: Hypercare, TSA exit, and Bosch handover | 2028-01-02 to 2028-04-01 |  |  |  | 809560
CAPEX / Additional Costs - Excluded from Labour Total
SAP expert support and rehearsal contingency | Risk Register R001 - external SAP carve-out support, rehearsal environment, and specialist remediation capacity. |  |  | 600,000 - 1,200,000
Merger-zone platform acceleration reserve | Risk Register R002 - additional platform engineering or temporary capacity if merger-zone build slips. |  |  | 400,000 - 900,000
Cutover command-center and rollback reserve | Risk Register R003 - final cutover defect sprint, extended command center, and rollback rehearsal support. |  |  | 250,000 - 500,000
Cyber control uplift and incident readiness | Risk Register R007 - DLP, logging, security review, and cyber readiness controls for the merger zone. |  |  | 250,000 - 500,000
Platform procurement and fallback capacity | Risk Register R012 - long-lead platform and connectivity fallback capacity. |  |  | 200,000 - 450,000
Regional hosting and legal compliance provision | Risk Register R014 - data sovereignty remediation or local hosting design changes if required. |  |  | TBC - confirm at QG1
Third-party audit and supplier-governance provision | Risk Register R020 - subcontractor audit and compliance assurance if external delivery layers expand. |  |  | 100,000 - 200,000
1. Derived from the generated schedule and aligned to the generated risk register rather than copied from any legacy project.
2. Phase names and dates match the schedule exactly: Phase 0 through Phase 5 as generated for Trinity-CAM (GPT).
3. Every schedule resource token has a matching cost line; Bosch and JCI internal roles are tracked at zero rate to preserve resource traceability without inflating the external labour baseline.
4. Integration-model note: the merger zone is a temporary operational bridge between JCI and Bosch, so platform and security contingencies are carried separately from labour totals.
5. High-priority risk references for contingency lines: R001, R002, R003, R007, R012, R014, and R020.
6. Budget baseline remains TBC - to be approved at QG1.