## Slide 1
Trinity-CAM (GPT)
Management Stakeholder Presentation
Integration model carve-out from JCI to Bosch via an Infosys-operated merger zone
Report date: 05 April 2026
48 sites | 12,000 IT users | 1,800+ applications | GoLive 01 Jan 2028
Seller: Johnson Controls International | Buyer: Robert Bosch GmbH
Prepared from generated schedule, risk, cost, and status outputs

## Slide 2
Executive Summary
April 2026 baseline view before programme kickoff on 01 Jul 2026
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
The carve-out transfers the JCI air conditioning business into Bosch using a temporary merger zone operated by Infosys.
All 12,000 users and 1,800+ applications start on the JCI side; the programme therefore depends on a clean JCI to merger-zone to Bosch transition path.
TSA operations conclude on 30 Jun 2026, followed by immediate programme mobilization and QG0 kickoff on 01 Jul 2026.
The derived external labour baseline is EUR 6.26M; CAPEX and contingency decisions remain gated to QG1.
The current register holds 24 threats with the highest exposure concentrated in SAP critical path, merger-zone readiness, and pre-GoLive quality gates.
Programme start
01 Jul 2026
GoLive
01 Jan 2028
Completion
01 Apr 2028
Top risk score
20
Management message
This is a pre-kickoff control baseline rather than an in-flight status deck. The immediate focus is governance stand-up, Infosys onboarding, and QG1 concept maturity.

## Slide 3
Programme Scope & Operating Model
Integration carve-out design for Trinity-CAM
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
JCI source IT -> Infosys merger zone -> Bosch target IT
The merger zone is a temporary operational bridge, not the target-state platform.
Seller: Johnson Controls International air conditioning business.
Buyer: Robert Bosch GmbH as sponsor customer and target operating owner.
PMO and methodology lead: KPMG.
Delivery partner: Infosys for merger-zone setup, run, IT services, and migrations.
Global scope covers 48 sites and 12,000 IT users.
Application estate exceeds 1,800 systems including a major SAP landscape.
TSA supports continuity until the programme start boundary and remains central to exit planning.
GoLive marks Day 1 operation in the merger zone; Bosch steady-state handover completes by QG5.
Sites
48
Users
12,000
Applications
1,800+
Delivery model
Integration via temporary merger zone

## Slide 4
Integrated Timeline & Stage Gates
Dates are read directly from the generated programme schedule
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
QG0 - Programme kickoff approved
01 Jul 2026
QG1 - Concept and transition model approved
01 Oct 2026
QG2 and QG3 - Build complete and test entry approved
31 Jul 2027
QG4 - Pre-GoLive gate approved
10 Dec 2027
GoLive - Day 1 cutover to merger zone complete
01 Jan 2028
QG5 - Project completion approved
01 Apr 2028
Phase sequence: Mobilize -> Discover/Design -> Build -> Test/Migrate -> Final Readiness -> Hypercare/Handover
Next 90 days to QG1
01 Jul 2026 to 15 Jul 2026: Stand up PMO, governance cadence, and workstream RACI
02 Jul 2026 to 31 Jul 2026: Onboard Infosys for merger zone delivery and managed services
15 Jul 2026 to 30 Aug 2026: Baseline TSA towers, service owners, and exit principles
11 Jul 2026 to 15 Aug 2026: Define legal perimeter, contracts, and supplier dependencies
QG4 remains separated from GoLive by a controlled final-readiness buffer.
All post-GoLive work is stabilization and Bosch handover only.
The schedule has no summary-task predecessor defects or gate/date collisions.

## Slide 5
Budget & Cost Structure
Derived from the generated labour cost plan and aligned to the risk register
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
External labour baseline
EUR 6.26M
Largest phase
EUR 2.49M
Budget release gate
QG1
Budget note
Budget baseline remains TBC - to be approved at QG1.
Cost by delivery team
KPMG - Architecture and Migration Advisory
EUR 1.33M
Infosys - Platform, Security, and Workplace
EUR 1.15M
KPMG - Programme Governance
EUR 0.89M
Infosys - Programme and Service Delivery
EUR 0.83M
Infosys - Application and Data Delivery
EUR 0.82M
Phase concentration
Phase 1: EUR 1.32M
Phase 2: EUR 2.49M
Phase 3: EUR 1.19M
Phase 4: EUR 0.05M
CAPEX / contingency carried outside labour baseline
SAP expert support and rehearsal contingency: 600,000 - 1,200,000
Merger-zone platform acceleration reserve: 400,000 - 900,000
Cutover command-center and rollback reserve: 250,000 - 500,000

## Slide 6
Top Risks & Management Actions
Prioritization derived from actual probability and impact fields in the GPT risk register
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
Open risks
24
High exposure
2
Medium exposure
9
Control focus
SAP, merger-zone readiness, wave execution, data quality
R001
SAP carve-out build and system copy into the merger zone reveal shared master data, hard-coded integrations, or sequence...
Score 20
KPMG SAP Architect
Mitigate
R003
The programme reaches late November 2027 with unresolved critical defects, incomplete migration evidence, or missing ste...
Score 15
KPMG PMO Lead
Mitigate
R023
Phase 1 architecture and application triage identify a meaningful subset of applications and infrastructure services tha...
Score 12
Infosys Cloud Lead
Exploit
R010
Migration rehearsals expose material data-quality defects in SAP or non-SAP datasets that require manual correction and...
Score 12
JCI Data Owner
Mitigate
R009
One or more user waves takes longer than planned because local site readiness, floorwalking support, or device enrollmen...
Score 12
Infosys Service Delivery Lead
Mitigate
Management direction: hold a weekly integrated risk review from QG1 onward, with SAP and merger-zone controls tracked as explicit steering actions rather than buried in workstream logs.

## Slide 7
Management Decisions Required
Actions to keep the programme viable ahead of QG1 and QG4
Robert Bosch GmbH | Trinity-CAM carve-out
Report date 05 Apr 2026
Approve the QG1 design and funding gate for merger-zone architecture, security controls, and programme governance on 01 Oct 2026.
Confirm Infosys as the accountable delivery partner for merger-zone build, operation, and migration throughput targets.
Mandate JCI data, application, and TSA tower owners to deliver named counterparts and decision SLAs before mobilisation completes.
Confirm Bosch target-state integration resources early enough to absorb the Day 1 merger-zone landing and the QG5 handover path.
Maintain 01 Jan 2028 as the hard Day 1 date and treat the 10 Dec 2027 QG4 gate as non-negotiable.
Key dates
QG1: 01 Oct 2026 QG2/QG3: 31 Jul 2027 QG4: 10 Dec 2027 GoLive: 01 Jan 2028 QG5: 01 Apr 2028
Programme principle: No hidden scope transfer from JCI to Bosch without governance, budget, and exit evidence.