## Cover sheet
Risk Analysis M&A |  | IT-as-is Manager | Bosch IT (Seller IT Manager)
|  | IT-Project Manager | Erik Ho (BD/MIL-ICC)
- Cover Sheet - |  | PMI-Lead | Hamburger PMO
Information about the project and the risk analysis:
Actions are tracked in
Further information:
Participants of latest meeting/update of risk analysis:
| Participant |  | Department |  | Function
PMI-Lead
IT-Project Manager
PjQM
Technical expert from project team
The required signature of the risk analysis (PjM and PjQM) is covered by the signature of the respective QA.
Document History:
| Change |  | Version | Date | Changed by
…
The risk analysis has to be updated regularly during the whole merger duration - The different states have to be versioned -

## Analysis of project risks
Analysis of as-is operation risks | [9 empty] | RZ statistic |  | Please insert rows exclusively over button!
[10 empty] | Threshold: | 12
Risks higher than or equal to threshold:
No. | Sub- project (optional) | Entry Date of Risk | Risk category | Risk (concrete, understandable description) | Effects (corresponds with T=Sign. of effects (column I)) | Causes | W | T | RZ | Actions (preventive and counter measures) | Responsible | Deadline | Status of action | Remarks / notes [optional] (e.g., critical general conditions; already planned actions)
1 |  |  | ScR - Schedule | GoLive (01 Dec 2026) at risk due to complexity of 17-site global cutover with 2600 users | Hard legal separation date tied to 01 Dec. No slip possible without board approval. | Parallel workstreams across EMEA, Americas and APAC; time-zone coordination overhead; limited cutover window | 4 | 5 |  | Phase cutover by region; EMEA first wave, then Americas and APAC; dedicate regional cutover leads; daily SteerCo from QG3 | Erik Ho (BD/MIL-ICC), IT PM | 30-Nov-26 | Red
2 |  |  | SR - Scope | SAP / ERP separation significantly more complex than initial inventory suggests | ERP is on the critical path. Any delay directly impacts GoLive. Escalation to SteerCo required. | Multiple shared SAP mandants; global Solar data entangled with Bosch corporate ERP; extensive custom ABAP | 4 | 5 |  | Start ERP separation assessment immediately (Jul 2026); engage dedicated SAP migration partner; greenfield decision by QG2 | Bosch ERP / SAP Team, Erik Ho (BD/MIL-ICC) | 31-Aug-26 | Red
3 |  |  | SR - Scope | Buyer identity unknown – final IT handover scope and integration requirements unclear | Stand Alone model mitigates buyer-dependency risk. Inherent uncertainty accepted. | Buyer undisclosed for legal reasons; buyer IT readiness and architecture unknown | 3 | 5 |  | Design Solar IT as fully self-sufficient Stand Alone; no buyer-side dependencies in baseline plan; update scope at buyer disclosure | Erik Ho (BD/MIL-ICC), Legal, Steering Committee | 30-Jun-26 | Amber
4 |  |  | ScR - Schedule | Active Directory migration for 2600 users across 17 sites delayed due to tooling or forest complexity | AD is foundational. Pilot critical. No backout option once cutover begins. | AD migration at scale requires extensive testing; DNS, GPO, and trust configuration errors at scale | 3 | 4 |  | Start AD build Sep 2026; pilot 2 sites first; 2x dress rehearsals; AD locked by QG3; dedicated AD team | Bosch AD Team, IT PM | 30-Oct-26 | Amber
5 |  |  | RR - Resource | Insufficient Bosch IT resources to manage 17-site global programme simultaneously | Resource gap most acute in Phases 3-4. Early contracting required. | Bosch IT teams have competing priorities; carved-out Solar team capacity limited during transition | 3 | 4 |  | Resource plan confirmed by QG1; third-party SI engagement for site execution; outsource device rollout | Erik Ho (BD/MIL-ICC), Bosch CIO | 30-Jun-26 | Amber
6 |  |  | BtR - Budget | Programme cost exceeds initial estimate due to global WAN/network provisioning complexity | Budget contingency TBC – to be approved at QG1. Conservative estimate +25%. | 17 sites requiring new WAN circuits; lead times 8-16 weeks per region; APAC/Americas pricing higher than EMEA | 3 | 4 |  | Issue global WAN RFQ by QG1; obtain firm quotes with lead times; plan parallel ordering | Finance, Bosch Procurement, WAN Provider | 30-Jun-26 | Amber
7 |  |  | LR - Legality | Data residency and privacy regulation compliance gaps across multiple jurisdictions (GDPR, US, APAC) | Multi-jurisdictional compliance is inherently complex. Early legal engagement critical. | 17 sites span multiple legal jurisdictions; Solar data flows must comply with GDPR, US data law, and APAC regulations | 3 | 4 |  | Engage regional legal counsel per jurisdiction by QG2; data residency architecture confirmed before build | Legal, Bosch CISO, Erik Ho (BD/MIL-ICC) | 31-Aug-26 | Amber
8 |  |  | ScR - Schedule | WAN circuit provisioning delayed at one or more of the 17 sites, blocking IT infrastructure build | WAN is on critical path for site readiness. Early ordering is mandatory. | Carrier lead times 8-16 weeks; site access permissions; regulatory approvals in some regions | 3 | 4 |  | Order WAN circuits by QG1; use 4G/5G backup connectivity as interim bridge; track weekly per site | Bosch Infra, WAN Provider | 30-Jun-26 | Amber
9 |  |  | SR - Scope | M365 / Azure tenant provisioning for 2600 mailboxes underestimated in complexity | M365 migration at 2600 users is large but well-understood. Phased approach required. | Large tenant migration; mailbox migration sequencing across time zones; SharePoint and Teams data volume | 2 | 4 |  | Begin M365 pre-ordering and test tenant in May 2026; use tiered migration waves by region | Bosch Azure Team, Erik Ho (BD/MIL-ICC) | 30-Jun-26 | Green
10 |  |  | CR - Change | Change management resistance from 2600 Solar users impacting Day 1 adoption | Change adoption risk is manageable with structured plan and champions network. | Global user base across 17 sites; cultural differences; limited communication in local languages | 2 | 4 |  | Global change and communications plan by QG2; local language change materials; regional change champions | Comms + Regional IT, Business Leads | 31-Aug-26 | Green
11 |  |  | BtR - Budget | Licence change-of-control costs significantly exceed budget across Solar application portfolio | Estimate 30-50% licence cost uplift for key applications. Build into budget. | ISVs enforce new licence terms on change of control; some vendors use carve-out as renegotiation leverage | 2 | 4 |  | Complete licence audit with CoC clause review by QG2; negotiate amendments early | Bosch Procurement, Legal | 31-Aug-26 | Green
12 |  |  | QR - Quality | UAT failures due to incomplete ERP / SAP regression testing across Solar business processes | ERP UAT is the highest-risk test stream. Dedicated ERP test lead required. | ERP test cases insufficient; business users unavailable for global UAT coordination | 2 | 4 |  | ERP test plan locked at QG3; business sign-off on UAT cases by 1-Nov-2026; regional UAT coordinators | Test Lead, Business Leads, Bosch ERP / SAP Team | 20-Nov-26 | Green
13 |  |  | RR - Resource | Key Solar IT staff retained by Bosch after separation, creating knowledge gap for Buyer | 17 sites across multiple employment law jurisdictions. Country-specific HR review required. | TUPE/transfer rules vary by country; some IT staff may not transfer with Solar business | 2 | 4 |  | HR IT mapping by QG1; retention agreements for key knowledge holders; knowledge transfer plan from Phase 5 | Bosch HR, Erik Ho (BD/MIL-ICC), Legal | 30-Jun-26 | Green
14 |  |  | CR - Change | Data migration incomplete or inconsistent for Solar business data by Day 1 across 17 sites | Solar data is commercially sensitive. Zero tolerance for data loss. | Data classification incomplete; high data volume across global sites; migration tooling untested at scale | 2 | 4 |  | Data ownership rules locked by QG2; phased data migration rehearsals per region; dress rehearsal mandatory | Bosch IT, Data Owner, IT PM | 30-Nov-26 | Green
15 |  |  | ScR - Schedule | TSA exit extends beyond planned May 2027 completion date | TSA overrun extends Bosch carver support costs. Maximum 6-month TSA contractually enforced. | TSA service definitions unclear; Buyer IT readiness delayed; some services harder to exit than planned | 2 | 3 |  | TSA catalogue locked at QG2; weekly TSA governance reviews from Day 1; maximum TSA duration contractually limited | Bosch IT, Buyer IT, Erik Ho (BD/MIL-ICC) | 31-May-27 | Green
16 |  |  | QR - Quality | Help Desk / IT Ops globally understaffed or untrained at GoLive across 17 sites | 17-site support model requires regional IT Ops leads. Contractor options as fallback. | Global recruitment timeline long; training lag for new IT staff across multiple regions | 2 | 3 |  | Global IT Ops hiring by Aug 2026; training Oct 2026; hypercare team embedded globally from Day 1 | Bosch HR, IT Ops, Regional IT Leads | 01-Nov-26 | Amber
17 |  |  | BR - Business | Solar business continuity disruption during cutover weekend impacts customer commitments | OT/SCADA scope must be confirmed by QG2. Critical operational systems require special handling. | Solar energy business is operationally critical; 24/7 monitoring systems must not be interrupted | 2 | 3 |  | Identify OT / SCADA systems in scope; plan phased cutover avoiding operational peaks; 24/7 war room during cutover | Solar Business Operations, IT PM | 30-Oct-26 | Green
18 |  |  | LR - Legality | Regulatory approvals for IT asset transfer delayed in one or more jurisdictions | Low probability but high impact if materialises. Flag to Group Legal immediately. | IT asset transfers in certain countries require regulatory notifications or approvals (e.g. competition authorities) | 1 | 4 |  | Map regulatory requirements per country by QG1; filings submitted by QG2; buffer time in Phase 5 | Legal, Finance, Erik Ho (BD/MIL-ICC) | 30-Jun-26 | Green
Note on A7: The risks are numbered sequentially.
Note on B7: Multi-Projects: Please insert the project to which the risk refers
Note on C7: Only relevant for risks identified after creation of risk analysis.
Note on D7: If needed, risks can be assigned to risk categories. The following categories can be used as well as others. BR = Business BtR = Budget CR = Customer Satisfaction QR = Quality RR = Resource ScR = Schedule SR = Scope LR = Legality SrR = Security PR = Further product risks EM = Employee
Note on F7: What are the effects once the risk/ potential failure occurs?
Note on G7: What are the causes for the risk/the failure to occur?
Note on H7: W = Probability of occurrence: 5 = very high 4 = high 3= medium 2 = low 1 = unlikley
Note on I7: T= Significance of effects: 5 = very high 4 = high 3 = medium 2 = low 1 = unlikley
Note on J7: Product of W and T; The RZ shall support the prioritisation of risks and will be calculated automatically
Note on N7: Possible values: open, in process (iP), completed (com)
Note on O7: What was planned to minimise the risk before carrying out this risk analysis? E.g.: Database overflow. Plan for a monitoring software generating alerts once data volume reaches 80% of hard disk capacity. Not all risks can be eliminated by an action.

## Explanation_History
Information about method/template
Scope of risk analysis: (Attention: Procedure partly changed compared to previous template version!) |  |  | Project risks can generally be differed by product risks (e.g. product suitability, general conditions of product) and process risks (e.g. project management; development process or process of producing the project result). In the risk analysis both has to be covered.
Update: Cycle and versions |  |  | The risk analysis has to be updated regularly during the whole project duration - at least to each QA. The different states have to be versioned - the currently latest version has to be filed with the respective QA.
Update: Procedure (Attention: Procedure partly changed compared to previous template version!) |  |  | Updating the risk analysis, existing risks will be reassessed and new risk will be listed in the overview. By reassessing existing risks, the existing values can be overwritten with the new values because previous values are saved in the different versions of the document. Therefor old versions of the risk analysis have to be archived with the project documentation.
Definition of actions (Attention: Procedure partly changed compared to previous template version!) |  |  | At least for risks whose risk figure (RZ) is higher than or equal to the threshold value of 12, an action or a reason why no action is defined has to be named. It is recommended to define actions also to risks with high significance of effects (T). The threshold can be lowered (e.g. from 12 to 9) but not increased for the single project. To every action a responsible person and deadline have to be named.
Tracking of risks and actions (Attention:Procedure partly changed compared to previous template version!) |  |  | The document in which the actions are tracked has to be named in the cover sheet. Actions have to be done on schedule (requirement of C/AU)! If an action is processed and the status is set on 'completed', the risk has to be reassessed. Therefore the old values can simply be overwritten. If an action lowers the former significance of effects (T) of the risk, not only the value of T but also the effects (verbal description column F) have to be overwritten. If a risk is still high after completion of the action, a new action has to be defined. Traceability of the actions and their completion is given by the recording of the different versions of the risk analysis.
Documentation |  |  | To ensure the traceability of the risk analysis (requirement of C/AU), - the docment history (cover sheet) and - the column " entry date of risk" (for later listed risks) have to be filled in.
If risks are escalated, this has to be definde as an action.
Information about the makros |  |  | To ensure the consistency of the template it is absolutely necessary that new lines are inserted exclusively about the button "New line".
Additional Information about risk categories |  |  | Explanation "Business Risk": Risk that the business processes of the customers do not work as needed
Risk assessment:
| W - Probability of occurrence: |  | 5 = very high 4 = high 3 = medium 2 = low 1 = unlikely
| T - Significance of effects: |  | 5 = very severe 4 = severe 3 = medium 2 = low 1 = none
| RZ - Risk figure |  | The risk figure supports the prioritization of risks and is the result of the product of W and T (RZ = W x T).
Document History Template "AS-IS operation Risk Analysis"
Version | Release Date | Author | Description of Changes
1.0 | 2022-06-13 | BD/MIL-MIA Ladenburgerr | Adaption to new BD-organisation
Changes of Content:
first version: Risk analysis template based on project risk analysis