## Cost Plan
ZEBRA PROJECT COST PLAN
Project Name: | Zebra (Packaging Carve-Out)
Timeline: | 1 April 2026 - 31 October 2027
Scope: | 37 sites, 3500+ users, 208 applications, SAP + TSA
Based on: | Zebra_Project_Schedule.xlsx
Risk-aligned: | Zebra_Risk_Register.xlsx
CATEGORY | RESOURCE | TOTAL DAYS | TOTAL HRS | HOURLY RATE (EUR) | TOTAL COST (EUR)
KPMG PMO & Governance
| KPMG PMO Lead | 240 | 1920 | 750 | 180000
| KPMG Project Manager | 320 | 2560 | 650 | 208000
SUBTOTAL |  |  |  |  | 388000
KPMG SAP & ERP Build
| KPMG SAP Architect | 150 | 1200 | 700 | 105000
| KPMG SAP Build Lead | 280 | 2240 | 680 | 190400
| KPMG SAP Specialist | 350 | 2800 | 600 | 210000
SUBTOTAL |  |  |  |  | 505400
KPMG Testing & QA
| KPMG QA Lead | 200 | 1600 | 650 | 130000
| KPMG Test Specialist | 480 | 3840 | 550 | 264000
SUBTOTAL |  |  |  |  | 394000
KPMG Change Management & Training
| KPMG Change Manager | 200 | 1600 | 600 | 120000
| KPMG Trainer | 280 | 2240 | 500 | 140000
SUBTOTAL |  |  |  |  | 260000
KPMG Data & Integration
| KPMG Data Architect | 160 | 1280 | 700 | 112000
| KPMG Data Engineer | 320 | 2560 | 550 | 176000
SUBTOTAL |  |  |  |  | 288000
KPMG Infrastructure & Security
| KPMG Infrastructure Architect | 120 | 960 | 650 | 78000
SUBTOTAL |  |  |  |  | 78000
RoboGmbH IT Support (Seller)
| RoboGmbH IT Manager | 180 | 1440 | 400 | 72000
| RoboGmbH ERP Specialist | 200 | 1600 | 350 | 70000
| RoboGmbH IT Technician | 250 | 2000 | 250 | 62500
SUBTOTAL |  |  |  |  | 204500
TOTAL LABOR COST |  |  |  |  | 2117900
COST BREAKDOWN BY CATEGORY
KPMG PMO & Governance | 388000
KPMG SAP & ERP Build | 505400
KPMG Testing & QA | 394000
KPMG Change Management & Training | 260000
KPMG Data & Integration | 288000
KPMG Infrastructure & Security | 78000
RoboGmbH IT Support (Seller) | 204500
COST BREAKDOWN BY PHASE
Phase 0: Initialization (01.04.2026 - 17.04.2026) | 63537
Phase 1: Concept (18.04.2026 - 18.05.2026) | 254148
Phase 2: Architecture & Design (19.05.2026 - 27.07.2026) | 529475
Phase 3: Development, Build & Test (28.07.2026 - 27.05.2027) | 1016592
Phase 4: GoLive & Closure (28.05.2027 - 31.10.2027) | 254148
CAPEX / ADDITIONAL COSTS (Excluded from Labor Total)
Risk #1 - SAP Separation Audit (external audit firm) | 35000 | Risk #1 (High P×I): 3x dry-run audits
Risk #2 - Application Portfolio Tools & Licenses | 25000 | Risk #2 (High P×I): License transition support tooling
Risk #7 - Regulatory Compliance Assessment | 40000 | Risk #7 (Very High P×I): GDPR + data residency audit
Risk #12 - Parallel Run System Rental (2 weeks) | 20000 | Risk #12 (High P×I): Temporary parallel environment
General Contingency (5% of labor) | 105895 | TBC - calculated at end
CAPEX SUBTOTAL | 225895
GRAND TOTAL (Labor + CAPEX) | 2343795
NOTES
1. Cost plan is DRAFT — to be approved at QG0. 2. Labor rates based on typical KPMG/Seller day rates; subject to FTE negotiation. 3. SAP system separation and 208-application portfolio transition are highest-cost complexity drivers. 4. CAPEX items (rows above) are linked to high-priority risks in Risk Register. 5. 37-site multi-geography cutover requires significant QA and change management investment. 6. TSA period labor (seller IT support) extends through Phase 4 to handover completion. 7. Contingency (5% of labor) covers risk mitigation overruns; escalation for CAPEX overruns required. 8. Buyer IT cost allocation not included (assumed by buyer under Stand Alone model).