## Schedule
ID | Outline Level | Name | Duration (days) | Start | Finish | Predecessors | Resource Names | Notes | Milestone
1 | 1 | Phase 0: Initialization | 60 days | 2026-04-01 | 2026-05-31 |  |  | Governance, legal, assessment baseline | No
2 | 2 | 0.1 Project Setup & Governance | 16 days | 2026-04-01 | 2026-04-17 |  |  | PMO, steering, RACI | No
3 | 3 | Appoint Zebra Programme Leads | 5 days | 2026-04-01 | 2026-04-06 |  | KPMG PMO Lead + KPMG Project Manager | Seller and Buyer sponsors appointed | No
4 | 3 | Establish Steering Committee | 3 days | 2026-04-04 | 2026-04-07 | 3 | KPMG PMO Lead | First steering committee session | No
5 | 3 | Define RACI and Governance Model | 5 days | 2026-04-04 | 2026-04-09 | 3 | KPMG Project Manager + KPMG PMO Lead | Approval of governance structure | No
6 | 3 | Set Up PMO Tools and Collaboration Site | 8 days | 2026-04-09 | 2026-04-17 | 3 | KPMG PMO Lead | SharePoint site, project tracking active | No
7 | 3 | Onboard KPMG and RoboGmbH Teams | 7 days | 2026-04-09 | 2026-04-16 | 3 | KPMG PMO Lead + RoboGmbH IT Manager | All teams mobilized | No
8 | 2 | 0.2 IT Landscape Assessment - 37 Sites | 30 days | 2026-04-11 | 2026-05-11 | 3 |  | Inventory, apps, infra, scope | No
9 | 3 | Application Portfolio Inventory (~208 apps) | 12 days | 2026-04-11 | 2026-04-23 | 5 | KPMG Data Architect + RoboGmbH IT Manager | Packaging-specific apps; flag shared Bosch dependencies | No
10 | 3 | IT Infrastructure As-Is Mapping (37 sites) | 15 days | 2026-04-11 | 2026-04-26 | 5 | RoboGmbH IT Manager + KPMG Infrastructure Architect | Site surveys top 15 locations; EMEA/APAC prioritized | No
11 | 3 | ERP Landscape Analysis (SAP scope) | 15 days | 2026-04-11 | 2026-04-26 | 5 | KPMG SAP Architect + RoboGmbH ERP Specialist | Identify packaging-specific vs shared SAP; separation complexity | No
12 | 3 | Data Ownership & Separation Rules (Draft) | 10 days | 2026-04-21 | 2026-05-01 | 9,11 | KPMG Data Architect | Data classification baseline | No
13 | 3 | Contract & Licence Inventory (~208 apps) | 12 days | 2026-04-11 | 2026-04-23 | 5 | RoboGmbH IT Manager | Change of control review; FOSS compliance; ~3,500 device licences | No
14 | 3 | HR IT Systems & Payroll Separation (37 sites) | 10 days | 2026-04-16 | 2026-04-26 | 5 | KPMG Data Architect | Country-by-country HR rules (Germany, China, India, Mexico, etc.) | No
15 | 3 | OT & Production IT Assessment | 10 days | 2026-04-19 | 2026-04-29 | 5 | RoboGmbH IT Manager + KPMG Infrastructure Architect | Production systems; safety certifications; ICS/SCADA scope | No
16 | 3 | Country-Specific Legal Requirements (Multi-region) | 8 days | 2026-04-23 | 2026-05-01 | 5 | KPMG Project Manager | Germany works council; China PIPL; India; Mexico SAT delays | No
17 | 2 | 0.3 Project Charter & Scope Definition | 20 days | 2026-05-01 | 2026-05-21 | 8 |  | Charter, approval, scope frozen | No
18 | 3 | Draft Zebra Project Charter | 8 days | 2026-05-01 | 2026-05-09 | 8 | KPMG PMO Lead + KPMG Project Manager | Executive charter document | No
19 | 3 | Define Scope Boundaries (37 sites, 3,500+ users, 208 apps) | 8 days | 2026-05-06 | 2026-05-14 | 10,11 | KPMG Project Manager + KPMG SAP Architect | Stand Alone model confirmed; no Merger Zone | No
20 | 3 | Guiding Principles Workshop | 3 days | 2026-05-11 | 2026-05-14 | 18,19 | KPMG PMO Lead + All Workstream Leads | First Make It Work; priorities set | No
21 | 3 | TSA Framework Preliminary Scope | 8 days | 2026-05-11 | 2026-05-19 | 18,19 | KPMG Project Manager + RoboGmbH IT Manager | Bosch operates all IT until Day 1; TSA scope defined | No
22 | 3 | Project Charter Approval & Gate QG0 | 5 days | 2026-05-19 | 2026-05-24 | 18,19,20,21 | KPMG PMO Lead | Charter signed; Phase 0 gate approval | No
23 | 3 | QG0 - Initialization Quality Gate | 0 days | 2026-05-24 | 2026-05-24 | 22 | KPMG PMO Lead + Buyer Sponsor | Charter approved; inventory confirmed; governance ready | Yes
24 | 1 | Phase 1: Concept | 65 days | 2026-05-25 | 2026-07-29 | 23 |  | Requirements, design strategy, baseline planning | No
25 | 2 | 1.1 Detailed As-Is Analysis | 40 days | 2026-05-25 | 2026-07-04 | 23 |  | Landscape detail, dependencies | No
26 | 3 | Application Portfolio Deep Dive (LeanIX, 208 apps) | 20 days | 2026-05-25 | 2026-06-14 | 9 | KPMG Data Architect + KPMG Infrastructure Architect | Flag Bosch shared dependencies; categorize critical vs standard | No
27 | 3 | SAP Landscape Detailed Analysis | 20 days | 2026-05-25 | 2026-06-14 | 11 | KPMG SAP Architect + RoboGmbH ERP Specialist | Identify separation complexity; module scope | No
28 | 3 | Infrastructure Detailed Mapping (37 sites, top 15 surveyed) | 20 days | 2026-05-25 | 2026-06-14 | 10 | KPMG Infrastructure Architect + RoboGmbH IT Manager | WAN, LAN, co-lo, security topology | No
29 | 3 | Contract & Licence Final Inventory (208 apps) | 15 days | 2026-06-08 | 2026-06-23 | 13 | RoboGmbH IT Manager | Change of control clause review; vendor dependencies | No
30 | 3 | HR & Payroll System Separation (Multi-region) | 15 days | 2026-06-10 | 2026-06-25 | 14 | KPMG Data Architect | Region-specific payroll rules finalized | No
31 | 2 | 1.2 Stand-Alone Architecture Design Strategy | 25 days | 2026-05-31 | 2026-06-25 | 26,27,28 |  | Architecture concept (no Merger Zone) | No
32 | 3 | Architecture Concept Workshop (Stand Alone approach) | 5 days | 2026-05-31 | 2026-06-05 | 26 | KPMG SAP Architect + KPMG Infrastructure Architect | Confirm Stand Alone; no Merger Zone; target architecture | No
33 | 3 | WAN & Network Architecture (37 sites) | 12 days | 2026-06-15 | 2026-06-27 | 32,28 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Hub-and-spoke model; 1-2 regional co-lo; 4-6 month lead time | No
34 | 3 | Active Directory Design (New Forest) | 10 days | 2026-06-15 | 2026-06-25 | 32 | KPMG Infrastructure Architect | New AD forest for Zebra; fully independent from Bosch | No
35 | 3 | M365 & Azure Tenant Design (3,500+ mailboxes) | 10 days | 2026-06-15 | 2026-06-25 | 32 | KPMG Infrastructure Architect | New M365 tenant; OneDrive, Teams in scope | No
36 | 3 | Co-Location & Data Centre Selection (1-2 regional hubs) | 10 days | 2026-05-31 | 2026-06-10 | 28 | RoboGmbH IT Manager | Primary hub selection; decision by QG1 | No
37 | 3 | Security Architecture (NewCo Zebra independent) | 12 days | 2026-06-20 | 2026-07-02 | 33,34 | KPMG Infrastructure Architect | Independent SOC; security baseline | No
38 | 3 | IAM & Identity Design (Decouple from Bosch) | 10 days | 2026-06-20 | 2026-06-30 | 34 | KPMG Infrastructure Architect | New IAM platform; decouple from Bosch Saviynt | No
39 | 2 | 1.3 Zebra IT Migration Strategy | 25 days | 2026-06-15 | 2026-07-10 | 27,29 |  | ERP, apps, clients, data | No
40 | 3 | ERP Migration Strategy Decision (Shell Copy vs Greenfield) | 12 days | 2026-06-15 | 2026-06-27 | 27 | KPMG SAP Architect + RoboGmbH ERP Specialist | Shell copy benchmarked 9-12 months; decision by QG1 | No
41 | 3 | Application Categorization & Wave Planning (208 apps) | 12 days | 2026-06-25 | 2026-07-07 | 26,40 | KPMG Data Architect | Wave 1 ~60 critical; Wave 2 ~80 standard; Wave 3 ~68 local/OT | No
42 | 3 | Data Migration & Separation Strategy | 10 days | 2026-06-30 | 2026-07-10 | 12,27 | KPMG Data Architect + KPMG Data Engineer | Non-selective approach; residual data in Bosch until TSA exit | No
43 | 3 | TSA Service Catalogue Definition | 15 days | 2026-06-25 | 2026-07-10 | 21,32 | KPMG Project Manager + RoboGmbH IT Manager | Catalogue all Bosch services Zebra requires; exit criteria per service | No
44 | 3 | Zebra Stand-Alone Operating Model (post-TSA) | 12 days | 2026-07-05 | 2026-07-17 | 40,41 | KPMG Infrastructure Architect | All services exit directly post-TSA; define operating model | No
45 | 2 | 1.4 Client Device & Workplace Strategy | 12 days | 2026-06-15 | 2026-06-27 | 26 |  | 3,500+ device migration approach | No
46 | 3 | Client Device Inventory & Assessment (~3,500 devices) | 8 days | 2026-06-15 | 2026-06-23 | 26 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Device age, type, replacement plan for out-of-support | No
47 | 3 | Client Migration Approach (Wave-based reimaging) | 8 days | 2026-06-20 | 2026-06-28 | 46 | KPMG Infrastructure Architect | 3,500 devices across 37 sites; EMEA/APAC/Americas stagger | No
48 | 2 | 1.5 Planning & Baseline | 15 days | 2026-07-10 | 2026-07-25 | 31,39,45 |  | Schedule, budget, risk baseline | No
49 | 3 | Detailed Project Plan Development | 10 days | 2026-07-10 | 2026-07-20 | 31,39 | KPMG PMO Lead + KPMG Project Manager | Full phase schedule with dependencies | No
50 | 3 | Risk Register Baseline (Initial risks) | 8 days | 2026-07-10 | 2026-07-18 | 39 | KPMG Project Manager | Risk identification and scoring | No
51 | 3 | OPL Establishment & Tracking | 5 days | 2026-07-15 | 2026-07-20 | 49 | KPMG PMO Lead | Open Points List system active | No
52 | 3 | Resource Plan & Budget Baseline | 8 days | 2026-07-15 | 2026-07-23 | 49 | KPMG PMO Lead + KPMG Project Manager | Labour and CAPEX baseline | No
53 | 3 | QG1 - Concept Quality Gate | 0 days | 2026-07-25 | 2026-07-25 | 49,44,43 | KPMG PMO Lead + Buyer Sponsor | Architecture approved; ERP strategy decided; TSA catalogue signed; proceed to Design | Yes
54 | 1 | Phase 2: Architecture & Design | 60 days | 2026-07-26 | 2026-09-24 | 53 |  | Detailed design, vendor selection, architecture finalization | No
55 | 2 | 2.1 Infrastructure Design & Procurement | 40 days | 2026-07-26 | 2026-09-04 | 53 |  | WAN, co-lo, AD, M365, security design | No
56 | 3 | WAN Provider Selection & Ordering (37 sites) | 15 days | 2026-07-26 | 2026-08-10 | 33 | RoboGmbH IT Manager + KPMG Infrastructure Architect | Order immediately after design; 4-6 month lead time | No
57 | 3 | Co-Location Data Centre Procurement (1-2 regional hubs) | 20 days | 2026-07-26 | 2026-08-15 | 36 | RoboGmbH IT Manager | Primary EMEA co-locator for Zebra DC | No
58 | 3 | Active Directory Detailed Configuration | 20 days | 2026-08-09 | 2026-08-29 | 56,34 | KPMG Infrastructure Architect | New Zebra AD forest specifications; delegation model | No
59 | 3 | M365 Tenant & Azure Configuration (3,500+ mailboxes) | 18 days | 2026-08-14 | 2026-09-01 | 35,56 | KPMG Infrastructure Architect | Tenant isolation; licensing; governance | No
60 | 3 | Security & Firewall Architecture Finalization | 18 days | 2026-08-19 | 2026-09-06 | 37,56 | KPMG Infrastructure Architect | Network security, endpoint security, DLP policies | No
61 | 3 | IAM Platform & SSO Design | 15 days | 2026-08-19 | 2026-09-03 | 38 | KPMG Infrastructure Architect | Identity governance, provisioning automation | No
62 | 3 | CMDB & ITSM Platform Design | 12 days | 2026-08-24 | 2026-09-05 | 56,58 | KPMG Infrastructure Architect | ServiceNow or alternative ITSM platform configuration | No
63 | 2 | 2.2 SAP & ERP Design | 30 days | 2026-07-26 | 2026-08-25 | 40 |  | Shell copy prep, interfaces, auth design | No
64 | 3 | SAP System Landscape Detail & Separation | 15 days | 2026-07-26 | 2026-08-10 | 27 | KPMG SAP Architect + RoboGmbH ERP Specialist | Module scope for Zebra packaging | No
65 | 3 | SAP Shell Copy Detailed Approach & Timeline | 18 days | 2026-08-04 | 2026-08-22 | 40,64 | KPMG SAP Architect + KPMG SAP Build Lead | Extraction approach; timeline; re-configuration items | No
66 | 3 | SAP Interfaces & Integration Design (APIs) | 15 days | 2026-08-09 | 2026-08-24 | 64 | KPMG SAP Build Lead + KPMG Data Engineer | Identify all inbound/outbound interfaces; EDI approach | No
67 | 3 | SAP Authorization & Security Design | 12 days | 2026-08-14 | 2026-08-26 | 38,64 | KPMG Infrastructure Architect | User roles; segregation of duties; authorization matrix | No
68 | 3 | SAP Test Environment & Tools Selection | 10 days | 2026-08-14 | 2026-08-24 | 65 | KPMG SAP Architect + RoboGmbH ERP Specialist | SIT, UAT environment specifications; performance testing tools | No
69 | 2 | 2.3 Application Migration Design (208 apps) | 25 days | 2026-07-30 | 2026-08-24 | 41 |  | Wave definition, packaging, integration strategy | No
70 | 3 | Application Wave Refinement & Dependencies | 12 days | 2026-07-30 | 2026-08-11 | 41 | KPMG Data Architect | Wave 1/2/3 app list finalized; cross-wave dependencies | No
71 | 3 | Application Package Development (Wave 1 critical ~60 apps) | 18 days | 2026-08-07 | 2026-08-25 | 70 | KPMG Data Architect + KPMG Infrastructure Architect | Deployment package; configuration; cutover script | No
72 | 3 | Custom App Adaptation Design (Re-point to Zebra domain) | 15 days | 2026-08-14 | 2026-08-29 | 71 | KPMG Data Architect | Domain, AD, M365, ITSM configuration changes | No
73 | 2 | 2.4 Client Workplace Design & Imaging | 15 days | 2026-07-30 | 2026-08-14 | 47 |  | Device imaging, wave plan | No
74 | 3 | Standard Image Development (SCCM/Intune) | 12 days | 2026-07-30 | 2026-08-11 | 47 | KPMG Infrastructure Architect | Standard image for Zebra domain; hardware refresh plan | No
75 | 3 | Regional Wave Plan (EMEA / APAC / Americas devices) | 8 days | 2026-08-04 | 2026-08-12 | 47,74 | KPMG Infrastructure Architect | Wave sequencing; logistics; regional priorities | No
76 | 2 | 2.5 Cutover Strategy & TSA Finalization | 25 days | 2026-08-09 | 2026-09-03 | 41,43,66 |  | Go-live plan, TSA contracts | No
77 | 3 | Detailed Cutover Plan (37 sites, 208 apps, SAP) | 18 days | 2026-08-09 | 2026-08-27 | 41,65 | KPMG Project Manager + KPMG SAP Architect | Parallel run approach; rollback plan; timing sequence | No
78 | 3 | TSA Service Descriptions Final (All 37 sites) | 15 days | 2026-08-14 | 2026-08-29 | 43 | KPMG Project Manager + RoboGmbH IT Manager | Each TSA service line; exit date; acceptance criteria | No
79 | 3 | TSA SLA & KPI Framework | 10 days | 2026-08-24 | 2026-09-03 | 78 | KPMG Project Manager | SLA levels; reporting cadence | No
80 | 3 | TSA Legal & Contracts Final Review | 12 days | 2026-08-24 | 2026-09-05 | 78,79 | KPMG Project Manager | Contract finalization and signature readiness | No
81 | 3 | QG2/3 - Design Quality Gate | 0 days | 2026-09-06 | 2026-09-06 | 55,63,69,73,76 | KPMG PMO Lead + Buyer Sponsor | Infrastructure designed; ERP designed; apps packaged; devices planned; TSA approved; proceed to Build | Yes
82 | 1 | Phase 3: Development, Build & Test | 100 days | 2026-09-07 | 2027-05-22 | 81 |  | Infrastructure build, ERP setup, app prep, testing | No
83 | 2 | 3.1 Infrastructure Build (37 sites) | 60 days | 2026-09-07 | 2026-11-06 | 81 |  | WAN, co-lo, AD, M365, security, operations setup | No
84 | 3 | WAN Circuits Delivery (EMEA batch 1, ~8 sites) | 25 days | 2026-09-07 | 2026-10-02 | 56 | RoboGmbH IT Manager + KPMG Infrastructure Architect | 4-6 month lead completed; circuit testing | No
85 | 3 | WAN Circuits Delivery (APAC batch 1, ~6 sites) | 25 days | 2026-09-07 | 2026-10-02 | 56 | RoboGmbH IT Manager + KPMG Infrastructure Architect | China local provider; stagger by country | No
86 | 3 | WAN Circuits Delivery (Americas batch 1, ~4-5 sites) | 25 days | 2026-09-07 | 2026-10-02 | 56 | RoboGmbH IT Manager + KPMG Infrastructure Architect | Mexico legal entity confirmed before delivery | No
87 | 3 | Co-Location DC Setup & Testing | 30 days | 2026-09-07 | 2026-10-07 | 57 | RoboGmbH IT Manager + KPMG Infrastructure Architect | Cooling, power, connectivity; Zebra servers racked | No
88 | 3 | Active Directory Build & User Provisioning | 30 days | 2026-09-28 | 2026-10-28 | 58,84 | KPMG Infrastructure Architect | All 3,500+ users and app access configured | No
89 | 3 | M365 Tenant & Azure Production Build | 25 days | 2026-10-03 | 2026-10-28 | 59,87 | KPMG Infrastructure Architect | 3,500+ mailboxes provisioned; OneDrive structure built | No
90 | 3 | Security & Firewall Implementation | 25 days | 2026-10-08 | 2026-11-02 | 60,84 | KPMG Infrastructure Architect | Security appliances; DLP; endpoint protection | No
91 | 3 | IAM Platform Deployment & User Sync | 25 days | 2026-10-03 | 2026-10-28 | 61,88 | KPMG Infrastructure Architect | SSO, provisioning automation for 3,500+ users | No
92 | 3 | CMDB & ITSM Platform Setup (Assets, CIs) | 20 days | 2026-10-23 | 2026-11-12 | 62,88 | KPMG Infrastructure Architect | Asset inventory; service catalogue; incident management | No
93 | 3 | Telephony Platform Setup & Number Porting (37 sites) | 20 days | 2026-10-28 | 2026-11-17 | 87 | RoboGmbH IT Manager | Phone system config; 4-8 weeks per operator per site | No
94 | 3 | File Share Infrastructure & User Documents | 18 days | 2026-10-23 | 2026-11-10 | 87,89 | KPMG Infrastructure Architect | NAS/Cloud setup for 3,500+ users; shared directories | No
95 | 3 | Backup & Disaster Recovery Setup | 15 days | 2026-11-02 | 2026-11-17 | 87 | KPMG Infrastructure Architect | Backup solution; RTO/RPO targets defined | No
96 | 2 | 3.2 SAP & ERP Development | 70 days | 2026-09-07 | 2026-11-16 | 81 |  | Shell copy, build, interfaces, auth, testing | No
97 | 3 | SAP System Landscape Build (Zebra-specific modules) | 20 days | 2026-09-07 | 2026-09-27 | 64 | KPMG SAP Architect + KPMG SAP Build Lead + RoboGmbH ERP Specialist | Base system build; module activation | No
98 | 3 | SAP Shell Copy Data Extraction & Preparation | 25 days | 2026-09-18 | 2026-10-13 | 97 | KPMG SAP Build Lead + RoboGmbH ERP Specialist | Master data cleanup; extraction from Bosch SAP | No
99 | 3 | Data Migration Dry Run 1 (Test) | 15 days | 2026-09-28 | 2026-10-13 | 98 | KPMG Data Engineer + RoboGmbH ERP Specialist | Extract, transform, load; validation | No
100 | 3 | Data Migration Dry Run 2 (Refinement) | 15 days | 2026-10-13 | 2026-10-28 | 99 | KPMG Data Engineer + RoboGmbH ERP Specialist | Fix issues from Dry Run 1 | No
101 | 3 | SAP Interfaces & Integration Development | 25 days | 2026-10-03 | 2026-10-28 | 66,98 | KPMG SAP Build Lead + KPMG Data Engineer | APIs, EDI mappings, middleware configuration | No
102 | 3 | SAP Authorization & Security Hardening | 15 days | 2026-10-18 | 2026-11-02 | 67,101 | KPMG Infrastructure Architect | User role assignments; access control verification | No
103 | 3 | SAP Test Environment Build (SIT ready) | 20 days | 2026-10-13 | 2026-11-02 | 68,98,101 | KPMG SAP Architect + RoboGmbH ERP Specialist | SIT/UAT environment ready for integration testing | No
104 | 2 | 3.3 Application Migration Preparation (208 apps) | 60 days | 2026-09-07 | 2026-11-06 | 81 |  | Wave packages, custom adaptation, integration test prep | No
105 | 3 | Wave 1 Application Packaging (Critical ~60 apps) | 25 days | 2026-09-07 | 2026-10-02 | 71 | KPMG Data Architect + KPMG Infrastructure Architect | Deployment packages; configuration parameters | No
106 | 3 | Wave 2 Application Packaging (Standard ~80 apps) | 25 days | 2026-09-28 | 2026-10-23 | 70 | KPMG Data Architect + KPMG Infrastructure Architect | packaging during Wave 1 execution prep | No
107 | 3 | Wave 3 Application Packaging (Local/OT ~68 apps) | 20 days | 2026-10-13 | 2026-11-02 | 70 | KPMG Data Architect + KPMG Infrastructure Architect | Regional and OT-specific apps | No
108 | 3 | Custom Application Adaptation for Zebra Environment | 25 days | 2026-09-28 | 2026-10-23 | 72,88 | KPMG Data Architect + RoboGmbH IT Manager | Domain re-point, AD, M365, ITSM integration | No
109 | 3 | Application Integration Development (APIs, Data mapping) | 20 days | 2026-10-08 | 2026-10-28 | 66,101 | KPMG Data Engineer + KPMG SAP Build Lead | Cross-app and SAP integration development | No
110 | 3 | Application Integration Testing Prep | 15 days | 2026-10-23 | 2026-11-07 | 105,108,109 | KPMG Infrastructure Architect + KPMG Test Specialist | Test scenario prep; test data setup | No
111 | 2 | 3.4 Client Workplace, Device & M365 Migration (ALL PRE-GoLive) | 100 days | 2026-09-07 | 2027-05-24 | 81 |  | Device imaging, all 5 migration waves, M365 mailbox migration ALL before QG4 | No
112 | 3 | SCCM / Intune Configuration (Standard image) | 20 days | 2026-09-07 | 2026-09-27 | 74 | KPMG Infrastructure Architect | Device management platform setup | No
113 | 3 | Device Imaging & Standard OS Build | 20 days | 2026-09-18 | 2026-10-08 | 74,112 | KPMG Infrastructure Architect | Standard image production; imaging tooling | No
114 | 3 | Regional Wave Preparation (EMEA / APAC / Americas logistics) | 15 days | 2026-09-28 | 2026-10-13 | 75,113 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Imaging schedule; regional IT team coordination | No
115 | 3 | User Profile & OneDrive Migration Tooling (Setup) | 12 days | 2026-10-13 | 2026-10-25 | 89,113 | KPMG Infrastructure Architect | Migration tools for user data; setup & testing | No
116 | 3 | Device Migration Wave 1 (EMEA hub sites, ~500 devices) | 8 days | 2026-10-18 | 2026-10-26 | 113,114 | KPMG Infrastructure Architect + RoboGmbH IT Manager | First regional wave; EMEA priority (pre-GoLive) | No
117 | 3 | Device Migration Wave 2 (APAC sites, ~700 devices) | 8 days | 2026-10-21 | 2026-10-29 | 114,113 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Parallel with Wave 1; China coordination (pre-GoLive) | No
118 | 3 | Device Migration Wave 3 (EMEA remaining, ~300 devices) | 8 days | 2026-10-26 | 2026-11-03 | 116 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Remaining EMEA sites (pre-GoLive) | No
119 | 3 | Device Migration Wave 4 (Americas, ~500 devices) | 8 days | 2026-10-28 | 2026-11-05 | 117 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Americas sites (pre-GoLive) | No
120 | 3 | Device Migration Wave 5 (Remaining & exceptions, ~400 devices) | 8 days | 2026-11-02 | 2027-05-22 | 118,119 | KPMG Infrastructure Architect | Stragglers, replacements before GoLive (pre-GoLive) | No
121 | 3 | M365 Mailbox & OneDrive Migration (3,500+ users — ALL PRE-GoLive) | 30 days | 2026-10-08 | 2027-05-22 | 89,115 | KPMG Infrastructure Architect | Batched user mailbox & OneDrive migration BEFORE GoLive so users ready Day 1 | No
122 | 2 | 3.5 System Integration Testing & UAT | 50 days | 2026-10-13 | 2027-05-22 | 81 |  | SIT, integration tests, UAT | No
123 | 3 | SAP System Integration Test 1 (SIT1) | 20 days | 2026-10-13 | 2026-11-02 | 103 | KPMG SAP Specialist + KPMG Test Specialist + RoboGmbH ERP Specialist | Integration of apps + SAP; validation | No
124 | 3 | Application Integration Testing (Wave 1 + SAP) | 18 days | 2026-10-23 | 2026-11-10 | 110,123 | KPMG Test Specialist + KPMG Data Architect | End-to-end Wave 1 app integration | No
125 | 3 | User Acceptance Testing (Business owners, 37 sites) | 25 days | 2026-11-02 | 2027-05-17 | 124 | KPMG QA Lead + KPMG Test Specialist + RoboGmbH IT Manager | Sign-off on functional & SAP transactions; regional testers; device reimaging validation | No
126 | 3 | Dress Rehearsal & Cutover Simulation | 8 days | 2027-05-17 | 2027-05-24 | 125 | KPMG Project Manager + KPMG SAP Build Lead + KPMG Test Specialist | Full dry-run with rollback; issue log closeout; migration validation | No
127 | 3 | Ready for QG4 Gate Review | 0 days | 2027-05-24 | 2027-05-24 | 120,121,126 | KPMG PMO Lead | All infrastructure, SAP, apps ready; 3,500 devices reimaged & migrated; 3,500 mailboxes migrated; UAT passed; dress rehearsal successful | Yes
128 | 1 | Phase 4: GoLive & Closure | 60 days | 2027-06-01 | 2027-09-14 | 127 |  | Cutover, hypercare, TSA exit, closure | No
129 | 2 | 4.1 GoLive Day 1 Activities | 7 days | 2027-06-01 | 2027-06-08 | 127 |  | Final data load, cutover execution, activation | No
130 | 3 | Final Data Load & Production Cutover | 3 days | 2027-06-01 | 2027-06-04 | 127 | KPMG Data Engineer + KPMG SAP Build Lead + RoboGmbH ERP Specialist | Final shell copy data load; integrity validation | No
131 | 3 | SAP Go-Live Activation | 2 days | 2027-06-01 | 2027-06-03 | 130 | KPMG SAP Specialist + RoboGmbH ERP Specialist | SAP production activation for Zebra | No
132 | 3 | Application Go-Live Activation (Wave 1, 60 apps) | 2 days | 2027-06-01 | 2027-06-03 | 130 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Apps cut to production; validation | No
133 | 3 | Network & Domain Cutover (All 37 sites) | 2 days | 2027-06-01 | 2027-06-03 | 130 | KPMG Infrastructure Architect + RoboGmbH IT Manager | AD cutover, DNS, WAN routing activation | No
134 | 3 | Help Desk 24x7 Activation | 1 days | 2027-06-01 | 2027-06-01 | 127 | RoboGmbH IT Manager + KPMG Test Specialist | Multi-region support live for 3,500 reimaged+migrated users (all devices ready pre-GoLive) | No
135 | 3 | GoLive Day 1 Milestone | 0 days | 2027-06-01 | 2027-06-01 | 131,132,133 | KPMG PMO Lead + Buyer Sponsor | Zebra business live on independent IT systems (all devices reimaged, all mailboxes migrated PRE-GoLive); TSA support begins | Yes
136 | 2 | 4.2 Hypercare & Stabilization (90 days) | 90 days | 2027-06-02 | 2027-08-30 | 135 |  | 24x7 support, stabilization, issue resolution; NO migrations post-GoLive | No
137 | 3 | Daily Operations Standups & Issue Management | 90 days | 2027-06-02 | 2027-08-30 | 135 | KPMG Project Manager + RoboGmbH IT Manager | Regional EMEA/APAC/Americas standups; P1/P2 hotline | No
138 | 3 | Performance Monitoring & Optimization | 90 days | 2027-06-02 | 2027-08-30 | 135 | KPMG Infrastructure Architect + RoboGmbH IT Manager | System performance tuning; infrastructure adjustments | No
139 | 3 | Data Integrity & Reconciliation (Bosch to Zebra) | 20 days | 2027-06-02 | 2027-06-22 | 135 | KPMG Data Engineer + RoboGmbH ERP Specialist | Verify all data migrated correctly; fix reconciliation items | No
140 | 3 | Issue Backlog & Prioritized Fix List | 60 days | 2027-06-11 | 2027-08-10 | 137 | KPMG Test Specialist + RoboGmbH IT Manager | Capture, prioritize, deploy hotfixes; spans hypercare period | No
141 | 3 | Wave 2 Application Go-Live (80 standard apps) | 5 days | 2027-06-21 | 2027-06-26 | 137 | KPMG Infrastructure Architect | Phased app activation after Wave 1 stabilization | No
142 | 3 | Wave 3 Application Go-Live (68 local/OT apps) | 3 days | 2027-07-21 | 2027-07-24 | 141 | KPMG Infrastructure Architect | Final app activation; OT system go-live within hypercare window | No
143 | 3 | Hypercare Close-Out Sign-Off | 0 days | 2027-08-30 | 2027-08-30 | 137,138,139,140,142 | KPMG PMO Lead + Buyer Sponsor | Hypercare period officially closed (90 days complete); transition to steady state | Yes
144 | 2 | 4.3 TSA Transition & Service Exit | 30 days | 2027-08-31 | 2027-09-30 | 143 |  | TSA service wave exit; handover to Zebra IT (after hypercare closes) | No
145 | 3 | TSA Exit Planning per Service Line | 10 days | 2027-08-31 | 2027-09-10 | 143 | KPMG Project Manager + RoboGmbH IT Manager | Define exit criteria; acceptance tests per service | No
146 | 3 | TSA Infrastructure Services Exit (Wave 1) | 15 days | 2027-09-10 | 2027-09-25 | 145 | KPMG Infrastructure Architect + RoboGmbH IT Manager | Network, data centre, security handoff | No
147 | 3 | TSA Application & ERP Services Exit (Wave 2) | 10 days | 2027-09-19 | 2027-09-29 | 146 | KPMG SAP Specialist + RoboGmbH IT Manager | SAP, apps, integration handoff | No
148 | 3 | TSA Exit Confirmation (Bosch services fully terminated) | 0 days | 2027-09-30 | 2027-09-30 | 147 | KPMG PMO Lead + Buyer Sponsor | All TSA services exited; Zebra IT fully independent | Yes
149 | 2 | 4.4 Programme Closure | 15 days | 2027-08-31 | 2027-09-14 | 143,148 |  | Lessons learned, archive, final sign-off | No
150 | 3 | Lessons Learned Workshop (All regions) | 5 days | 2027-08-31 | 2027-09-05 | 143 | KPMG PMO Lead + All Workstream Leads | Debrief; best practices; challenges documented | No
151 | 3 | Programme Closure Report & Knowledge Transfer | 8 days | 2027-09-06 | 2027-09-13 | 150 | KPMG PMO Lead + KPMG Project Manager | Final report; operational runbooks; team debrief | No
152 | 3 | Financial Reconciliation & Archive | 10 days | 2027-08-31 | 2027-09-10 | 143 | KPMG PMO Lead | Finance closeout; CAPEX/labour final reconciliation | No
153 | 3 | QG5 - Programme Closure Gate | 0 days | 2027-09-14 | 2027-09-14 | 150,151,152,148 | KPMG PMO Lead + Buyer Sponsor | Hypercare closed (90 days); TSA fully exited; Zebra IT independent; programme formally closed | Yes
154 | 2 | Project Completion | 0 days | 2027-09-14 | 2027-09-14 | 153 |  | All artifacts archived; final sign-off | Yes