## Info
Revision history
Document Id | ZBR-RR-20260404
File Name | Zebra_Risk_Register.xlsx
Project Name | Zebra (Packaging Carve-Out)
Project Id | ZBR
Document Owner | KPMG PMO
Review Date | Reviewers |  | Changes
About this template
Risk Category | Select from categories as defined by the Risk Management Plan.
Cause | Specifically what causes the risk to become a realized issue/problem
Effect | What happens if the trigger point occurs
Owner | Risk owner.
Creation date | Date risk identified.
Source | Source of risk.
Impact | Qualitative ranking of impact to project, using scales defined in the Risk Management Plan
Probability | Probability of risk being realized, using scales defined in the Risk Management Plan.
Matrix Score | This is calculated once you select the Impact and Probability.
Qualitative Impact | Space for further description of potential impact.
Quantitative Impact | quantitative / potential risk cost
Risk response strategy | Select from strategies as defined by the Risk Management Plan.
Status | Risk status (e.g. whether it has been triggered or not). You will need to update the values list in cells
Notes | Additional notes.
Template Version | Issue Date | Author | Changes
1.0 | 2023-12-07 | S. Hoehnel | initial template based on V5.2 of the central risk register (S. Wohlfahrt); only examples provided on top

## Risk Register
Risk Register
Risk Identification | [8 empty] | Risk Analysis | [6 empty] | Risk Response Planning |  |  | Risk Monitoring and Control
risk ID | creation date | risk category | cause(s) | event | effect(s) | risk event date | owner | source | impact | prob- ability | threat / opportunity | matrix score | qualitative impact (including period of consideration) | monetary impact [EUR] current year | monetary impact [EUR] three subsequent years | risk response strategy | measure | due date | status | reporting date | impact actual | prob- ability actual | impact (actual) | probability (actual) | matrix score (actual) | notes
1 | 01/04/2026 | Technology, R&D | 37 Packaging sites using shared SAP instance with multiple business units | SAP data separation incomplete or incorrect, affecting Packaging vs other business unit transactions | Post-GoLive data leakage; regulatory exposure; loss of buyer confidence in data integrity | 05/06/2027 | KPMG SAP CoE + RoboGmbH ERP | Formal Risk Review | High | 70% | threat |  |  |  |  | Mitigate | 3x SAP dry-run data extractions; custom ABAP separation logic; independent audit pre-cutover | 15/05/2027 | in progress | 04/04/2026 | High | 70% |  |  |  | Critical path item; 37-site footprint magnifies impact
2 | 01/04/2026 | Technology, R&D | 208 legacy applications with unclear owner responsibility; mixed cloud/on-prem/mainframe | Application transition delay; licensing disputes; integration failures on buyer infrastructure | GoLive delay; operational disruption; additional cost recovery from buyer | 15/05/2027 | KPMG IT Architecture + App Owners | Status Meeting | High | 50% | threat |  |  |  |  | Mitigate | Detailed app portfolio triage by week 8; vendor engagement for license transfer; integration labs | 30/03/2027 | not started | 04/04/2026 | High | 50% |  |  |  | 208 apps is high-complexity.; expect vendor lock-in on 15 - 20 apps
3 | 01/04/2026 | Schedule | 37 geographically distributed sites with varying IT maturity and network readiness | Parallel cutover rollout fails at 1 - 2 sites due to network latency, local infra gaps, or coordination breakdown | Partial GoLive; islands of downtime; customer impact in Packaging operations; regulatory breach if supply-chain systems offline | 20/05/2027 | KPMG Program Manager + RoboGmbH Ops + Buyer Ops | Formal Risk Review | Very High | 50% | threat |  |  |  |  | Mitigate | Site readiness checklist (week 16); network validation by week 12; regional coordinators; rollback playbooks per site | 10/05/2027 | in progress | 04/04/2026 | Very High | 50% |  |  |  | 37-site handover is single highest operational complexity; site variance assessment due week 8
4 | 05/04/2026 | Technology, R&D | Packaging master data (materials, orders, supply-chain records) spans 15 years; data quality varies by source system | Data migration validation reveals anomalies; rework required post-GoLive; inventory/order discrepancies | Hypercare extensions; buyer unable to reconcile; supply-chain disruption; cost overrun | 25/05/2027 | KPMG Data Team + DB Admins | Status Meeting | Moderate | 70% | threat |  |  |  |  | Mitigate | Data audit week 6; transformation rules validated week 12; reconciliation tooling; buyer sign-off pre-cutover | 20/05/2027 | not started | 04/04/2026 | Moderate | 70% |  |  |  | 3500+ users depend on data accuracy; legacy system silos expected
5 | 08/04/2026 | Legal & Compliance | Seller (RoboGmbH) IT and Buyer IT teams not yet aligned on TSA SLAs; hand-off criteria undefined | TSA exit delayed; ambiguous accountability; seller IT unable to wind down Packaging operations on time | Extended TSA costs; vendor lock-in; reputational damage to seller-buyer relationship | 31/05/2027 | KPMG + RoboGmbH Legal + IT + Buyer Legal & IT | Formal Risk Review | High | 30% | threat |  |  |  |  | Mitigate | TSA workstream kickoff week 5; co-define SLA schedule week 8; legal sign-off week 12; exit milestones locked week 16 | 31/03/2027 | in progress | 04/04/2026 | High | 30% |  |  |  | Stand Alone model with TSA; separation of concerns critical
6 | 10/04/2026 | Resources | Buyer IT staffing plan not finalized; infrastructure capacity for 3500+ users unvalidated | Buyer unable to provision network, storage, or compute by GoLive; infrastructure gaps discovered in week 20 | Cutover delay; temporary rehost on seller; additional licensing; buyer penalties | 10/05/2027 | KPMG + Buyer IT Lead + Buyer Infrastructure | Stakeholder | High | 40% | threat |  |  |  |  | Mitigate | Buyer infrastructure audit week 6; capacity plan week 10; resource hiring plan week 8; monthly validation gates | 31/03/2027 | not started | 04/04/2026 | High | 40% |  |  |  | Buyer unknown; limited visibility; critical dependency on buyer execution
7 | 12/04/2026 | Legal & Compliance | Packaging data spans EU + global sites; GDPR, local data residency, export-control rules not yet mapped to new buyer infrastructure | Post-GoLive compliance breach; data residency violation; regulatory fine or injunction | Operational restrictions; forced data replication; supply-chain disruption; reputational risk | 01/06/2027 | KPMG + Information Security + Buyer Legal | Formal Risk Review | Very High | 30% | threat |  |  |  |  | Mitigate | Data classification by week 6; residency rules mapped week 10; buyer infra audit week 12; legal validation week 16 | 20/05/2027 | not started | 04/04/2026 | Very High | 30% |  |  |  | Global footprint (37 sites) = multi-jurisdiction complexity; legal hold may block buyer if unresolved
8 | 15/04/2026 | Schedule | Packaging is revenue-generating business unit; minimal tolerance for downtime; no detailed contingency for extended issues | QG4 (pre-GoLive) escalates due to unresolved critical issues; cutover delayed; business impact | Packaging sales disruption; customer contracts at risk; financial penalty from buyer | 15/05/2027 | KPMG + PMO + RoboGmbH Ops + Buyer Exec | Formal Risk Review | Very High | 20% | threat |  |  |  |  | Mitigate | Business continuity playbook week 10; QG4 criteria locked week 14; dress rehearsal week 18; go/no-go calls daily week 20-22 | 10/05/2027 | not started | 04/04/2026 | Very High | 20% |  |  |  | Packaging revenue sensitivity = commercial risk; escalation path to buyer exec required
9 | 18/04/2026 | Budget | Among 208 apps, 15 - 20 are ISV/SaaS solutions requiring vendor re-licensing or contract renegotiation for new buyer | Vendor re-contract delays; licensing costs spike; buyer refuses cost; cutover blocked; app decommission unplanned | Budget overrun; scope reduction; loss of functionality; go-live delay | 01/05/2027 | KPMG + IT Procurement + Vendor Management | Status Meeting | Moderate | 70% | threat |  |  |  |  | Mitigate | ISV app audit week 5; vendor contact + license check week 8; cost negotiation week 12; buyer approval week 14 | 30/04/2027 | not started | 04/04/2026 | Moderate | 70% |  |  |  | Vendor surprises common in carve-outs; budget TBC if vendors non-cooperative
10 | 20/04/2026 | Resources | Seller IT teams on Packaging systems are stretched across other carve-out projects; buyer hiring lag; knowledge capture informal | Hypercare extended; seller IT unavailable for issue resolution; buyer staff lack Packaging-specific system knowledge | Post-GoLive support costs; issue resolution SLA breaches; staff turnover risk (buyer frustration) | 30/05/2027 | KPMG + Training + Seller IT + Buyer IT | Status Meeting | Moderate | 50% | threat |  |  |  |  | Mitigate | Knowledge audit week 8; train-the-trainer program week 12; documentation frozen week 18; buyers sign-off on readiness week 20 | 25/05/2027 | not started | 04/04/2026 | Moderate | 50% |  |  |  | Buyer unknown; timing of buyer hiring unknown; hypercare cost exposure high
11 | 25/04/2026 | Technology, R&D | 37 sites require persistent network connectivity from buyer infrastructure back to residual RoboGmbH systems (interfaces, shared services) | Network latency or bandwidth bottleneck discovered post-GoLive; interface performance degradation; security audit blocks traffic | Transaction delays; batch job failures; regulatory compliance issue; data breach risk | 10/05/2027 | KPMG + Infrastructure Architect + Information Security + Buyer IT | Formal Risk Review | Moderate | 40% | threat |  |  |  |  | Mitigate | Network design review week 10; DMZ architecture week 12; security validation week 16; load testing week 18 | 01/05/2027 | not started | 04/04/2026 | Moderate | 40% |  |  |  | Stand Alone model = buyer must own network; residual interconnects = operational risk
12 | 28/04/2026 | Schedule | Parallel run duration (2 - 4 weeks) underfunded; business pressure to shorten; dual-system reconciliation unvalidated | Parallel run cut short prematurely; reconciliation gaps undetected; go/no-go decision made on incomplete data | Post-GoLive data inconsistencies; transaction loss in Packaging orders/inventory; buyer escalation | 20/05/2027 | KPMG + PMO + Packaging Operations | Status Meeting | High | 40% | threat |  |  |  |  | Mitigate | Parallel run protocol locked week 14; reconciliation tools validated week 16; daily go/no-go reviews week 20 onwards | 15/05/2027 | not started | 04/04/2026 | High | 40% |  |  |  | Business continuity critical; cutover window = highest-risk period
13 | 30/04/2026 | Stakeholder Relations & Public Affairs | 3500+ Packaging users across 37 sites; limited change readiness; some sites in low-maturity markets | User error spike post-GoLive; helpdesk overwhelmed; low adoption; workarounds undermine controls | Support overrun; hidden business process failures; regulatory exposure (if controls bypassed); staff retention risk | 25/05/2027 | KPMG + Training + Buyer Change Manager + Packaging Leadership | Stakeholder | Moderate | 60% | threat |  |  |  |  | Mitigate | Change readiness assessment week 6; communications plan week 8; train-the-trainer week 12; site-level kick-offs week 19 | 20/05/2027 | not started | 04/04/2026 | Moderate | 60% |  |  |  | 3500+ users = change management complexity; low-maturity sites = higher risk
14 | 02/05/2026 | Legal & Compliance | Buyer legally confidential; legal team blocking normal governance cadence; buyer exec visibility limited; buyer IT access delayed | Project decisions delayed; buyer IT prep incomplete; confidentiality breach if buyer details leak | Shortened runway for buyer ramp-up; QG4 risks escalate; GoLive delay | 10/05/2027 | KPMG + RoboGmbH Legal + Project Manager | Formal Risk Review | Moderate | 30% | threat |  |  |  |  | Accept | Confidentiality structure established week 1; buyer IT point-of-contact assigned week 3; encrypted comms from week 3 | 15/04/2026 | implemented | 04/04/2026 | Moderate | 30% |  |  |  | Buyer unknown until deal finalized; accept legal risk as project constraint
15 | 05/05/2026 | Budget | Seller running SAP on extended support; buyer must plan upgrade; upgrade path for Packaging suite unclear | Buyer inherits unsupported SAP version; licensing disputes; emergency upgrade required 6 - 12 months post-GoLive | Unplanned SAP upgrade cost; operational disruption 6 - 12 months post-GoLive; buyer cost recovery claim | 30/05/2027 | KPMG + SAP CoE + RoboGmbH ERP + Buyer ERP Lead | Formal Risk Review | Moderate | 50% | threat |  |  |  |  | Mitigate | SAP roadmap finalized week 8; upgrade decision locked week 12; buyer agrees to roadmap week 14 | 30/04/2027 | not started | 04/04/2026 | Moderate | 50% |  |  |  | Seller may shift upgrade burden to buyer; contractual clarity essential
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
Insert Rows Above This Line Only
Warning: Be careful adding/removing rows in the following section - these values are used for data validation
Risk Category
Technology, R&D
Engineering
Manufacturing
Quality
Strategy & Portfolio
Budget
Schedule
Resources
Supply Chain
Market & Competitors
Customers
Raw Materials
Stakeholder Relations & Public Affairs
Intellectual Property
Legal & Compliance
Ecosystems & Ethics
Security & Data Protection
Risk Source
Formal Risk Review
SQA Audit/Review
Status Meeting
Stakeholder
Other
Impact Values
|  | Very Low | 0.05
|  | Low | 0.1
|  | Moderate | 0.2
|  | High | 0.4
|  | Very High | 0.8
Probability Values
|  | 10% | 0.1
|  | 30% | 0.3
|  | 50% | 0.5
|  | 70% | 0.7
|  | 90% | 0.9
Green/Yellow/Red Threshold Values
|  | Green - maximum score | 0.05
|  | Yellow - minimum score | 0.06
|  | Yellow - maximum score | 0.14
|  | Red - minimum score | 0.15
Risk Strategy
Avoid
Transfer
Mitigate
Accept
Exploit
Enhance
Share
Status
not started
in progress
on hold
implemented
cancelled
Note on E4: Which issues could lead to the risk event?
Note on F4: When exactly does a threat become a problem repectively an opportunity become an occasion?
Note on G4: What would be the consequences?
Note on H4: If the risk event can be linked to an exact or latest date.

## Matrix
Risk Register | [14 empty] | Matrix (initial) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS | [52 empty] | Matrix (actual) Data Calculation - DO NOT DELETE, MOVE OR INSERT CELLS
Probability & Impact Matrix (initial)
Probability |  | Threats |  |  |  |  | Opportunities | [9 empty] | Green/Yellow/Red Threshold Values | [52 empty] | Green/Yellow/Red Threshold Values
| 0.9 | [16 empty] | Green - maximum score |  |  | 0.05 | [49 empty] | Green - maximum score |  |  | 0.05
| 0.7 | [16 empty] | Yellow - minimum score |  |  | 0.06 | [49 empty] | Yellow - minimum score |  |  | 0.06
| 0.5 | [16 empty] | Yellow - maximum score |  |  | 0.14 | [49 empty] | Yellow - maximum score |  |  | 0.14
| 0.3 | [16 empty] | Red - minimum score |  |  | 0.15 | [49 empty] | Red - minimum score |  |  | 0.15
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
Impact
Probability & Impact Matrix (actual)
Probability |  | Threats |  |  |  |  | Opportunities
0.9
0.7
0.5
0.3
0.1
| 0 | very low | low | medium | high | very high | very high | high | medium | low | very low
|  | Impact | [15 empty] | P-I # threat | [24 empty] | P-I # opportunity | [27 empty] | P-I # threat | [24 empty] | P-I # opportunity
[18 empty] | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 |  |  |  | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 3-1 | 3-2 | 3-3 | 3-4 | 3-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5 | 4-1 | 4-2 | 4-3 | 4-4 | 4-5
|  | Risk ID | Risk Category |  | Matrix Score | Threat / Opportunity | quantitative impact [€] | risk strategy | owner | reporting date | status | Cause | Effect | Matrix Score (actual) | Impact | Probability | [51 empty] | Impact (actual) | Probability (actual)
END OF MATRIX DATA (max 130 records)
Impact Values
| Very Low | 0.05
| Low | 0.1
| Moderate | 0.2
| High | 0.4
| Very High | 0.8
Probability Values
| Very Low | 0.1
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very High | 0.9
Green/Yellow/Red Threshold Values
| Green - maximum score | 0.05
| Yellow - minimum score | 0.06
| Yellow - maximum score | 0.14
| Red - minimum score | 0.15