## Slide 1: Project Bravo
Management Stakeholder Update
BGSW AI Business Carve-Out into 50/50 JV with Tata
Report Date: 04 Apr 2026

## Slide 2: Executive Summary
Status: On track for Day 1 GoLive on 01 Jul 2026
Scope: 17 AI applications, 70 users, 2 India sites.
Model benefits: no TSA, no Merger Zone, no antitrust filing.
Baseline: EUR 554K labour budget, CAPEX decision at QG0.
SteerCo focus: legal entity timing and Jun build resourcing.
Project Bravo | Combination model with Bosch leadership control
GoLive
01 Jul 2026
SPI
1.00
CPI
1.00

## Slide 3: Scope and Carve-Out Model
In scope: AI app wave, users/devices, cloud/identity/network/security
17 AI applications in one migration wave
70 users and device transition to JV standards
JV AD forest, M365 tenant, Azure setup across 2 India sites
No ERP in scope and no TSA required after GoLive
What is in scope and why execution risk is lower
Applications
17
Users
70
Sites
2

## Slide 4: Timeline and Quality Gates
April to October 2026 plan with mandatory gate control
QG0
30 Apr
QG1/2/3
26 Jun
GoLive
01 Jul
QG4
02 Jul
QG5
30 Oct
Key milestones: QG0 (30 Apr) → QG1/2/3 combined (26 Jun) → GoLive (01 Jul) and QG4 (02 Jul) → QG5 (30 Oct)
QG4 Pre-GoLive gate must be cleared before Day 1 operations commence on 01 Jul 2026

## Slide 5: KPI and Readiness Snapshot
SPI 1.00 and CPI 1.00: on plan
Apps migrated: 0/17 (migration planned in June)
Open risks: 3 amber | Critical issues: 0
High confidence: PMO, Infra, Security, Workplace
Medium confidence: Legal setup, Data separation, Licensing
Control metrics and confidence by workstream
Open Risks
3 Amber
Critical Issues
0
Readiness
On Plan

## Slide 6: Budget View
Labour baseline: EUR 554K | CAPEX: TBC at QG0
Top cost buckets: Programme Mgmt, IT PM, Hypercare
Infrastructure and app migration costs within plan
Contingency reserve available for transition volatility
No budget overrun indicators at current stage
Labour baseline and major cost buckets
Labour
EUR 554K
CAPEX
TBC QG0
Reserve
EUR 83K

## Slide 7: Top Risks and Mitigations
R1 Bandwidth constraints Apr-Jun (score 16, amber)
R3 Licensing cost pressure (score 9, amber)
R5 Key IT staff availability in June (score 12, amber)
Mitigations active: resource protection, quote lock, staffing backup
Weekly escalation in PMO governance
Active amber risks and mitigation status
R1
16
R5
12
Review
Weekly

## Slide 8: Management Decisions Required
Approve CAPEX envelope at QG0
Confirm Tata-side IT staffing for May architecture workshops
Approve June critical resource protection plan
Support legal escalation for JV entity registration timeline
Maintain weekly executive checkpoint cadence to GoLive
Steering actions requested this month
Decisions
4
Owner
SteerCo
Cadence
Weekly