## Cost Plan
PROJECT BRAVO — IT Cost Plan (Labour Only)
CATEGORY / TASK | RESOURCE | TOTAL DAYS | TOTAL HRS | RATE (EUR/hr) | TOTAL COST (EUR)
Based on: | Bravo_Project_Schedule.xlsx
Risk-aligned: | Bravo_Risk_Register.xlsx
Project: | Bravo ¦ Seller: Bosch BGSW ¦ Buyer: Tata
PM: | Riyaz Ahmed Syed Ahmed (BD/MIL-PSM4)
Sites / Users / Apps: | 2 (India) ¦ 70 users ¦ 17 apps ¦ No ERP ¦ No TSA
Duration: | 01 Apr 2026 – 30 Oct 2026 (7 months)
Budget Baseline: | TBC - to be approved at QG0
PROGRAMME MANAGEMENT
Programme Management | Riyaz Ahmed (BD/MIL-PSM4) | 85 | 680 | 175 | 119000
PMO Coordination | PMO + Riyaz Ahmed | 30 | 240 | 100 | 24000
Steering Committee Facilitation | Riyaz Ahmed | 15 | 120 | 175 | 21000
SUBTOTAL — PROGRAMME MANAGEMENT |  | 130 | 1040 |  | 164000
IT PROJECT MANAGEMENT
IT Project Management | BGSW IT PM | 85 | 680 | 120 | 81600
Workstream Coordination | WS Leads | 40 | 320 | 100 | 32000
SUBTOTAL — IT PROJECT MANAGEMENT |  | 125 | 1000 |  | 113600
INFRASTRUCTURE & CLOUD
Active Directory Build (JV Forest) | BGSW AD Team | 15 | 120 | 110 | 13200
M365 Tenant & Azure Setup | BGSW Azure Team | 15 | 120 | 110 | 13200
Network Setup (2 India Sites) | BGSW Infra | 15 | 120 | 100 | 12000
Security & IAM Platform | BGSW CISO | 12 | 96 | 120 | 11520
Cloud Environment Configuration | BGSW Cloud Team | 10 | 80 | 110 | 8800
SUBTOTAL — INFRASTRUCTURE & CLOUD |  | 67 | 536 |  | 58720
APPLICATION MIGRATION
Application Deep-Dive & Classification (17 apps) | BGSW IT Architects | 15 | 120 | 110 | 13200
Application Reconfiguration for JV (17 apps) | Dev Teams | 20 | 160 | 100 | 16000
Integration & UAT Testing (17 apps) | App Teams + Test Team | 15 | 120 | 90 | 10800
Data Migration Execution | BGSW IT + Riyaz Ahmed | 12 | 96 | 100 | 9600
License & Contract Review (17 apps) | BGSW Procurement + IT | 12 | 96 | 90 | 8640
SUBTOTAL — APPLICATION MIGRATION |  | 74 | 592 |  | 58240
CLIENT WORKPLACE
Device Inventory & Assessment (70 devices) | BGSW IT + Asset Mgmt | 5 | 40 | 90 | 3600
Device Reimaging - JV Standard Image (70 devices) | BGSW CWP | 10 | 80 | 90 | 7200
Help Desk Activation & Training | IT Ops | 5 | 40 | 90 | 3600
SUBTOTAL — CLIENT WORKPLACE |  | 20 | 160 |  | 14400
ARCHITECTURE & DESIGN
As-Is Analysis & Architecture Design | BGSW IT Architects | 20 | 160 | 120 | 19200
JV Architecture Workshop Facilitation | BGSW + Tata Architects | 5 | 40 | 120 | 4800
Security Architecture Design | BGSW CISO | 8 | 64 | 120 | 7680
SUBTOTAL — ARCHITECTURE & DESIGN |  | 33 | 264 |  | 31680
LEGAL & COMPLIANCE
JV Legal Entity Setup (India) | Legal + Finance | 10 | 80 | 150 | 12000
Contract & Data Separation Review | Legal + Riyaz Ahmed | 10 | 80 | 150 | 12000
SUBTOTAL — LEGAL & COMPLIANCE |  | 20 | 160 |  | 24000
HR IT
HR IT Mapping (70 Users) | BGSW HR IT | 5 | 40 | 90 | 3600
SUBTOTAL — HR IT |  | 5 | 40 |  | 3600
HYPERCARE & CLOSURE
Hypercare Operations (60 working days) | IT Ops + Help Desk | 60 | 480 | 90 | 43200
Application Stability Monitoring (17 apps) | App Teams + IT Ops | 30 | 240 | 90 | 21600
Programme Closure | Riyaz Ahmed + Bosch BD/MIL | 15 | 120 | 175 | 21000
SUBTOTAL — HYPERCARE & CLOSURE |  | 105 | 840 |  | 85800
OVERALL PROJECT TOTAL (LABOUR ONLY) |  | 579 | 4632 |  | 554040
COST BREAKDOWN BY CATEGORY
PROGRAMME MANAGEMENT |  |  |  |  | 164000
IT PROJECT MANAGEMENT |  |  |  |  | 113600
INFRASTRUCTURE & CLOUD |  |  |  |  | 58720
APPLICATION MIGRATION |  |  |  |  | 58240
CLIENT WORKPLACE |  |  |  |  | 14400
ARCHITECTURE & DESIGN |  |  |  |  | 31680
LEGAL & COMPLIANCE |  |  |  |  | 24000
HR IT |  |  |  |  | 3600
HYPERCARE & CLOSURE |  |  |  |  | 85800
TOTAL LABOUR |  |  |  |  | 554040
COST BREAKDOWN BY PHASE
Phase 0 - Initialization (01 Apr – 30 Apr 2026) |  |  |  |  | 55000
Phase 1 - Concept (01 May – 15 May 2026) |  |  |  |  | 38000
Phase 2 - Architecture & Design (11 May – 29 May 2026) |  |  |  |  | 72000
Phase 3 - Build and Test (01 Jun – 26 Jun 2026) |  |  |  |  | 165000
Phase 4 - GoLive & Closure (29 Jun – 30 Oct 2026) |  |  |  |  | 224040
TOTAL LABOUR |  |  |  |  | 554040
CAPEX / ADDITIONAL COSTS (excluded from labour total)
ITEM | OWNER | ESTIMATE / NOTE
M365/Azure JV Tenant Licensing (<70 users) | BGSW Procurement | TBC - to be confirmed at QG0
India Cloud Infrastructure (2 sites) | BGSW Cloud Team | TBC - to be confirmed at QG0
Network Circuit Setup (2 India JV Sites) | BGSW Infra | TBC - to be confirmed at QG0
Device Hardware Replacement if required (≤70 devices) | BGSW CWP | TBC - to be confirmed at QG0
Risk Contingency (Risk #1 - schedule risk) | See Risk Register | 15% of labour = EUR 83,106
Risk Contingency (Risk #3 - cloud cost overrun) | See Risk Register | EUR 15,000 reserved
NOTES
• All figures are labour-only estimates; hardware, licensing, WAN, and cloud subscription costs are excluded from the labour total.
• CAPEX items (M365, Azure, networking) to be formally quoted and approved at QG0 SteerCo.
• Risk contingency lines derived from Bravo_Risk_Register.xlsx: Risk #1 (Amber; P4xI4=16) and Risk #3 (Amber; P3xI3=9).
• No TSA cost provision required: Bosch-led JV; BGSW services available via normal governance channels post-GoLive.
• Budget baseline state: TBC - to be approved at QG0 (30 Apr 2026).