## Project Schedule
ID | Outline Level | Name | Duration | Start | Finish | Predecessors | Resource Names | Notes | Milestone
1 | 1 | Phase 0 - Initialization | 22 days | 04/01/26 | 04/30/26 |  | Riyaz Ahmed + BGSW IT |  | No
2 | 2 | 0.1 Project Setup and Governance | 8 days | 04/01/26 | 04/10/26 |  | Riyaz Ahmed |  | No
3 | 3 | Appoint Bravo Programme Leads (BGSW and JV-Tata) | 3 days | 04/01/26 | 04/03/26 |  | BGSW CIO + Riyaz Ahmed |  | No
4 | 3 | Establish Bravo Steering Committee | 3 days | 04/01/26 | 04/03/26 | 3 | BGSW + Tata Senior Mgmt |  | No
5 | 3 | Define RACI and Governance Model | 5 days | 04/06/26 | 04/10/26 | 3 | Riyaz Ahmed |  | No
6 | 3 | Set Up PMO Tools and Collaboration Site | 5 days | 04/06/26 | 04/10/26 | 4 | PMO + Riyaz Ahmed |  | No
7 | 2 | Signing - Frozen Zone Activated | 0 days | 04/07/26 | 04/07/26 | 3 | BGSW + Tata Executive | No AI IT production changes without SteerCo approval from this date | Yes
8 | 2 | 0.2 BGSW AI IT Landscape Assessment (2 India Sites) | 15 days | 04/06/26 | 04/24/26 | 3 | BGSW IT + Riyaz Ahmed | 2 India sites | No
9 | 3 | AI IT Inventory (17 Apps / 70 Users / 2 Sites) | 5 days | 04/06/26 | 04/10/26 | 5 | BGSW IT PM | 17 AI apps; 70 users; 2 India sites; no ERP; no SAP | No
10 | 3 | Location Confirmation - 2 India Sites | 5 days | 04/06/26 | 04/10/26 | 5 | BGSW IT + Facilities |  | No
11 | 3 | JV Legal Entity Preparation (India MCA Registration) | 10 days | 04/13/26 | 04/24/26 | 9 | Legal + Finance | 50/50 Tata-Bosch JV; Bosch leadership control; not antitrust relevant; no regulatory filing required | No
12 | 3 | Identify AI IT Dependencies on BGSW Shared Services | 10 days | 04/13/26 | 04/24/26 | 9 | BGSW IT Architects | Minimal dependencies; Bosch-led JV remains closely aligned with BGSW operations post-GoLive | No
13 | 2 | 0.3 Scope Definition and Charter | 10 days | 04/13/26 | 04/24/26 | 8 | Riyaz Ahmed |  | No
14 | 3 | Define Scope - 17 AI Apps, 70 Users, 2 India Sites | 5 days | 04/13/26 | 04/17/26 | 8 | Riyaz Ahmed + BGSW IT | No ERP; No SAP; No TSA post-GoLive; Bosch-led JV; Combination model | No
15 | 3 | JV Operating Framework Confirmation | 5 days | 04/13/26 | 04/17/26 | 8 | Riyaz Ahmed + Legal | Bosch leadership control; 50/50 JV with Tata; not antitrust relevant; JV continues under Bosch governance | No
16 | 3 | Project Charter Draft and Approval | 5 days | 04/20/26 | 04/24/26 | 14,15 | Riyaz Ahmed |  | No
17 | 2 | QG0 - Initialization Quality Gate | 0 days | 04/30/26 | 04/30/26 | 12,16 | Steering Committee | Charter approved; inventory confirmed (17 apps, 70 users, 2 India sites); JV governance agreed; proceed to Concept | Yes
18 | 1 | Phase 1 - Concept | 11 days | 05/01/26 | 05/15/26 | 17 | BGSW IT + Riyaz Ahmed |  | No
19 | 2 | 1.1 As-Is Analysis | 11 days | 05/01/26 | 05/15/26 | 17 | BGSW IT + Riyaz Ahmed |  | No
20 | 3 | Application Deep-Dive - 17 AI Apps | 8 days | 05/01/26 | 05/12/26 | 17 | BGSW IT Architects | Classify all 17 apps: retain in JV / retire / re-host; no ERP or SAP in scope | No
21 | 3 | IT Infrastructure Mapping - 2 India Sites | 5 days | 05/01/26 | 05/07/26 | 17 | BGSW Infra Team |  | No
22 | 3 | Data Ownership and Separation Rules | 5 days | 05/04/26 | 05/08/26 | 17 | Riyaz Ahmed + Legal | AI data vs BGSW corporate data; simplified by Bosch JV leadership | No
23 | 3 | Contract and Licence Review - 17 AI Apps | 8 days | 05/01/26 | 05/12/26 | 17 | BGSW Procurement + IT | Change-of-control clause review for all 17 AI applications | No
24 | 3 | HR IT Mapping - 70 AI Business Users | 5 days | 05/01/26 | 05/07/26 | 17 | BGSW HR IT | India payroll and HR for 70 users across 2 India sites | No
25 | 1 | Phase 2 - Architecture and Design | 15 days | 05/11/26 | 05/29/26 | 20 | BGSW IT Architects + Riyaz Ahmed |  | No
26 | 2 | 2.1 JV IT Architecture Design | 15 days | 05/11/26 | 05/29/26 | 20 | BGSW IT Architects + Riyaz Ahmed |  | No
27 | 3 | JV Architecture Workshop (Combination Model) | 3 days | 05/11/26 | 05/13/26 | 20 | BGSW + Tata Architects | Confirms Combination JV model; Bosch leadership; JV IT target state defined | No
28 | 3 | M365 and Azure Tenant Design - JV Entity (<70 Mailboxes) | 7 days | 05/14/26 | 05/22/26 | 27 | BGSW Azure Team | New M365 tenant; <70 mailboxes; Teams and OneDrive in scope | No
29 | 3 | Active Directory Design - JV Forest | 7 days | 05/14/26 | 05/22/26 | 27 | BGSW AD Team | New AD forest for JV; fully separate from BGSW corporate AD | No
30 | 3 | Network Architecture - 2 India JV Sites | 7 days | 05/14/26 | 05/22/26 | 27 | BGSW Infra | Domestic India connectivity across 2 JV sites; no international WAN required | No
31 | 3 | Security Architecture - JV Entity | 5 days | 05/25/26 | 05/29/26 | 29,30 | BGSW CISO | JV security independent of BGSW; ISO 27001 baseline; Bosch security standards retained | No
32 | 2 | 2.2 Migration Strategy and Planning Baseline | 15 days | 05/11/26 | 05/29/26 | 20 | Riyaz Ahmed + WS Leads |  | No
33 | 3 | Application Migration Plan - 17 Apps (Single Wave) | 7 days | 05/11/26 | 05/19/26 | 20 | Riyaz Ahmed + WS Leads | Single wave; all 17 apps; Bosch-led JV simplifies target endpoint configuration | No
34 | 3 | Data Migration Plan | 7 days | 05/11/26 | 05/19/26 | 22 | Riyaz Ahmed + BGSW IT |  | No
35 | 3 | Detailed Project Plan and Budget Baseline | 5 days | 05/25/26 | 05/29/26 | 33 | Riyaz Ahmed + Finance |  | No
36 | 3 | Risk Register Baseline | 5 days | 05/25/26 | 05/29/26 | 33 | Riyaz Ahmed + WS Leads |  | No
37 | 1 | Phase 3 - Build and Test | 20 days | 06/01/26 | 06/26/26 | 35,36 | All Workstreams |  | No
38 | 2 | 3.1 JV IT Infrastructure Build | 18 days | 06/01/26 | 06/24/26 | 36 | BGSW Infra + Partners |  | No
39 | 3 | M365 Tenant Provisioning (<70 Mailboxes) | 5 days | 06/01/26 | 06/05/26 | 36 | BGSW Azure Team |  | No
40 | 3 | Azure and Cloud Environment Setup - JV | 7 days | 06/08/26 | 06/16/26 | 39 | BGSW Cloud Team |  | No
41 | 3 | Active Directory Build - JV Forest | 10 days | 06/01/26 | 06/12/26 | 36 | BGSW AD Team | Foundation for all 70 JV users and 17 AI applications; no backout possible | No
42 | 3 | Network Setup - 2 India JV Sites | 10 days | 06/01/26 | 06/12/26 | 36 | BGSW Infra |  | No
43 | 3 | Security and IAM Platform Setup - JV | 8 days | 06/11/26 | 06/22/26 | 41,42 | BGSW CISO |  | No
44 | 2 | 3.2 Application Migration - 17 AI Apps (Single Wave) | 18 days | 06/01/26 | 06/24/26 | 36 | Dev Teams + BGSW IT |  | No
45 | 3 | Application Reconfiguration for JV - 17 Apps | 12 days | 06/01/26 | 06/16/26 | 36 | Dev Teams | Re-point 17 apps from BGSW to JV AD / M365 / Azure; Bosch-led JV simplifies target configuration | No
46 | 3 | Data Migration Execution | 8 days | 06/11/26 | 06/22/26 | 45 | BGSW IT + Riyaz Ahmed |  | No
47 | 2 | 3.3 Device Migration - 70 Devices (2 India Sites) | 10 days | 06/15/26 | 06/26/26 | 41 | BGSW CWP Team |  | No
48 | 3 | Device Inventory and Assessment - 70 Devices | 3 days | 06/15/26 | 06/17/26 | 41 | BGSW IT + Asset Mgmt |  | No
49 | 3 | Device Reimaging - JV Standard Image (70 Devices) | 7 days | 06/18/26 | 06/26/26 | 48 | BGSW CWP | JV domain image across 2 India sites | No
50 | 2 | 3.4 Testing and Validation | 10 days | 06/15/26 | 06/26/26 | 44 | Test Team + Business |  | No
51 | 3 | Integration Testing - All 17 AI Applications | 7 days | 06/15/26 | 06/23/26 | 45 | App Teams + Test Team |  | No
52 | 3 | User Acceptance Testing (UAT) - 70 Users | 5 days | 06/18/26 | 06/24/26 | 51 | Business Key Users | JV AI business users confirm Day 1 readiness across 2 India sites | No
53 | 3 | Security and Penetration Testing - JV Environment | 5 days | 06/15/26 | 06/19/26 | 43 | BGSW CISO |  | No
54 | 2 | UAT Sign-Off | 0 days | 06/24/26 | 06/24/26 | 52 | Business Leads + Riyaz Ahmed |  | Yes
55 | 2 | QG1/2/3 - Combined Quality Gate (Concept + Architecture + Build) | 0 days | 06/26/26 | 06/26/26 | 49,53,54 | Steering Committee | Architecture approved; all 17 apps reconfigured and tested; 70 devices configured; UAT passed; proceed to GoLive preparation | Yes
56 | 1 | Phase 4 - GoLive and Closure | 89 days | 06/29/26 | 10/30/26 | 55 | All Workstreams |  | No
57 | 2 | 4.1 Pre-GoLive Preparation | 2 days | 06/29/26 | 06/30/26 | 55 | Riyaz Ahmed + WS Leads |  | No
58 | 3 | Cutover Plan Finalisation and Go No-Go Assessment | 1 days | 06/29/26 | 06/29/26 | 55 | All WS Leads + Riyaz Ahmed |  | No
59 | 3 | Help Desk Activation and Training - JV | 2 days | 06/29/26 | 06/30/26 | 55 | IT Ops | India support coverage for 70 JV AI users across 2 sites ready before GoLive | No
60 | 3 | End-User Pre-GoLive Communication - 70 AI Business Users | 1 days | 06/29/26 | 06/29/26 | 55 | Comms + BGSW IT | Pre-GoLive communication to all 70 AI users across 2 India sites | No
61 | 2 | QG4 - Pre-GoLive Quality Gate | 0 days | 06/30/26 | 06/30/26 | 58,59,60 | Steering Committee | Cutover plan approved; all 17 apps ready; 70 users and devices ready; JV infra stable; DAY 1 GOLIVE AUTHORISED | Yes
62 | 2 | 4.2 Day 1 GoLive | 1 days | 07/01/26 | 07/01/26 | 61 | All Workstreams | GoLive proceeds only after QG4 passed on 30 Jun 2026 | No
63 | 3 | Day 1 - JV IT GoLive (Legal Separation Effective) | 0 days | 07/01/26 | 07/01/26 | 61 | Executive Leadership | Bosch-led JV AI IT fully separated from BGSW; JV IT independent from this date; no TSA required | Yes
64 | 3 | Network Domain Cutover to JV Active Directory | 1 days | 07/01/26 | 07/01/26 | 63 | BGSW Infra |  | No
65 | 3 | Application Day 1 Activation - All 17 AI Apps | 1 days | 07/01/26 | 07/01/26 | 63 | App Teams |  | No
66 | 3 | User Go-Live Communication - 70 AI Business Users | 1 days | 07/01/26 | 07/01/26 | 63 | Comms + BGSW IT |  | No
67 | 2 | 4.3 Hypercare - 60 Working Days | 60 days | 07/06/26 | 09/25/26 | 62 | WS Leads + IT Ops |  | No
68 | 3 | Daily Operations Review Meetings | 60 days | 07/06/26 | 09/25/26 | 62 | Riyaz Ahmed + WS Leads | India standup cadence; JV AI systems stability; Bosch-led escalation path available | No
69 | 3 | Incident Management and P1/P2 Resolution | 60 days | 07/06/26 | 09/25/26 | 62 | IT Ops + Help Desk |  | No
70 | 3 | Application Stability Monitoring - 17 Apps | 60 days | 07/06/26 | 09/25/26 | 62 | App Teams + IT Ops | No TSA; JV Bosch-led; escalation via normal BGSW governance channels | No
71 | 2 | Hypercare Close - Formal Sign-Off | 0 days | 09/25/26 | 09/25/26 | 68,69,70 | Steering Committee |  | Yes
72 | 2 | 4.4 Programme Closure | 25 days | 09/28/26 | 10/30/26 | 71 | Riyaz Ahmed + Bosch BD/MIL |  | No
73 | 3 | Lessons Learned Workshop | 3 days | 09/28/26 | 09/30/26 | 71 | All WS Leads |  | No
74 | 3 | Final Financial Reconciliation | 5 days | 09/28/26 | 10/02/26 | 71 | Finance + Riyaz Ahmed |  | No
75 | 3 | Programme Closure Report | 10 days | 10/05/26 | 10/16/26 | 73 | Riyaz Ahmed + Bosch BD/MIL |  | No
76 | 3 | Final Programme Sign-Off | 0 days | 10/16/26 | 10/16/26 | 75,74 | Executive Leadership |  | Yes
77 | 2 | QG5 - Programme Closure Quality Gate | 0 days | 10/30/26 | 10/30/26 | 76 | Steering Committee | Hypercare stable; JV IT fully operational under Bosch governance; all 17 apps stable; Project Bravo formally closed | Yes