## Shopping_List_Vorbereitung
FRAME - License Shopping List
Status 06.06.2025
#1 | Vendor | Product | Date for priority availability (otherwise procurement by 30.06) | Reason for request for priority availability | Changes since February 28, 2025 | Changes out of "locally managed list" | Type | Quantity | Metric | Ready for Procurement | License Server planned? | Comment | Comment 2 | Action | Responsible | Due Date
1 | 3E | SAP "MaCS" (PT3) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_69430
n/a | Adobe | Acrobat Prof |  |  |  |  | Subscription | 125 | User | n/a
n/a | Adobe | Acrobat Standard incl. FRL |  |  |  |  | Subscription | 1044 | User | n/a
n/a | Adobe | After Effects |  |  |  |  | Subscription | 39 | User | n/a
n/a | Adobe | Animate |  |  |  |  | Subscription | 2 | User | n/a
n/a | Adobe | Audition |  |  |  |  | Subscription | 6 | User | n/a
n/a | Adobe | Bridge |  |  |  |  | Subscription | 33 | User | n/a
n/a | Adobe | Character Animator |  |  |  |  | Subscription | 2 | User | n/a
n/a | Adobe | Creative Cloud (all apps) incl FRL |  |  |  |  | Subscription | no longer relevant | User | n/a
n/a | Adobe | Dreamweaver |  |  |  |  | Subscription | 5 | User | n/a
n/a | Adobe | Illustrator |  |  |  |  | Subscription | 52 | User | n/a
n/a | Adobe | Incopy |  |  |  |  | Subscription | 2 | User | n/a
n/a | Adobe | Indesign |  |  |  |  | Subscription | 21 | User | n/a
n/a | Adobe | Lightroom Classic |  |  |  |  | Subscription | 3 | User | n/a
n/a | Adobe | Media Encoder |  |  |  |  | Subscription | 38 | User | n/a
n/a | Adobe | Photoshop |  |  |  |  | Subscription | 46 | User | n/a
n/a | Adobe | Photoshop Elements |  |  |  |  | Subscription | 3 | User | n/a
n/a | Adobe | Premiere Elements |  |  |  |  | Subscription | 11 | User | n/a
n/a | Adobe | Premiere Pro |  |  |  |  | Subscription | 13 | User | n/a
2 | Adobe | Technical Communication Suite |  |  |  |  | Subscription | 1 | User | y
n/a | Adobe | Acrobat XD |  |  |  |  | Subscription | 3 | User | n/a
2 | Adobe | Acrobat Pro |  |  |  |  | Subscription | 74 | User | y
2 | Adobe | Acrobat Std |  |  |  |  | Subscription | 807 | User | y
2 | Adobe | Single App |  |  | 2025-05-14 |  | Subscription | 22 | User | y |  | 14.05.2025 Quanity lowered from 24 to 22
2 | Adobe | All Apps |  |  |  |  | Subscription | 46 | User | y
3 | AEB | AEB Carrier Connect | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_27560
3 | AEB | ConnectShip | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_55189
3 | AEB | GTS - Global Trade Services (P94) 11.0 | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_52878
3 | AEB | ShipExec | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_65111
3 | AEB | Helios | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_71156
3 | AEB | TANGO | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_64815
3 | AEB | Traco | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_47196
3 | AEB | CarrierConnect | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_18084
n/a | Aleph | Aleph |  |  | 2025-04-30 | x |  | 1 (user name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
5 | Alteryx | Designer 2023 Desktop |  |  |  |  | Subcription | 6 | User | n |  | 30.04: Still in clarification, most likely to be discontinued | Upade 30.04.25: see Email from Andreas Baur to Karl-Heinz Jansen (BT/BDO-DO-ST) - no feedback from Karl-Heinz Jansen
5 | Alteryx | Server |  |  |  |  | Subcription | 1 | Server | n |  | 30.04: Still in clarification, most likely to be discontinued | Upade 30.04.25: see Email from Andreas Baur to Karl-Heinz Jansen (BT/BDO-DO-ST) - no feedback from Karl-Heinz Jansen
6 | Altium | Viewer | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 2 | User | y | WS04a ¦ Altium Infrastructrue Server (AIS)
6 | Altium | Designer Enterprise | 22.06.2025 | Set Up Licence Server | 2025-05-14 |  | Subscription | 8 | User | y | WS04a ¦ Altium Infrastructrue Server (AIS) | 29.04.2025 Enterprise Edition, 14.05.2025 Quantity adjusted
7 | Amazon | AWS | [6 empty] | Pay as you go | y |  | Setup contract direct or via Cloud Service Provider
8 | Anaconda | Python Enterprise |  |  | x | x | Subscription | 275 | User | y | Update. 29.04. Kein Lizenzserver nötig, User beziehen die Lizenz über ihren Client und greifen auf Cloud Anaconda Service zu. | Quantity adjusted
9 | Ansys | ANSYS Workbench Mechanics 19.1 | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Electronics Enterprise Prep/Post | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Electronics Premium HFSS | 22.06.2025 | Set Up Licence Server |  |  | tbd | 6 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Electronics Premium Icepak | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Electronics Enterprise | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | HPC Pack #3 (up to 132 cores->new 64 cores) | 22.06.2025 | Set Up Licence Server | 2025-05-14 |  | tbd | 64 | cores | y | WS04a ¦ FlexLM | Quantity and metric adjusted
9 | Ansys | ANSYS Discovery Modeling | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Geometry Interface for SolidWorks | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS LS-DYNA | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Mechanical Enterprise PrepPost | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS LS-DYNA HPC | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | ANSYS Mechanical Enterprise Solver | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | Simplurer | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | SPEOS | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | SPEOS OST | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | Design Modeler | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
9 | Ansys | Ansys Zemax OpticStudio Premium | 2025-06-22 | Set Up Licence Server |  |  | tbd | 3 | User | y | WS04a ¦ FlexLM | decide on licenses model
n/a | Apis | IQ-RM Pro |  |  | 2025-05-16 |  | Perpetual | 195 | User | n/a |  | Not requered anymore | Update 16.05: According to the alignment between Apis and Ronny Jakubasch (BT/QM-ST), no sourcing activities are required, and the license will no longer be needed after the end of 2025
n/a | Apis | IQ-CT Analysis |  |  | 2025-05-16 |  | Perpetual | 195 | User | n/a |  | Not requered anymore | Update 16.05: According to the alignment between Apis and Ronny Jakubasch (BT/QM-ST), no sourcing activities are required, and the license will no longer be needed after the end of 2025
11 | Atlassian | Confluence (on Prem) | 2025-06-22 | Go-Live of this product is 05.05.; tbd if this is provided by Bosch; analog to Bitbucket |  |  | Subscription | 2000 | User | y
11 | Atlassian | Jira (on Prem) | 2025-06-22 | Go-Live of this product is 05.05.; tbd if this is provided by Bosch; analog to Bitbucket |  |  | Subscription | 2000 | User | y
11 | Atlassian | SourceTree | 05.05.025 (Freeware) |  | x |  | tbd | 2000 (Freeware) | User | Y (freeware) |  | Freeware -> but must be procured | Added application, free Addon
11 | Atlassian | Bitbucket Data Center | 2025-06-22 | Need to switch licenses before cut-off | x |  | Subscription | 2000 | User | y |  |  | Data Center edition
n/a | Atlassian | Bitbucket (Source Code 03) | - |  | x |  | Subscription | 1 | User | n/a |  |  | Consulidated data center edition
11 | Atlassian | Announcer for Bitbucket (incl. PegDown, incl. jSoup) V 4.6.2 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y
n/a | Atlassian | Bitbucket PlantUML Plug-in V 1.4.0 |  |  | 24/04/2025 |  | Subscription | 2000 | User | n/a |  | will be terminated. Alternative: There is a plugin for Confluence to display code from Bitbucket and it can also render PlantUML diagrams there. https://support.atlassian.com/bitbucket-data-center/kb/display-plantuml-diagrams-in-bitbucket-server-dc-ui-using-markdown/
11 | Atlassian | Bitbucket Server - Auto-unapprove Pull Requests V 5.0.0 | 05.05.025 (Freeware) | Go-live of Bitbucket needs licenses (free) | 2025-04-15 |  | Subscription | 2000 (Freeware) | User | Y (freeware) |  | Freeware -> but must be procured
11 | Atlassian | Categories for Bitbucket V 1.6.2 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y
n/a | Atlassian | Code Owners for Bitbucket V 6.6.0 | - |  | 15.04.2025 |  | Subscription | 2000 | User | n/a |  | Data Center | no longer required
11 | Atlassian | Commit Graph for Bitbucket Data Center V 2024.03.31 | 05.05.025 (Freeware) | Go-live of Bitbucket needs licenses (free) | x |  | Subscription | 2000 (Freeware) | User | Y (freeware) |  | Freeware -> but must be procured | Added application, free Addon
11 | Atlassian | Control Freak - Commit Checks and Jira Hooks for Bitbucket V 2024.12.08 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y |  | Data Center
11 | Atlassian | Include Code Quality for Bitbucket V 7.0.2 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y
11 | Atlassian | Repository Templates for Bitbucket Server V 4.2.1 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y
11 | Atlassian | SAML Single Sign On for Bitbucket V 6.11.2 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | y
n/a | Atlassian | Snippets for Bitbucket Server V 3.2.1.8 | - |  | 15.04.2025 |  | Subscription | 2000 | User | n/a |  |  | no longer required
n/a | Atlassian | Yet Another Commit Checker V 1.26.0 | 2025-05-05 | Go-live of Bitbucket needs licenses |  |  | Subscription | 2000 | User | n/a |  | Data Center | no longer required
11 | Atlassian | ScriptRunner for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/6820/scriptrunner-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Clone Plus for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/44043/clone-plus-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Xray Test Management for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211769/xray-test-management-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Jira Misc Workflow Extensions (JMWE) (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/292/jira-misc-workflow-extensions-jmwe?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | JSU Automation Suite for Jira Workflows (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/5048/jsu-automation-suite-for-jira-workflows?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Risk Register (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1213146/risk-register?hosting=datacenter&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | WBS Gantt - Chart- Enterprise Project Management for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211768/wbs-gantt-chart-for-jira-enterprise-project-management?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Easy Agile TeamRhythm - User Story Map & Retrospectives (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1212078/easy-agile-teamrhythm-user-story-map-retrospectives?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | easeRequirements - Requirements Management for Jira (R4J) | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1213064/easerequirements-requirements-management-for-jira-r4j?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Bulk Clone Professional for Jira (Data Center) 2000 Users 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1213028/bulk-clone-professional-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Last Log for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211604/last-log-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Jeditor - Rich Text Editor for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1210768/jeditor-rich-text-editor-for-jira?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Configuration Manager for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211611/configuration-manager-for-jira-cmj?hosting=datacenter&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Multiple Subtasks for Jira (Data Center) 2000 Users | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1229293/multiple-subtasks-for-jira?hosting=datacenter&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Comala Publishing | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/143/comala-publishing?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Content Formatting Macros for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/247/content-formatting-macros-for-confluence?hosting=cloud&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | draw.io Diagrams & Whiteboards | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1210933/draw-io-diagrams-whiteboards?hosting=cloud&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Excel for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/216/excel-for-confluence?hosting=datacenter&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | LaTeX Math | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1216800/latex-math-for-confluence-with-math-editor-texlive-chatgpt?hosting=cloud&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Linking for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/166/linking-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | MultiExcerpt | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/169/multiexcerpt?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Numbered Headings | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/16063/numbered-headings?hosting=cloud&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | PlantUML Diagrams for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/41025/plantuml-for-confluence?hosting=datacenter&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Scroll HTML Exporter for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/420604/scroll-html-exporter-for-confluence?hosting=cloud&tab=overview | Added application, link to specific product to be identified
11 | Atlassian | Scroll ImageMap for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/253/scroll-imagemap-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Scroll PDF Exporter for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/7019/scroll-pdf-exporter-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Scroll Versions for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1210818/scroll-versions-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Scroll Viewport for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211636/scroll-viewport-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Table Filter, Charts & Spreadsheets for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/27447/table-filter-charts-spreadsheets-for-confluence?hosting=datacenter&tab=pricing | Added application
11 | Atlassian | Webhook to Jenkins for Bitbucket Server V 6.4.5 | 2025-05-05 | Go-live of Bitbucket needs licenses | x |  | Subscription | 2000 | User | Y |  |  | Added application
11 | Atlassian | Scroll Translations for Confluence | 2025-05-05 | Go-Live of this product is 05.05.; to be procued by Triton | x |  | Subscription | 2000 | User | y |  | https://marketplace.atlassian.com/apps/1211616/scroll-translations-for-confluence?hosting=datacenter&tab=pricing | Added application
12 | Autodesk | Inventor Pro | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 3 | User | y | WS04a ¦ FlexLM
12 | Autodesk | AutoCAD (userbased) | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 66 | User | y | WS04a ¦ FlexLM
12 | Autodesk | AutoCAD Architecture (userbased) | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 6 | User | y | WS04a ¦ FlexLM
n/a | Autodesk | AutoCAD Electrical (SCCM) |  |  |  |  | Subscription | no longer relevant | User | n/a
12 | Autodesk | AutoCAD Mechanical (userbased) | 22.06.2025 | Set Up Licence Server | 2025-05-14 |  | Subscription | 0 | User | y | WS04a ¦ FlexLM | 14.05.2025: Quantity adjusted, product part of Autodesk Autocad
12 | Autodesk | Autodesk 3ds Max (userbased) | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 2 | User | y | WS04a ¦ FlexLM
12 | Autodesk | Autodesk Revit (userbased) | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 7 | User | y | WS04a ¦ FlexLM
12 | Autodesk | Navisworks | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 1 | User | y | WS04a ¦ FlexLM
13 | Avensoft | CAR Tool: nService Software Subscription |  |  | 2025-04-09 | x |  | 1 |  | procurement in progress by workstream outside license management
14 | Axway | TSIM | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_18652
14 | Axway | EDI Manager | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_65527
15 | B&W Software | Creo AuxApps for DC - EFA |  |  |  |  | unknown | 1 | User | y
16 | Balsamiq | Balsamiq Wireframes |  |  |  |  | tbd | 30 | User | y |  | decide on licenses model
17 | Bechtle | Worksuite Nextcloud |  |  | x | x |  | 200 | User | already ordered
18 | Bricsys | Bricscad Pro | 22.06.2025 | Set Up Licence Server |  |  | tbd | 5 | User | y | WS04a ¦ Reprise Licence Server | decide on licenses model
n/a | Broadcom | Symantec Endpoint Protection |  |  |  |  | Subscription | 3523 | device | n/a |  | no longer required | not required as per Anton P.
19 | Broadcom | UC4 | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_54545
19 | Broadcom (VMWare) | ESX / vSphere VVS CN |  |  | 2025-05-14 |  | Subscription | 64 -> 72 minimum purchase | Cores | y
19 | Broadcom (VMWare) | ESX / vSphere VVS TW |  |  | 2025-05-14 |  | Subscription | 64 -> 72 minimum purchase | Cores | y
19 | Broadcom (VMWare) | ESX / vSphere VVS US |  |  |  |  | Subscription | 384 | Cores | y
19 | Broadcom (VMWare) | ESX / vSphere VVS MX |  |  | 2025-05-14 |  | Subscription | 64 -> 72 minimum purchase | Cores | y
19 | Broadcom (VMWare) | ESX / vSphere VVS EMEA |  |  |  |  | Subscription | 624 | Cores | y
20 | Cadence Design Systems | Cadence OrCAD PSpice 17.4 | 22.06.2025 | Set Up Licence Server |  |  | unknown | 8 | User | y | WS04a ¦ FlexLM
n/a | Cadence Design Systems | OrCAD-CN |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM | Same product as above - to be removed from the list | clarified demand, not needed
20 | Cadence Design Systems | OrCAD Capture 17.4 | 22.06.2025 | Set Up Licence Server | x |  | unknown | 8 | User | y | WS04a ¦ FlexLM |  | clarified demand
n/a | Cadence Design Systems | PspiceAD |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM |  | clarified demand, not needed
n/a | Cadence Design Systems | OrCAD PSpice Designer |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM |  | clarified demand, not needed
n/a | Cadence Design Systems | OrCAD PSpice Designer Plus |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM |  | clarified demand, not needed
n/a | Cadence Design Systems | OrCAD PCB Designer Professional + PSpice |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM |  | clarified demand, not needed
n/a | Cadence Design Systems | OrCAD PCB Designer Standard |  |  | x |  | unknown |  |  | n/a | WS04a ¦ FlexLM |  | clarified demand, not needed
21 | Camline | Cornerstone 8 | [5 empty] | 4 | User | y
22 | Cartel Infosystems | FRAME_Cartel-Infosystems_SOTI_Lizenzen |  |  | 2025-04-09 |  | Cloud Contract | 400 |  | procurement in progress by workstream outside license management |  | See Email from Dietmar Walter from 09th. April & Info from Bettina Rech
23 | CheckMK | CheckMK | [7 empty] | procurement in progress by workstream outside license management
n/a | Cisco | Cisco AnyConnect Secure Mobility Client 4.10 |  |  |  |  | n/a | discontinued | n/a | n/a
n/a | Cisco | Cisco Secure Client 5.x |  |  |  |  | n/a | discontinued | n/a | n/a
n/a | Cisco | Webex |  |  |  |  | n/a | discontinued | n/a | n/a
n/a | Citrix | Workspace / Virtual Desktop |  |  |  |  | tbd |  |  | n/a |  | as of Jan 23, 2025: no Citrix
| Citrix | VMware vSphere |  |  | 2025-06-06 |  |  | 4x32 Cores = 128 Cores | Cores | procurement in progress by workstream outside license management |  | Add demand - Email 06.06. Pierre Kromat | 06.06.2025: Quantity according Comline input, souring via Triton / or Keenfinity (in discussion) see Email Pierre Kromat
24 | Cognigy | ST-LOG/ Order Status Tracking |  |  |  |  | Subscription |  |  | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
25 | Comsol | COMSOL Multiphysics | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | User | y | WS04a ¦ FlexLM | decide on licenses model
25 | Comsol | ACOUSTICS | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | User | y | WS04a ¦ FlexLM | decide on licenses model
25 | Comsol | Design | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
25 | Comsol | CADIMPORT | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ FlexLM | decide on licenses model
n/a | Congree Language Technologies GmbH | Congree UCC |  |  | x |  |  |  |  | n/a |  | BT locally ordered | updated, already ordered locally
26 | Corel | CorelDRAW Technical Suite |  |  |  |  | Perpetual | 11 | User | y
26 | Corel | Corel VideoStudio Pro |  |  |  |  | tbd | 6 | User | y |  | decide on licenses model
26 | Corel | Corel PaintShop Pro |  |  |  |  | Perpetual | 2 | User | y
26 | Corel | MindManager 23 |  |  | 2025-05-27 |  | Subscription | 58 | User | y | Update 27.05: No license server needed – file sharing is sufficient. – KeenIT |  | See Email from Max Zehrt
27 | Crownpeak | BT-ST/ Dealer Locator | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_25342
27 | Crownpeak | BT-VS/ Webforms (Monday Webforms) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_88683
27 | Crownpeak | Dynacord Website on First Spirit | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_15031
27 | Crownpeak | Electro-Voice Website on First Spirit | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_34472
27 | Crownpeak | NewCo Website WCMS First Spirit Cloud | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_41304
n/a | Dassault | Catia V5 |  |  |  |  | Perpetual | 1 | User | n/a |  | no longer used (Sousa Marcia (BT/PUQ2) <Marcia.Sousa@pt.bosch.com>)
28 | Dassault | eDrawings Professional Viewer | 22.06.2025 | Set Up Licence Server |  |  | tbd | 20 | User | y | WS04a ¦ Dassault Licence Server | decide on licenses model
n/a | Dassault | SmartTeam |  |  |  |  | Perpetual | 1 | User | n/a |  | no longer used (Sousa Marcia (BT/PUQ2) <Marcia.Sousa@pt.bosch.com>)
n/a | Dassault | Solidworks Professional |  |  | x |  | tbd | 98 | User | n/a | WS04a ¦ FlexLM | 20250402: detailed demand specified in other lines
28 | Dassault | Solidworks Composer | 22.06.2025 | Set Up Licence Server | x |  | Subscription | 1 | Network | y | WS04a ¦ Dassault Licence Server |  | Added application
28 | Dassault | Solidworks Composer | 22.06.2025 | Set Up Licence Server | x |  | Subscription | 4 | User | y | WS04a ¦ Dassault Licence Server |  | Added application
28 | Dassault | Solidworks Composer | 22.06.2025 | Set Up Licence Server | x |  | Subscription (3 months) | 1 | User | y | WS04a ¦ Dassault Licence Server |  | Added application
28 | Dassault | cae_cwdesigner | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwstd | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | camstd | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | edrw | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 9 | User China | y | WS04a ¦ Dassault Licence Server | Alternative: 3 Network Licenses
28 | Dassault | swoffice | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User China | y | WS04a ¦ Dassault Licence Server
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Germany | y | WS04a ¦ Dassault Licence Server
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 9 | User Mexico | y | WS04a ¦ Dassault Licence Server | Alternative: 2 Network Licenses
28 | Dassault | swoffice | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Mexico | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwadvpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Netherlands | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | User Netherlands | y | WS04a ¦ Dassault Licence Server | Alternative: 1 Network Licenses
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Netherlands | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cosmosfloworks_elec | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cosmosfloworkspe | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwadvpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwdesigner | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwstd | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | edrw | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 9 | User Portugal | y | WS04a ¦ Dassault Licence Server | Alternative: 2 Network Licenses
28 | Dassault | swoffice | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | composer | 22.06.2025 | Set Up Licence Server | 2025-05-16 |  | tbd | 6 | User Portugal | n/a | WS04a ¦ Dassault Licence Server
28 | Dassault | toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | User Portugal | y | WS04a ¦ Dassault Licence Server
28 | Dassault | cae_cwadvpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | edrw | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | plastics_pro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | solidworks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 28 | User US | y | WS04a ¦ Dassault Licence Server | Alternative: 8 Network Licenses
28 | Dassault | swoffice | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | swofficepremium_cwadvpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | swofficepro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | visustd | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | swofficepremium_cwpro | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
28 | Dassault | toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | User US | y | WS04a ¦ Dassault Licence Server
29 | Docker | Docker Desktop Business |  |  | 2025-05-14 |  | Subscription | 34 | User | y |  | 14.05.2025 Business Edition
30 | Docusign | Docusign |  |  | 2025-04-23 |  | Subscription | 410 Envelopes | Envelope | y |  |  | See Email to Bettina Recha on 23th April
31 | Downstream Technologies | CAM350 V15.x |  |  |  |  | unknown | 45 | User | y | WS04a ¦ FlexLM
n/a | EDICOMUNICACIONES MEXICO | Edicom |  |  | 2025-04-30 | x |  | Unlimited (User name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
33 | Empower | Empower Charts |  |  |  |  | Subscription | 157 | User | y
n/a | Entrust | Entelligence Security Provider |  |  |  |  | n/a | will be replaced, tbd | User | n/a
34 | Eske | Smart Order Processing BT LOG-AM | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
35 | Figma | Figma Organization | 01.05.2025 | Required to move assets from old SaaS with Bosch to new SaaS with KF | 2025-04-16 |  | Subscription | 20 | User | procurement in progress by workstream outside license management |  | Purchase order released by Eva Andritschky on 16.04.25
36 | Flexera Software | InstallShield Premier |  |  | x | x |  | 2 | User | y
37 | Fossid | Fossid | 11.05.2025 | Go-live of FOSSID needs licenses | 2025-04-16 |  |  | ? |  | procurement in progress by workstream outside license management |  | See Email from Thomas Büttner from 16th. April | SOL_63471
38 | Ghisler Software GmbH | TotalCommander |  |  | x | x |  | not defined yet |  | n |  | 28.04: Still in clarification | Upade 28.04.25: see Email Mr. Ridder to Harald Schoengen - not critical
n/a | Github | Social Coding Access |  |  |  |  | tbd | see Microsoft | n/a | n/a
39 | Google | BT/BigQuery Webpage traffic measure | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_25868
39 | Google | Google Maps API Keys for Javascript(DynamicMaps) API: <7000 Requests per month |  |  | x | x |  | 2 | Keys | y |  | https://developers.google.com/maps/documentation/javascript/get-api-key
39 | Google | Google Maps API Keys for Javascript(DynamicMaps) API: <10000 Requests per month |  |  | x | x |  | 1 | Keys | y |  | https://developers.google.com/maps/documentation/javascript/get-api-key
39 | Google | Google Maps API Keys for Places API: <5000 Requests per month |  |  | x | x |  | 2 | Keys | y |  | https://developers.google.com/maps/documentation/places/web-service/get-api-key
40 | Hexagon | Q-DAS Notebook V14 (Qs-Stat and Solara) |  |  |  |  | unknown | 12 | User | y | Update 29.04. Template mit Doku wird erstellt (Installationsquelle + Lizenz) -> User kann sich selbst Lizenz installieren. Bereitstellung auf beliebigen Fileserver
41 | Hyperion | HFM-Financial Statements (YEC) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_23489
n/a | IBM | Doors |  |  |  |  | tbd | no longer relevant | User | n/a
n/a | IBM | Rational Token License |  |  |  |  | tbd | no longer relevant | Token | n/a
n/a | IBM | Clearcase |  |  |  |  | tbd | no longer relevant | User | n/a
42 | IBM | BT_ST_PnL (Planning Analytics) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_48112
43 | IDM Computer Solutions | UltraEdit 20.x |  |  | x | x |  |  |  | n |  | 28.04: Still in clarification | Upade 28.04.25: see Email Mr. Ridder to Harald Schoengen - not critical
44 | Irfan Skeljan | Irfanview |  |  |  |  | Perpetual | 873 | User | y
45 | Ivalua | Ivalua | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
46 | Jam Software | Treesize |  |  |  |  | Perpetual | 379 | User | y
47 | Jetbrains | Clion |  |  |  |  | Subscription | 5 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | dotUltimate |  |  |  |  | Subscription | 6 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | IntelliJ IDEA Ultimate |  |  |  |  | Subscription | 18 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | PyCharm |  |  |  |  | Subscription | 4 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | JetBrains Licenses all |  |  |  |  | Subscription | 79 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | ReSharper Internet |  |  |  |  | Subscription | 12 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
47 | Jetbrains | WebStorm |  |  |  |  | Subscription | 2 | User | y | Update 02.04. Gespräch mit Service Owner -> zukünftig nur noch Webbased Licences. Lizenzserver wird nicht mehr benötigt
48 | JFrog | Artifactory #BoschDevCloud by CI | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_44983
48 | JFrog | Artifactory Enterprise X | 22.06.2025 | Need to switch licenses before cut-off |  |  |  | 3 | Instances | y
49 | Kinaxis | RapidResponse |  |  |  |  | tbd | 80 | User | procurement in progress by workstream outside license management |  | decide on licenses model, consider SAP Add on
n/a | KNIME | KNIME Analytics Platform |  |  | x |  | Subscription | 15 |  | n/a |  | no longer required | See Email from Andreas Baur 08.04 - we do not need KNIME for Keenfinity | Not required for Keenfinity
51 | LeanIX (SAP) | Application Portfolio Management |  |  |  |  | Subscription | 300 | Applications | y
n/a | LeanIX (SAP) | Architecture and Roadmap Planning (50%) |  |  |  |  | Subscription | 300 | Applications | n/a |  | currently not relevant (Andreas Baur 17.01.2025)
51 | LeanIX (SAP) | LeanIX Technology Risk and Compliance |  |  | x |  | Subscription | 300 | Applications | y |  | new entry 03/10/25 | Added application
52 | Learnpulse | Screenpresso Pro |  |  |  |  | Perpetual | 3110 | User | y
53 | Mathworks | Audio_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Compiler | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Distrib_Computing_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Image_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Instr_Control_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MAP_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Blocks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Stateflow | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Statistics_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Symbolic_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN EU | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Audio_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU DE | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB | 22.06.2025 | Set Up Licence Server | x |  | tbd | 3 | NNU DE | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU DE | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Communication_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Compiler | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Database_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 8 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Image_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 7 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB_Report_Gen | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Neural_Network_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Real-Time_Workshop | 22.06.2025 | Set Up Licence Server | x |  | tbd | 4 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | RTW_Embedded_Coder | 22.06.2025 | Set Up Licence Server | x |  | tbd | 3 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Simscape | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Video_and_Image_Blockset | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Wavelet_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU NL | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Audio_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Compiler | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Distrib_Computing_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Image_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Instr_Control_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MAP_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Blocks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Statistics_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Symbolic_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | CN US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Antenna_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Audio_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Distrib_Computing_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Instr_Control_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB | 22.06.2025 | Set Up Licence Server | x |  | tbd | 14 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Optimization_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Phased_Array_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | RF_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Robotics_System_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Blocks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 6 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Video_and_Image_Blockset | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU US | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Compiler | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Control System Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Database_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 5 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Image_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 7 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Instr_Control_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MAP_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB | 22.06.2025 | Set Up Licence Server | x |  | tbd | 7 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB_Coder | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | MATLAB_Report_Gen | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Neural_Network_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Real-Time_Workshop | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | RTW_Embedded_Coder | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Blocks | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Signal_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 4 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | SIMULINK | 22.06.2025 | Set Up Licence Server | x |  | tbd | 3 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Spreadsheet Link | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Statistics_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | Symbolic_Toolbox | 22.06.2025 | Set Up Licence Server | x |  | tbd | 1 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
53 | Mathworks | XPC_Target | 22.06.2025 | Set Up Licence Server | x |  | tbd | 2 | NNU Taiwan | y | WS04a ¦ FlexLM |  | updated demand details, split into regions
n/a | MeinTest GmbH Switzerland | TestComplete |  |  | x | x |  |  |  | n/a |  | only transfer of existing contract to Keenfinity
54 | Mentor (Siemens) | visECAD Layout Viewer | 22.06.2025 | Set Up Licence Server |  |  | tbd | 15 | User | y | WS04a ¦ Safenet Server | decide on licenses model
54 | Mentor (Siemens) | visECAD Plus | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | User | y | WS04a ¦ Safenet Server | decide on licenses model
55 | Microsoft | M365 E3 incl. Teams |  |  |  |  | Subscription | 3251 | User | y |  | Bosch can purchase MFST E3 only in bunde with following products: Defender for Endpoint P2, Defender for O365 P1, AAD P2, AIP P2, Cusomer Key, Customer LockBox)
55 | Microsoft | Microsoft Entra ID P2 | 2025-06-01 |  |  |  | Subscription | 3251 | User | y
n/a | Microsoft | Microsoft Teams Shared Devices |  |  |  |  | Subscription | 0 | Devices | n/a |  | no relevant |  | Define Quantity | SWS1, Chris, Claus Giehl
55 | Microsoft | Teams Phone Standard |  |  |  |  | Subscription | 3251 | User | y
55 | Microsoft | Audio Conferencing |  |  |  |  | Subscription | 3251 | User | y
55 | Microsoft | Visio Plan 2 |  |  | 2025-05-14 |  | Subscription | 544 | User | y |  | 14.05.2025: Plan 2
n/a | Microsoft | ProjectPro |  |  |  |  | Subscription | duplicate | User | n/a
55 | Microsoft | Windows Server Data Center |  |  |  |  | tbd | 1128 | Cores | y
55 | Microsoft | Visual Studio Enterprise | 22.06.2025 | Azure DevOps onprem usage | 2025-05-14 |  | Subscription | 55 | User | y |  | 14.05.2025: will initially be procured as Professional as per Keenfinity decision
55 | Microsoft | Visual Studio Professional | 22.06.2025 | Azure DevOps onprem usage |  |  | Subscription | 105 | User | y
55 | Microsoft | AzureDevOps Server CAL (dedicated) | 22.06.2025 | Azure Devops onprem usage |  |  | tbd | 56 | User | y
n/a | Microsoft | Remote Assist (userbased) |  |  |  |  | tbd | 1 | User | n/a |  |  | no need according to user feedback |  | User
55 | Microsoft | Visual Studio Enterprise with GitHub Enterprise |  |  |  |  | tbd | 165 | User | y
55 | Microsoft | Visual Studio Professional with GitHub Enterprise |  |  |  |  | tbd | 260 | User | y
55 | Microsoft | Visual Studio Test Professional |  |  |  |  | tbd | 7 | User | y
55 | Microsoft | SQL Server Standard |  |  |  |  | tbd | 100 | Cores | y
55 | Microsoft | Exchange Server on Premise (Enterprise) |  |  | 2025-05-14 |  | tbd | 3 | Instances | y |  | 14.05.2025 Enterprise
55 | Microsoft | Github Enterprise Cloud |  |  | 45755 |  | Subscription | 190 | User | y |  |  | Cloud edition
55 | Microsoft | Project Plan P3 |  |  |  |  | Subscription | 224 | User | y
55 | Microsoft | Office 2016 Pro Plus |  |  |  |  | tbd | 159 | User | y
n/a | Microsoft | Power BI Desktop - Cloud |  |  |  |  | Subscription | 288 | User | n/a |  | replaced by Power BI Pro |  | Assess demand details | SWS7 mit SWS1 and SWO-SME Monja Franken
55 | Microsoft | Power BI Pro |  |  |  |  | Subscription | 178 | User | y
n/a | Microsoft | Power Platform (Power Apps, Power Automate) |  |  |  |  | Subscription | not defined yet | User | n/a |  | replaced by following 4 products |  | Assess demand details | SWS7 mit SWS1 and SWO-SME Monja Franken
n/a | Microsoft | SEJ-00002 Power Apps Premium Sub Per User |  |  |  |  | Subscription | 15 | User | n/a |  | duplicate
55 | Microsoft | 1O4-00001 Power Automate Premium Sub Per User |  |  |  |  | Subscription | 10 | User | y
55 | Microsoft | 8F5-00001 Power Automate Process Sub |  |  |  |  | Subscription | 2 | Process | y
55 | Microsoft | J8Q-00005 Power Apps Per App Sub 1 App or Website |  |  |  |  | Subscription | 500 | App | y
55 | Microsoft | SEJ-00002 Power Apps Premium Sub Per User |  |  |  |  | Subscription | 10 | User | y
n/a | Microsoft | J8Q-00005 Power Apps Per App Sub 1 App or Website |  |  |  |  | Subscription | 500 | App | n/a |  | duplicate
55 | Microsoft | Power BI Premium Capacities |  |  |  |  | Subscription |  |  | n |  | 30.04: Still in clarificaton | Update 30.04.25: Still no update - see email from Karl-Heinz Jansen (BT/BDO-DO-ST) >> to be covered via Azure contract (PAYG); - Chris Schygulla 3.2.25: Sicher werden Premium Kapazitäten benötigt. Mangels Governance/ Ownership BT kann der Umfang nicht bewertet werden: 11.33.25: auf Nachfrage keine weiteren Details derzeit verfügbar
55 | Microsoft | Github Copilot Business |  |  |  |  | Subscription | 150 | User | y
55 | Microsoft | RDS Cal |  |  |  |  | tbd | 200 | User | y
n/a | Microsoft | E5 Security Add On |  |  | x |  | Subscription | 3251 | User | n/a |  | no longer required | will not be used as per Anton (3/14/2025)
55 | Microsoft | Windows 10/11 Enterprise |  |  | x |  | tbd | 331 | Devices | y | KMS |  | added application
55 | Microsoft | Github Advanced Security |  |  | x |  | Subscription | 12 | User | y
55 | Microsoft | Azure | [6 empty] | Pay as you go | y |  | Setup contract direct or via Cloud Service Provider
57 | MinIO, Inc. | MinIO |  |  | 2025-05-14 | x |  | based on capacity / storage: 12k/100tb yearly |  | already ordered locally |  | 14.05.2025 already ordered
58 | Minitab | Minitab Statistical |  |  |  |  | Subscription | 178 | User | y
59 | Miro | Miro Enterprise | 2025-05-26 | Instance has to be available for migration | 2025-05-13 |  | Subscription | 250 | User | procurement in progress by workstream outside license management |  | Will be purchesed via Keenfinity | 13.05: Email to Michal & Davide to start purchasing process |  | Stefan Müller
60 | Mobatek | MobaXterm Professional |  |  |  |  | Perpetual | 34 | User | y
n/a | Mongodb | MongoDB |  |  | x | x |  | 1 |  | n/a |  | migration of existing service to new AWS contract
n/a | MX Transmite, SAPI de CV | EConnect Pro Control |  |  | 2025-04-30 | x |  | Unlimited (User name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
62 | Nagarro ES GmbH | maiConnect | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
63 | National Instrument | LabVIEW Professional Development System | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabWindows/CVI Full Development System | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | NI Measurement Studio Enterprise Edition | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW MathScript Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Unit Test Framework Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW VI Analyzer Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Digital Filter Design Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Advanced Signal Processing Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Desktop Execution Trace Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabWindows/CVI Signal Processing Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW DataFinder Toolkit* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | NI SignalExpress* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 64 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW for Mac and Linux | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Electrical Power Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | ECU Measurement and Calibration Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Automotive Diagnostic Command Set | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabWindows/CVI PID Control Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabWindows/CVI SQL Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | NI-Industrial Communications for Ethernet/IP | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Statechart Module* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Analog Waveform Editor* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Digital Waveform Editor* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 27 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | TestStand | 22.06.2025 | Set Up Licence Server |  |  | tbd | 38 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Switch Executive | 22.06.2025 | Set Up Licence Server |  |  | tbd | 38 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | TestStand ATML Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 38 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Requirements Gateway | 22.06.2025 | Set Up Licence Server |  |  | tbd | 21 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Real-Time Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 30 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW FPGA Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 30 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Analytics and Machine Learning | 22.06.2025 | Set Up Licence Server |  |  | tbd | 10 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW FPGA Compilation Tools | 22.06.2025 | Set Up Licence Server |  |  | tbd | 10 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabWindows/CVI Real-Time Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 10 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW OPC UA Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 10 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | NI Motion Assistant* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Sound and Vibration Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Vision Development Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | Vision Builder for Automated Inspection | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Modulation Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW SoftMotion Module* | 22.06.2025 | Set Up Licence Server |  |  | tbd | 7 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Datalogging and Supervisory Control Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Control Design and Simulation Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | LabVIEW Model Interface Toolkit | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | User | y | WS04a ¦ FlexLM | decide on licenses model
63 | National Instrument | VeriStand | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | User | y | WS04a ¦ FlexLM | decide on licenses model
64 | NetApp | NetApp | [7 empty] | procurement in progress by workstream outside license management |  |  | Input Chris Schneider
n/a | nextapp.co | [5 empty] | Sue Saeger 19.12. |  |  | n/a |  | not in scope, local
n/a | Nexthink | Nexthink Collector |  |  |  |  | SWS1 | duplicate |  | n/a
n/a | Nextthink | Collector |  |  |  |  | tbd | 3523 | device | n/a |  | Product discontinued |  |  | SWS1
n/a | Nía International Systems SA de CV | SAAE |  |  | 2025-04-30 | x |  | Unlimited (User name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
66 | Nia, Roca | GTXXI, SAAE (maquiladora) | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
n/a | NVIDIA Corporation & affiliates | Nvidia vGPU |  |  | x | x |  | not defined yet |  | n/a |  | no need
67 | OpenText | BT-ST Open Text: StreamServer 16.6.5 | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
68 | Optravis | Bosch Transfer Price Management (Optravis) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_32907
68 | Optravis | Transferprice Management Tool (Optravis) | [7 empty] | procurement in progress by workstream outside license management |  |  | RBCM2363
69 | Oracle | Database Standard Edition 2 |  |  |  |  | Perpetual | 2 | Sockets | In discussion: 12 Months TSA |  |  | Falco: 2 Standorte, je 1 Server, 1 CPU pro Server
69 | Oracle | Oracle JRE (Java) |  |  |  |  | Subscription | 4300 | User | y |  |  |  |  | SWS1
69 | Oracle | Virtualbox |  |  |  |  | Subscription | 214 | User | y
n/a | Oracle | SQL 2022??? |  |  | x |  | SOL 99057 |  |  | n/a |  | clarified with Jose: MS SQL already covered by Input from Falco | clarified, Vendor Microsoft, Covered
69 | Oracle (SAP DB) | Database Enterprise Edition |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
69 | Oracle (SAP DB) | Tuning Pack |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
69 | Oracle (SAP DB) | Partinioning |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
69 | Oracle (SAP DB) | Advanced Compression |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
69 | Oracle (SAP DB) | Diagnostics Pack |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
69 | Oracle (SAP DB) | Database-In-Memory (auf PFK und PF5) |  |  |  |  | Perpetual or Term License | 1930 | Named User Plus | In discussion: 12 Months TSA |  | Alternative to Named User: license 168 Oracle Processors (equals 7 Hosts with 48 cores each) |  | Clarify TSA | SWS2
70 | Pathlock | Taris | [5 empty] | 15 Systems, 4400 User |  | procurement in progress by workstream outside license management
71 | Peak Avenue | iQ-Audit 2.3 | [7 empty] | procurement in progress by workstream outside license management |  | not part of the project, this solution will not be provided by the project | SOL_64843
71 | Peak Avenue | IQ-Audit by AHP | [7 empty] | procurement in progress by workstream outside license management |  | not part of the project, this solution will not be provided by the project | SOL_18364
71 | Peak Avenue | eISIR | [7 empty] | procurement in progress by workstream outside license management |  | not part of the project, this solution will not be provided by the project | SOL_83961
72 | pit-cup | Pit-CAD |  |  | 2025-04-15 |  | unknown | 2 | User | n/a |  | Update 03.06: Continuation of the previous solution is not possible; therefore, no license procurement is required. | Update 03.06.25: Continuation of the previous solution is not possible; therefore, no license procurement is required. Alternative solution is the responsibility of the Real Estate Workstream (Stefan Reinhardt) - See also SOL. Aligned with Christian Schygula & Thomas Buettner. See also teams massage to Tobias Müller Keenfinity.
72 | pit-cup | Pit-FM |  |  | 2025-04-15 |  | unknown | 6 | User | n/a |  | Update 03.06:Continuation of the previous solution is not possible; therefore, no license procurement is required. | Update 03.06.25: Continuation of the previous solution is not possible; therefore, no license procurement is required. Alternative solution is the responsibility of the Real Estate Workstream (Stefan Reinhardt) - See also SOL. Aligned with Christian Schygula & Thomas Buettner. See also teams massage to Tobias Müller Keenfinity.
73 | Postman, Inc. | Postman Basic Plan |  |  | x | x |  | 25 | User | y |  | https://www.postman.com/pricing/ ($14/month per user if billed annually)
n/a | PRISMA Tecnología Computacional SA de CV | GTXXI |  |  | 2025-04-30 | x |  | Unlimited (User name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
75 | productboard | BT-VS productboard.com | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_99086
76 | Progress | Loadmaster (VLM-1G) with Enterprise Plus Subscription |  |  |  |  | Subscription | 4 | Instances | y
n/a | Proveedor Autorizado de Certificacion EdifactMX SA de CV | Edifact |  |  | 2025-04-30 | x |  | 20 (user name licenses) |  | n/a |  | not requered | See Email from Dietmar Walter / 30.04.25
n/a | PTC | PTC-WindchillPDMLink-Contributor |  |  |  |  | Subscription | 29 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-Creo |  |  |  |  | Subscription | 58 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-eBOM |  |  |  |  | Subscription | 5 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-eBOM-ACAD |  |  |  |  | Subscription | 3 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-eBOM-Creo |  |  |  |  | Subscription | 28 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-eBOM-Creo-ACAD |  |  |  |  | Subscription | 4 | User | n/a
n/a | PTC | PTC-WindchillPDMLink-Viewer |  |  |  |  | Subscription | 6 | User | n/a
78 | PTC | Service: PTC-Creo-Stand-Alone / License: Creo Advanced Assembly Extension - Global License | 22.06.2025 | Set Up Licence Server | 2025-05-16 |  | Subscription | 25 | Global Floating | y | WS04a ¦ FlexLM | 11 users + 63 user from Windchill base: -> 25 global floating | license details added, quantity updated
78 | PTC | Service: PTC-Creo-Stand-Alone / License: Creo Design Essentials Global (no PLM included) | 22.06.2025 | Set Up Licence Server | 2025-05-16 |  | Subscription | 25 | Global Floating | y | WS04a ¦ FlexLM | 11 users + 63 user from Windchill base: -> 25 global floating | license details added, quantity updated
n/a | PTC | PTC-CreoView-Stand-Alone | 22.06.2025 | Set Up Licence Server | 2025-05-16 |  | Subscription | 10 | User | n/a | WS04a ¦ FlexLM | Recoomendation Martin Lehrke: do not use, Windchill users have functionality included, standalone is around the process
78 | PTC | Service: PTC-WindchillPDMLink-Creo / License: Windchill Base | 22.06.2025 | Set Up Licence Server | 2025-06-06 |  | Subscription | 73 | User | y | WS04a ¦ FlexLM | Update 06.06: Quantity adjusted from 63 to 73 according Email from Max Zehrt >> Email to Dietmar Walter to inform Triton accordingly license details added, quantity updated | Update 06.06: Quantity adjusted from 63 to 73 according Email from Max Zehrt >> Email to Dietmar Walter to inform Triton accordingly license details added, quantity updated
78 | PTC | Service: PTC-WindchillPDMLink-Creo / License: Windchill Creo Data Management & Visualization | 22.06.2025 | Set Up Licence Server | 2025-06-06 |  | Subscription | 73 | User | y | WS04a ¦ FlexLM | Update 06.06: Quantity adjusted from 63 to 73 according Email from Max Zehrt >> Email to Dietmar Walter to inform Triton accordingly license details added, quantity updated | Update 06.06: Quantity adjusted from 63 to 73 according Email from Max Zehrt >> Email to Dietmar Walter to inform Triton accordingly license details added, quantity updated
78 | PTC | Tool Design Option | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 1 | User | y | WS04a ¦ FlexLM
78 | PTC | Complete Machining Option | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 2 | User | y | WS04a ¦ FlexLM
n/a | PTC | Creo Advanced Assembly Extension (former | 22.06.2025 | Set Up Licence Server | 2025-04-29 |  | Subscription | 71 | User | n/a | WS04a ¦ FlexLM | duplicate
78 | PTC | Creo View Validate (formerly ProductView) | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 4 | User | y | WS04a ¦ FlexLM
78 | PTC | Mathcad Prime | 22.06.2025 | Set Up Licence Server |  |  | Subscription | 13 | User | y | WS04a ¦ FlexLM
n/a | PTC | Arbortext | 22.06.2025 | Set Up Licence Server | 15.04.2025 |  | Subscription | 6 | User | n/a | WS04a ¦ FlexLM |  | consolidated into PTC-Arbortext-IsoDraw-CreoIllustrate
n/a | PTC | IsoDraw | 22.06.2025 | Set Up Licence Server | 15.04.2025 |  | Subscription | 6 | User | n/a | WS04a ¦ FlexLM |  | consolidated into PTC-Arbortext-IsoDraw-CreoIllustrate
78 | PTC | Creo Elements / Direct - Modeling subscr. (SPN-CC200-F-) | 22.06.2025 |  | 2025-05-16 |  | Subscription | 12 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Model Manager subscr. (SPN-CC210-F-) | 22.06.2025 |  | 2025-05-16 |  | Subscription | 14 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Workflow Client subscr. | 22.06.2025 |  | 2025-05-16 |  | Subscription | 7 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - WM Documents subscr. | 22.06.2025 |  | 2025-05-16 |  | Subscription | 7 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Interface for Adobe 3D PDF subscr. | 22.06.2025 |  | 2025-05-16 |  | Subscription | 1 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Surfacing subscr. (SPN-CC250-F-) | 22.06.2025 |  | 2025-05-16 |  | Subscription | 1 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Sheet Metal subscr.(SPN-CC320-F-) | 22.06.2025 |  | 2025-05-16 |  | Subscription | 1 |  | Y |  | Added on 15.05.2025
78 | PTC | Creo Elements / Direct - Finite Element Analysis subscr. (SPN-CC345-F-) | 22.06.2025 |  | 2025-05-16 |  | Subscription | 1 |  | Y |  | Added on 15.05.2025
n/a | PTC | Service: PTC-Arbortext-IsoDraw-CreoIllustrate / License: Arbortex Editor & Styler |  |  | 2025-04-29 |  | Subscription | 7 | User | n/a |  | no longer required | Update 29.04: See Email from Max Zehrt - not longer required
n/a | PTC | Service: PTC-Arbortext-IsoDraw-CreoIllustrate / License: illustrate |  |  | 2025-04-29 |  | Subscription | 7 | User | n/a |  | no longer required | Update 29.04: See Email from Max Zehrt - not longer required
n/a | PTC | Service: PTC-Arbortext-IsoDraw-CreoIllustrate / License: arbortext IsoDraw |  |  | 2025-04-29 |  | Subscription | 7 | User | n/a |  | no longer required | Update 29.04: See Email from Max Zehrt - not longer required
78 | PTC | Creo Simulation Live (• Creo Simulation Live) | 22.06.2025 | Set Up Licence Server | 15.04.2025 |  | Subscription | 1 | Floating | y | WS04a ¦ FlexLM | line item added | line item added
79 | Qualtrics | Qualtrics | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_53289
80 | Quanos | Quanos ST-Server 24 | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
81 | Realtime Soft | UltraMon |  |  | 2025-05-15 | x |  |  |  | n/a |  | 15.05: no purchase needed, purchase perpetual license locally long time ago | Updade 28.04.25: see Email Mr. Ridder to Harald Schoengen - not critical
82 | Redhat | Redhat Enterprise Linux Standard Support, bundled with Satellite |  |  |  |  | Subscription | 40 | Node | y |  |  |  |  | SWS1
n/a | Redhat | Satellite |  |  |  |  | Subscription | 40 |  | n/a
83 | Reuters | Integration Point GTV | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_77915
84 | Revizto | Revizto | [5 empty] | 2 | User | y
85 | RiB | iTWO Baseline |  |  |  |  | unknown | 3 | Concurrent User | y
85 | RiB | iTWO 5D |  |  |  |  | unknown | 3 | Concurrent User | y
85 | RiB | iTWO tx Volumen 3.000 |  |  |  |  | unknown | 3 | Packs | y
n/a | RWS | Passolo |  |  | x | x |  | 2 |  | n/a | WS04a ¦ FlexLM
n/a | RWS (Trados) | Passolo Professional Edition (Network SN) |  |  | 04.04.2025 | x |  | 1 | User | n/a | WS04a ¦ FlexLM | already purchased
n/a | RWS (Trados) | Passolo .NET Add-in |  |  | 04.04.2025 | x |  | 1 | User | n/a | WS04a ¦ FlexLM | already purchased
n/a | RWS (Trados) | Passolo Delphi Add-in |  |  | 04.04.2025 | x |  | 0 | User | n/a | WS04a ¦ FlexLM | already purchased
n/a | RWS (Trados) | Passolo Java Add-in |  |  | 04.04.2025 | x |  | 0 | User | n/a | WS04a ¦ FlexLM | already purchased
n/a | S.A.X. | eForms NG |  |  |  |  | tbd | 3251 | User | n/a |  | WS3: out of scope
86 | SAP | 7017299 SAP Single Sign-On |  |  |  |  | Perpetual | 38 | User | In discussion: Procurement by Bosch, Transfer |  | SSO no longer available. Successor „Secure Logging Service for SAP GUI“ only available as cloud product.​
86 | SAP | 7017328 SAP CRM Sales |  |  |  |  | Perpetual | 694 | User | In discussion: Procurement by Bosch, Transfer |  | Product discontinued
86 | SAP | 7017330 SAP CRM Service |  |  |  |  | Perpetual | 1005 | User | In discussion: Procurement by Bosch, Transfer |  | Product discontinued
n/a | SAP | 7018629 SAP Landscape Transformation, enterprise edition |  |  |  |  | Perpetual | 6 |  | n/a |  | no longer required
86 | SAP | 7018652 SAP S/4HANA Enterprise Management for Professional use |  |  | x |  | Perpetual | 1429 | User | In discussion: Procurement by Bosch, Transfer |  | Agree on dual use right for ECC​; evaluate user license types based on STAR-Report | updated based on STAR report
86 | SAP | 7018653 SAP S/4HANA Enterprise Management for Productivity use |  |  | x |  | Perpetual | 185 | User | In discussion: Procurement by Bosch, Transfer |  |  | updated based on STAR report
86 | SAP | 7018654 SAP S/4HANA Enterprise Management for Functional use |  |  | x |  | Perpetual | 150 | User | In discussion: Procurement by Bosch, Transfer |  |  | updated based on STAR report
86 | SAP | 7018682 SAP S/4HANA, Developer access |  |  |  |  | Perpetual | 30 | User | In discussion: Procurement by Bosch, Transfer
86 | SAP | BRIM: 7018705 SAP S/4HANA for convergent invoicing, 11 to 30 units |  |  |  |  | Perpetual | 23 blocks a 50.000.000 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7019741 SAP Shared Service Framework for S/4HANA |  |  |  |  | Perpetual | 15 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020280 SAP S/4HANA Digital Access, 5001 to 10000 units |  |  |  |  | Perpetual | 5001 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020287 SAP Application Interface Framework, up to 50 units |  |  |  |  | Perpetual | 5 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020302 SAP S/4HANA Finance for cash management, 11 to 50 units |  |  |  |  | Perpetual | 12 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020309 SAP S/4HANA Finance for receivables management, 11 to 100 units |  |  |  |  | Perpetual | 12 | Blocks of 100mill EUR revenue | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020500 SAP S/4HANA contract, lease and real estate management, 1501 to 5000 units |  |  |  |  | Perpetual | 50 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7020617 SAP Document and Reporting Compliance for S/4HANA, 11 to 100 units |  |  |  |  | Perpetual | 33 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | 7021400 SAP S/4HANA Supply Chain for extended warehouse management, up to 15 units |  |  | x |  | Perpetual | 600000 | Documents | In discussion: Procurement by Bosch, Transfer |  |  | added application
86 | SAP | Commerce Service Portal |  |  |  |  | Cloud Contract | 13487 external / 50 internal | User | procurement in progress by workstream outside license management
86 | SAP | Commerce ST Portal |  |  |  |  | Cloud Contract | 4781 | User | procurement in progress by workstream outside license management
n/a | SAP | Convergent Charging Server |  |  | x |  |  |  |  | n/a |  |  | updated, not required, covered in different line item
n/a | SAP | Digital Access |  |  |  |  | Perpetual | 1.000.000 | Documents | n/a |  | duplicate |  | Perform SAP Measurement | SWS2
86 | SAP | ERP Foundation / Starter Pack |  |  |  |  | Perpetual | 1 | Piece | In discussion: Procurement by Bosch, Transfer
86 | SAP | Hana DB |  |  |  |  | Perpetual | 15% of license value SAP | % | In discussion: Procurement by Bosch, Transfer
86 | SAP | SAP Business Objects (Normal User) |  |  |  |  | Perpetual | 160 | Concurrent Sessions | In discussion: Procurement by Bosch, Transfer |  |  |  | Perform SAP Measurement | SWS2
86 | SAP | SAP Business Objects (TopUser) |  |  |  |  | Perpetual | 50 | Standard User | In discussion: Procurement by Bosch, Transfer |  |  |  | Perform SAP Measurement | SWS2
86 | SAP | BRIM: CRM:SOM Subscription Order Management |  |  |  |  | Perpetual | 23 blocks a 50.000.000 | units | In discussion: Procurement by Bosch, Transfer
86 | SAP | BRIM: CC:Convergent Charging |  |  |  |  | Perpetual | 23 blocks a 50.000.000 | units | In discussion: Procurement by Bosch, Transfer
n/a | SAP | SAP Business Warehouse |  |  | x |  | Perpetual | 676 | User | n/a |  | on Prem BW free of charge | updated, not required, covered in different line item
n/a | SAP | SAP CRM |  |  |  |  | tbd | 1300 | User | n/a |  | duplicate |  | Perform SAP Measurement | SWS2
n/a | SAP | SAP EWM (auf Hana DB) |  |  | x |  | Perpetual | 307 | User | n/a |  | covered with 7021400 SAP S/4HANA Supply Chain for extended warehouse management | updated, not required, covered in different line item
87 | Saviynt | IdM Reporting 2.0 | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_19086
87 | Saviynt | Identity Management (oneIdM) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_22941
87 | Saviynt | CARDIO | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_3508
88 | Scapos | Packassistant |  |  |  |  | unknown | 2 | User | y
89 | Scooter Software | Beyond Compare |  |  |  |  | Perpetual | 598 | User | y
90 | Sharadien | Sharedien MAM/DAM Shared Cloud | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_92937
n/a | Siemens PLM | Teamcenter Product Cost Management |  |  |  |  | tbd | 3 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
n/a | Siemens PLM | Visualization |  |  |  |  | tbd | 116 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
n/a | Siemens PLM | Teamcenter NX |  |  |  |  | tbd | 1 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
n/a | Siemens PLM | Teamcenter NX CAE |  |  |  |  | tbd | 1 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
n/a | Siemens PLM | DPnE Prod Plan |  |  |  |  | tbd | 1 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
n/a | Siemens PLM | ProCodex (userbased) |  |  |  |  | tbd | 17 | User | n/a | WS04a ¦ FlexLM |  |  |  | SWS4
91 | Siemens PLM | Digital Thread Navigation XaaS | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Regional Floating EMEA | y | WS04a ¦ FlexLM
91 | Siemens PLM | Digital Thread Navigation XaaS | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Regional Floating AM | y | WS04a ¦ FlexLM
91 | Siemens PLM | DXF File Open for TC Vis | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Global Floating | y | WS04a ¦ FlexLM
91 | Siemens PLM | IGES File Open for TC Vis | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Global Floating | y | WS04a ¦ FlexLM
91 | Siemens PLM | JT Bi-Directional Translator for STEP | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | Global Floating | y | WS04a ¦ FlexLM
91 | Siemens PLM | Plant Simulation Professional Concurrent | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Regional Floating EMEA | y | WS04a ¦ FlexLM
91 | Siemens PLM | TC Visualization Mockup | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Regional Floating EMEA | y | WS04a ¦ FlexLM
91 | Siemens PLM | TC Visualization Pro Plus | 22.06.2025 | Set Up Licence Server |  |  | tbd | 10 | Global Floating | y | WS04a ¦ FlexLM
91 | Siemens PLM | Teamcenter Visualization Animation | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Global Floating | y | WS04a ¦ FlexLM
91 | Siemens PLM | Variation Analysis (Concurrent) | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Regional Floating EMEA | y | WS04a ¦ FlexLM
92 | Siesmic | BT/ Percolate (SaaS) | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_11408
93 | Snowflake | DALI 1.0 | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_61692
94 | SNP | REDLake Data Provisioning Service | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_74324
94 | SNP | SNP Glue |  |  |  |  | Subcription |  |  | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
95 | SoaPoeple | GETPAID 1.0 | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_74590
96 | SonarSource | Sonarqube Server Enterprise | 22.06.2025 | Need to switch licenses before cut-off |  |  | Subscription | 5000000 | lines of code | y
97 | Soti Inc. | SOTI MobiControl |  |  | 2025-04-09 |  |  | 400 |  | procurement in progress by workstream outside license management |  | See Email from Dietmar Walter / 09.04.25 | See Email from Dietmar Walter / 09.04.25
98 | Sparx | Enterprise Architect Corporate | 22.06.2025 | Set Up Licence Server |  |  | tbd | 30 | Floating User | y | WS04a ¦ Sparx specific | decide on licenses model
99 | Stethos | W-ELP | [7 empty] | procurement in progress by workstream outside license management |  |  | Mail S. Müller Nov 8, 2024
100 | Stibo Systems | Shared-PIM-STEP | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_46174
101 | SupplyON | EuroLog | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_21368
101 | SupplyON | SupplyON | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_92241
101 | SupplyON | SupplyON Web EDI | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_35401
101 | SupplyON | TOMs | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_33552
102 | Tableau | Desktop |  |  |  |  | Subscription | 3 | User | y
102 | Tableau | Prep Builder |  |  |  |  | Subscription | 1 | User | y
103 | Talend | Talend | [7 empty] | procurement in progress by workstream outside license management |  |  | Input from BT purchasing and controlling list - entered by Stefan M.
104 | Teamviewer | Teamviewer Enterprise Edition |  |  | 2025-05-02 |  |  | 55 | User | y |  |  | 03.05.2025: Decide to procure
105 | Techsmith | Camtasia |  |  |  |  | tbd | 7 | User | y |  | decide on licenses model
106 | TEC-IT Datenverarbeitung | TBarCode Office Enterprise 2D |  |  |  |  | Perpetual | 3 | User | y
106 | TEC-IT Datenverarbeitung | TBarcodeOCX 11 |  |  |  |  | Perpetual | 11 | User | y
107 | TEKLYNX | Codesoft BT |  |  | 2025-05-14 |  | tbd | 103 | User | already ordered |  | 14.05.2025 already ordered
108 | testrail.com | Testrail onprem |  |  | x | x |  | 10 | User | already ordered locally |  | 14.05.: details added, edition still in clarification | Upade 28.04.25: see Email Mr. Ridder to Harald Schoengen - not critical
109 | TrendMicro | NetApp-AV-Server (TrendMicro) | [7 empty] | procurement in progress by workstream outside license management |  |  | Input Chris Schneider
109 | TrendMicro | Server-AV (TrendMicro) | [7 empty] | procurement in progress by workstream outside license management |  |  | Input Chris Schneider
110 | Trimble | SketchUp Pro 2024 |  |  |  |  | Subscription | 9 | User | y
n/a | Various | SAP Addons |  |  | 2025-05-02 |  |  |  |  | n/a |  |  | Upate 02.05.25: Specify in respective line item
112 | Veeam | Veeam Data platform Foundation Universal |  |  |  |  | Subscription | 30 | Packs a 10 Instances | procurement in progress by workstream outside license management |  |  | wird über Comline beschafft, Angebot ist angefordert |  | SWS1
113 | Vertex | Vertex BT O-Series | [7 empty] | procurement in progress by workstream outside license management |  |  | SOL_52178
114 | VisualSVN | VisualSVN Enterprise (1000 User) | 10.05.2025 | Go live of Subversion needs license | 2025-04-16 |  | unknown | 1 | Instance | procurement in progress by workstream outside license management |  | Purchase order released by Eva Andritschky on 16.04.25
115 | Voxel51 | FiftyOne Enterprise |  |  | x | x |  | 10 | Users | y
116 | Whole tomato | Visual Assist Standard Edition |  |  | x | x |  | 11 |  | y |  | Personal Edition not for commercial use (organizations)
117 | Zuken | ZX1601 PC-Z1601-W1-L Design Gateway | 22.06.2025 | Set Up Licence Server |  |  | tbd | 6 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9001 die Hauptlizenz für Design Force, in den GX-Paketen enthalten | 22.06.2025 | Set Up Licence Server |  |  | tbd | 6 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9050 ZX9050I-W1-L DFM Elements | 22.06.2025 | Set Up Licence Server |  |  | tbd | 8 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX4601 ZX4601I-W1-L Components Editor | 22.06.2025 | Set Up Licence Server |  |  | tbd | 4 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9011 ZX9011I-W1-L Intelligent Place and Route | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9038 ZX9038I-W1-L DF EMD Collaborator | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX3301 PC-Z3301-W1-L Board Viewer Advance | 22.06.2025 | Set Up Licence Server |  |  | tbd | 3 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX4602 Interface-Lizenzen für ZX4601 Components Editor | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX4904 ZX4904I-W1-L Scenario EX | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9043 eine Zusatzlizenz für Design Force, in den GX-Paketen enthalten | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX1602 PC-Z1602-W1-L DG Standard ASCII Input/Output Module | 22.06.2025 | Set Up Licence Server |  |  | tbd | 2 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX1605 PC-Z1605-W1-L DG Library Editor | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX1607 PC-Z1607-W1-L DG PDF Compiler | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX1610 PC-Z1610-W1-L DG Circuit Difference Output/Confirmation | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX1617 PC-Z1617-W1-L DG Destination Management | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX4901 ZX4901I-W1-L Design Force SI | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX4903 ZX4903I-W1-L Design Force PI/EMI | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9013 ZX9013-W1-L Dragon EX | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9014 ZX9014I-W1-L Multi Object Design | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9019 ZX9019I-W1-L SiP Design | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9030 ZX9030I-W1-L DF ODB++ Export | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9032 ZX9032I-W1-L DF ANSYS ANF I/F | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9039 ZX9039I-W1-L Advanced STEP Generator | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9040I-W1-L DF Unidat 2.1 Output | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9041 ZX9041I-W1-L Power/Ground Plane Area Calculator | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZX9057 XX-Z9057-W1-L IPC-D-356 Export | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZXN000AL Framework Engine (user) | 22.06.2025 | Set Up Licence Server |  |  | tbd | 5 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZXN011AL EDA Library Master (user) | 22.06.2025 | Set Up Licence Server |  |  | tbd | 5 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
117 | Zuken | ZXN008YK3 WAN - Global WAN (3 Zones) Server License | 22.06.2025 | Set Up Licence Server |  |  | tbd | 1 | Floating | y | WS04a ¦ FlexLM | decide on licenses model
n/a | Zuken | DS-CR, Layout, Schematic |  |  |  |  | tbd |  | unknown | n/a | WS04a ¦ FlexLM | see comment in LDL