## Cover sheet
Risk Analysis M&A |  | IT-as-is Manager | BGSW CIO
|  | IT-Project Manager | Riyaz Ahmed Syed Ahmed (BD/MIL-PSM4)
- Cover Sheet - |  | PMI-Lead | Riyaz Ahmed Syed Ahmed (BD/MIL-PSM4)
Information about the project and the risk analysis:
Actions are tracked in
Further information:
Participants of latest meeting/update of risk analysis:
| Participant |  | Department |  | Function
PMI-Lead
IT-Project Manager
PjQM
Technical expert from project team
The required signature of the risk analysis (PjM and PjQM) is covered by the signature of the respective QA.
Document History:
| Change |  | Version | Date | Changed by
…
The risk analysis has to be updated regularly during the whole merger duration - The different states have to be versioned -

## Analysis of project risks
Analysis of as-is operation risks | [9 empty] | RZ statistic |  | Please insert rows exclusively over button!
[10 empty] | Threshold: | 12
Risks higher than or equal to threshold:
No. | Sub- project (optional) | Entry Date of Risk | Risk category | Risk (concrete, understandable description) | Effects (corresponds with T=Sign. of effects (column I)) | Causes | W | T | RZ | Actions (preventive and counter measures) | Responsible | Deadline | Status of action | Remarks / notes [optional] (e.g., critical general conditions; already planned actions)
1 | Bravo | 03-Apr-26 | ScR - Schedule | BGSW and Tata JV management bandwidth constrained during 3-month build-to-GoLive sprint (Apr-Jun 2026) | Phase 3 build and testing delays; GoLive of 1 Jul 2026 missed | Carve-out running concurrently with live AI business operations; split leadership focus | 4 | 4 |  | Dedicate BGSW carve-out lead with explicit protected time allocation; Deputy named; Weekly SteerCo cadence from Day 1 | Riyaz Ahmed, BGSW CIO | 30-Apr-26 | Amber | High priority. Mitigation plan in place. Monitor weekly.
2 | Bravo | 03-Apr-26 | SR - Scope | JV legal entity registration in India delayed beyond QG0 target (30 Apr 2026) | QG0 gate cannot be passed; entire programme timeline shifts right | MCA India bureaucratic processing times (4-8 weeks); first-time JV registration complexity | 3 | 5 |  | Engage external India legal counsel by Apr 3; initiate MCA filing within first week of project | Riyaz Ahmed, Legal, Finance | 10-Apr-26 | Green | Critical path item. India legal counsel essential. No antitrust filing required.
3 | Bravo | 03-Apr-26 | BtR - Budget | India cloud and M365 licensing costs exceed initial estimate for JV tenant provisioning | Budget overrun in Phase 3; delay in cloud environment readiness | Azure India region pricing; JV tenant licensing model complexity for 70 users | 3 | 3 |  | Conduct M365/Azure RFQ by end of Apr; lock licensing model at QG0; budget contingency of 15% reserved | Finance, BGSW Procurement | 30-Apr-26 | Amber | Small user base (70) limits financial exposure. Containable risk.
4 | Bravo | 03-Apr-26 | ScR - Schedule | Phase 3 build (Jun 2026) delayed due to BGSW infrastructure resource contention | GoLive date of 1 Jul 2026 missed; Phase 4 cutover cannot proceed | BGSW infra team shared across multiple India projects; AD and network build sequential dependencies | 3 | 4 |  | Reserve BGSW infra team capacity from May; confirm resource allocation at QG1/2/3 gate | Riyaz Ahmed, BGSW Infra Lead | 01-Jun-26 | Green | Short build window (Jun only). Resource reservation critical.
5 | Bravo | 03-Apr-26 | RR - Resource | Key BGSW IT personnel unavailable during compressed Jun 2026 build-and-test window | Build quality impacted; integration testing incomplete by QG1/2/3 (26 Jun) | Annual leave; BGSW parallel project demands; carve-out knowledge concentrated in few individuals | 3 | 4 |  | Enforce Jun leave freeze for critical roles; identify/train backups; document knowledge by end of May | BGSW HR, Riyaz Ahmed | 29-May-26 | Amber | June is the highest-risk month. Contingency plan required.
6 | Bravo | 03-Apr-26 | SR - Scope | Application migration scope expands beyond 17 AI apps due to late-discovered dependencies | Phase 3 timeline overrun; additional testing cycles required | Incomplete initial inventory; business users requesting additional apps post-QG0 | 2 | 4 |  | Hard scope freeze at QG0 (30 Apr); no additions after that date without SteerCo approval and timeline impact assessment | Riyaz Ahmed, WS Leads | 30-Apr-26 | Green | Small app count (17) makes scope creep manageable if freeze enforced.
7 | Bravo | 03-Apr-26 | CR - Change | Active Directory forest separation for JV incomplete by GoLive (1 Jul 2026) | Day 1 users unable to log on to JV systems; GoLive blocked | AD tooling complexity; configuration errors in JV forest build; insufficient testing time | 2 | 5 |  | Start AD build in week 1 of Jun; run integration and regression testing in parallel; conduct dress rehearsal Jun 24-26 | BGSW AD Team, Riyaz Ahmed | 24-Jun-26 | Green | AD is foundational for Day 1. No backout. Pilot and rehearsal mandatory.
8 | Bravo | 03-Apr-26 | BtR - Budget | Licence change-of-control costs for 17 AI applications exceed estimates | Budget overrun; delay in app migration if contracts not renegotiated in time | ISVs invoking change-of-control clauses; unexpected vendor lock-in terms | 2 | 3 |  | Complete licence review with change-of-control clause analysis by May 14; negotiate amendments ahead of Phase 3 | BGSW Procurement, Legal | 14-May-26 | Green | 17 apps is manageable. Early review essential.
9 | Bravo | 03-Apr-26 | QR - Quality | UAT failure rate high due to compressed testing window (18-24 Jun 2026) | QG1/2/3 gate (26 Jun) delayed; GoLive 1 Jul 2026 at risk | Business users not available for full UAT; test environment not stable | 3 | 4 |  | Engage business UAT leads by May 1; establish test environment in week 1 of Jun; run smoke tests daily from Jun 15 | Riyaz Ahmed, Business Leads | 15-Jun-26 | Green | UAT window is tight (5 working days). Early prep critical.
10 | Bravo | 03-Apr-26 | SR - Scope | Tata JV counterpart team (architecture, IT) not staffed in time for May concept workshops | JV IT architecture design delayed; Phase 2 deliverables incomplete | Tata internal hiring/assignment process for JV roles not yet started | 3 | 3 |  | Confirm Tata JV IT team nominees at Steering Committee kickoff (Apr 1); escalate to executive sponsor if not confirmed by Apr 10 | Riyaz Ahmed, Tata Executive Sponsor | 10-Apr-26 | Amber | Bosch leadership control mitigates: BGSW can proceed if Tata team is delayed.
11 | Bravo | 03-Apr-26 | LR - Legal | JV shareholder agreement final terms delay IT separation decisions | Scope boundary between BGSW and JV IT undefined; Phase 2 architecture blocked | Legal negotiations between Bosch and Tata on IP ownership and data rights extending beyond Apr | 2 | 4 |  | Identify IT decisions independent of full SHA; escalate blocking items to SteerCo; resolve core IP scope by QG0 | Legal, Riyaz Ahmed | 30-Apr-26 | Green | Bosch leadership control reduces legal complexity significantly.
12 | Bravo | 03-Apr-26 | CR - Change | Data separation between BGSW corporate and JV AI business data is more complex than anticipated | Data migration execution delayed past Jun 22; Day 1 data completeness at risk | AI training datasets and model artefacts stored in shared BGSW repositories; unclear data lineage | 3 | 3 |  | Complete data ownership mapping by May 19; agree separation rules with legal and data owners before Phase 3 starts | Riyaz Ahmed, Legal, BGSW IT | 29-May-26 | Green | Bosch-led JV reduces risk: BGSW data stewardship retained post-GoLive.
13 | Bravo | 03-Apr-26 | ScR - Schedule | Hypercare issues in Jul-Sep 2026 require BGSW resources beyond planned capacity | BGSW IT cost overrun; closure milestone (Oct 30) delayed | Application instability post-GoLive; 17 apps not fully stabilised before hypercare close | 2 | 3 |  | Ensure all 17 apps fully tested before GoLive; define clear P1/P2 escalation matrix; 60-day hypercare window is adequate buffer | Riyaz Ahmed, IT Ops | 01-Jul-26 | Green | No TSA risk as JV is Bosch-led; escalation to BGSW via governance channel available.
14 | Bravo | 03-Apr-26 | BR - Business | AI business continuity disrupted during Jun 2026 build and cutover activities | Tata / BGSW AI business projects delayed; executive sponsor dissatisfaction | Carve-out build activities running concurrently with live AI project deliveries | 2 | 3 |  | Define AI business activity blackout window for Week of Jun 29-Jul 1; agree cutover communications with business leads | BGSW AI Business Lead, Riyaz Ahmed | 29-Jun-26 | Green | Business continuity plan to be approved at QG1/2/3 gate.
15
Note on A7: The risks are numbered sequentially.
Note on B7: Multi-Projects: Please insert the project to which the risk refers
Note on C7: Only relevant for risks identified after creation of risk analysis.
Note on D7: If needed, risks can be assigned to risk categories. The following categories can be used as well as others. BR = Business BtR = Budget CR = Customer Satisfaction QR = Quality RR = Resource ScR = Schedule SR = Scope LR = Legality SrR = Security PR = Further product risks EM = Employee
Note on F7: What are the effects once the risk/ potential failure occurs?
Note on G7: What are the causes for the risk/the failure to occur?
Note on H7: W = Probability of occurrence: 5 = very high 4 = high 3= medium 2 = low 1 = unlikley
Note on I7: T= Significance of effects: 5 = very high 4 = high 3 = medium 2 = low 1 = unlikley
Note on J7: Product of W and T; The RZ shall support the prioritisation of risks and will be calculated automatically
Note on N7: Possible values: open, in process (iP), completed (com)
Note on O7: What was planned to minimise the risk before carrying out this risk analysis? E.g.: Database overflow. Plan for a monitoring software generating alerts once data volume reaches 80% of hard disk capacity. Not all risks can be eliminated by an action.

## Explanation_History
Information about method/template
Scope of risk analysis: (Attention: Procedure partly changed compared to previous template version!) |  |  | Project risks can generally be differed by product risks (e.g. product suitability, general conditions of product) and process risks (e.g. project management; development process or process of producing the project result). In the risk analysis both has to be covered.
Update: Cycle and versions |  |  | The risk analysis has to be updated regularly during the whole project duration - at least to each QA. The different states have to be versioned - the currently latest version has to be filed with the respective QA.
Update: Procedure (Attention: Procedure partly changed compared to previous template version!) |  |  | Updating the risk analysis, existing risks will be reassessed and new risk will be listed in the overview. By reassessing existing risks, the existing values can be overwritten with the new values because previous values are saved in the different versions of the document. Therefor old versions of the risk analysis have to be archived with the project documentation.
Definition of actions (Attention: Procedure partly changed compared to previous template version!) |  |  | At least for risks whose risk figure (RZ) is higher than or equal to the threshold value of 12, an action or a reason why no action is defined has to be named. It is recommended to define actions also to risks with high significance of effects (T). The threshold can be lowered (e.g. from 12 to 9) but not increased for the single project. To every action a responsible person and deadline have to be named.
Tracking of risks and actions (Attention:Procedure partly changed compared to previous template version!) |  |  | The document in which the actions are tracked has to be named in the cover sheet. Actions have to be done on schedule (requirement of C/AU)! If an action is processed and the status is set on 'completed', the risk has to be reassessed. Therefore the old values can simply be overwritten. If an action lowers the former significance of effects (T) of the risk, not only the value of T but also the effects (verbal description column F) have to be overwritten. If a risk is still high after completion of the action, a new action has to be defined. Traceability of the actions and their completion is given by the recording of the different versions of the risk analysis.
Documentation |  |  | To ensure the traceability of the risk analysis (requirement of C/AU), - the docment history (cover sheet) and - the column " entry date of risk" (for later listed risks) have to be filled in.
If risks are escalated, this has to be definde as an action.
Information about the makros |  |  | To ensure the consistency of the template it is absolutely necessary that new lines are inserted exclusively about the button "New line".
Additional Information about risk categories |  |  | Explanation "Business Risk": Risk that the business processes of the customers do not work as needed
Risk assessment:
| W - Probability of occurrence: |  | 5 = very high 4 = high 3 = medium 2 = low 1 = unlikely
| T - Significance of effects: |  | 5 = very severe 4 = severe 3 = medium 2 = low 1 = none
| RZ - Risk figure |  | The risk figure supports the prioritization of risks and is the result of the product of W and T (RZ = W x T).
Document History Template "AS-IS operation Risk Analysis"
Version | Release Date | Author | Description of Changes
1.0 | 2022-06-13 | BD/MIL-MIA Ladenburgerr | Adaption to new BD-organisation
Changes of Content:
first version: Risk analysis template based on project risk analysis