## Cover sheet
Risk Analysis M&A |  | IT-as-is Manager | Bosch CIO
|  | IT-Project Manager | IT PM (Bosch-led)
- Cover Sheet - |  | PMI-Lead | KPMG
Information about the project and the risk analysis:
Actions are tracked in
Further information:
Participants of latest meeting/update of risk analysis:
| Participant |  | Department |  | Function
PMI-Lead
IT-Project Manager
PjQM
Technical expert from project team
The required signature of the risk analysis (PjM and PjQM) is covered by the signature of the respective QA.
Document History:
| Change |  | Version | Date | Changed by
…
The risk analysis has to be updated regularly during the whole merger duration - The different states have to be versioned -

## Analysis of project risks
Analysis of as-is operation risks | [9 empty] | RZ statistic |  | Please insert rows exclusively over button!
IT-as-is Manager |  |  | Bosch CIO |  | 0 | 0 |  |  |  | Threshold: | 12
IT-Project Manager |  |  | IT PM (Bosch-led) |  | 0 | 0 |  |  |  | Risks higher than or equal to threshold: | 10
PMI-Lead |  |  | KPMG |  | 0 | 0
No. | Sub- project (optional) | Entry Date of Risk | Risk category | Risk (concrete, understandable description) | Effects (corresponds with T=Sign. of effects (column I)) | Causes | W | T | RZ | Actions (preventive and counter measures) | Responsible | Deadline | Status of action | Remarks / notes [optional] (e.g., critical general conditions; already planned actions)
1 | Phase 1 – Governance | 2026-07-01 | ScR = Schedule | IT project leadership not appointed on time by Bosch and JCI | Delayed project kick-off; governance vacuum; Phase 1 milestones slip | Executive bandwidth constraints; unclear mandate between Bosch CIO and JCI CIO | 2 | 4 | 8 | Escalate appointment to ExCo by project start date; confirm names in SPA pre-conditions | Bosch CIO + JCI CIO | 2026-07-14 | Open | Prerequisite for all Phase 1 activities
2 | Phase 1 – Governance | 2026-07-01 | SR = Scope | Governance model and RACI not agreed between Bosch and JCI within Initialization | Unclear decision authority; stalled workstream progress; Steering Committee ineffective | Differing governance expectations; prior relationship between JCI and Bosch not yet formalised | 2 | 3 | 6 | RACI workshop facilitated by KPMG by week 2; escalation matrix agreed before QG1 | KPMG + IT PM | 2026-07-20 | Open | FRAME precedent: RACI agreed in first 4 weeks
3 | Phase 1 – Scope | 2026-07-01 | SR = Scope | 180-site location list incomplete or inaccurate | Infrastructure design based on wrong site count; wave planning errors; budget miscalculation | JCI facilities data fragmented across regions; AP/AM site data not centrally maintained | 3 | 3 | 9 | Mandate JCI Facilities to submit full site list with addresses and types by week 3; validate against HR headcount data | JCI IT + Facilities | 2026-08-24 | Open | 180 sites confirmed as baseline; AP and AM are largest regions
4 | Phase 1 – Legal | 2026-07-01 | LR = Legality | Legal entity identification delayed — especially Mexico, China, India | ERP country go-live excluded; manual compliance workarounds; SPA conditions not met | Complex local registration processes; bank account setup delays; tax authority lead times | 4 | 3 | 12 | Engage local legal counsel per country by Phase 1; Mexico contingency plan (phased go-live); India RBIN exception initiated with Bosch CISO | Legal + Finance | 2026-08-28 | Open | Brazil/China/India/Mexico flagged as high-complexity in CLAUDE.md
5 | Phase 1 – TSA | 2026-07-01 | SR = Scope | TSA framework not agreed before QG1; 18-month scope and service catalogue disputed | TSA cannot be operationalised; service gaps on Day 1; JCI obligations unclear | JCI and Bosch not aligned on which services are included; pricing model disputed | 2 | 4 | 8 | TSA preliminary framework defined by Legal and IT PM before QG1; catalogue refined in Phase 2 | Legal + IT PM | 2026-09-12 | Open | JCI operates all IT for Bosch for 18 months from 01 Jul 2028
6 | 2.1 – As-Is Analysis | 2026-10-01 | SR = Scope | Application inventory incomplete — not all ~500 apps captured in LeanIX / CMDB | Unplanned apps discovered during migration; scope inflation; wave plan disruption | Shadow IT; regional/local apps not registered centrally; incomplete CMDB entries | 4 | 3 | 12 | Mandate all JCI business units to submit full app list; LeanIX discovery scan; app inventory freeze after QG2; regional validation workshops in AP/AM/EMEA | JCI IT Architects + KPMG | 2026-11-26 | Open | FRAME comparable: ~500 apps; use LeanIX as master landscape tool
7 | 2.1 – As-Is Analysis | 2026-10-01 | RR = Resource | JCI non-cooperative or slow in providing as-is IT data | Incomplete landscape assessment; concept phase delayed; TSA service catalogue gaps | JCI data confidentiality concerns pre-SPA; competing JCI operational priorities; unclear SPA obligations | 3 | 4 | 12 | Establish data access protocol in SPA; weekly data request tracker; Steering Committee escalation path; KPMG facilitates JCI data sessions | Bosch IT PM + KPMG | 2026-09-30 | Open | Critical dependency: all Phase 2 analysis relies on JCI data provision
8 | 2.2 – Architecture | 2026-10-01 | ScR = Schedule | Co-locator data centre procurement delayed across 3 regions (AP / AM / EMEA) | Regional hub not ready; all Phase 3 infrastructure build activities blocked for affected region | Co-locator RFP takes longer than planned; AP/AM data centre capacity constraints; contract negotiation | 2 | 4 | 8 | Co-locator selection decision by QG2; parallel RFP for all 3 regions; shortlist of 2 providers per region as contingency | Bosch Procurement + Bosch Infra | 2027-01-13 | Open | 3 regional co-locators required: AP hub, AM hub, EMEA hub
9 | 2.3 – Migration Strategy | 2026-10-01 | QR = Quality | Data separation rules not finalised before migration begins | Data leakage risk; compliance breach; migration rework; legal disputes between Bosch and JCI | Unclear data ownership; shared data between Bosch-retained and JCI carved-out entities | 3 | 4 | 12 | Data ownership working group with Legal, JCI, and KPMG; non-selective migration approach (FRAME precedent); finalise rules and obtain sign-off before QG2 | KPMG + Legal | 2027-01-29 | Open | FRAME used non-selective migration approach — recommended for Trinity
10 | 2.1 – Contracts | 2026-10-01 | LR = Legality | Change-of-control clauses triggered on key vendor contracts (~6000 device licences) | Vendor contract termination; service disruption Day 1; unplanned renegotiation costs | ~6000 device licences and software contracts contain change-of-control clauses not yet reviewed | 3 | 3 | 9 | Full contract audit completed by QG2; proactive vendor engagement initiated early; licence transfer agreements executed before SPA signing | JCI Procurement + Legal | 2028-04-01 | Open | ~6000 device licences in scope; change of control notifications to vendors in Phase 4
11 | 2.3 – ERP Strategy | 2026-10-01 | SR = Scope | ERP migration strategy (relocation vs split vs greenfield) not decided by QG2 | Phase 3 SAP development cannot start; migration partner onboarding delayed; cost unknown | Bosch and JCI management not aligned on ERP carve-out model; greenfield cost estimates pending | 2 | 4 | 8 | ERP strategy workshop facilitated by KPMG by Dec 2026; decision escalated to Steering Committee; FRAME precedent (relocation/shell copy) used as default baseline | ERP Architects + KPMG | 2026-12-25 | Open | FRAME used shell copy approach; recommended for Trinity SAP landscape
12 | 2.1 – Regional | 2026-10-01 | SR = Scope | Brazil ERP tax complexity causes scope inflation and potential Day 1 exclusion | Brazil CSO excluded from Day 1 go-live; manual tax compliance process; additional ERP development cost | Brazil nota fiscal / SPED requirements unique; JCI Brazil SAP heavily customised for local tax law | 4 | 3 | 12 | Engage Brazilian tax ERP specialist by Phase 2; assess scope of Brazilian localisations; develop Brazil-specific phased go-live contingency; timeline buffer for Brazil | JCI ERP Team + KPMG | 2027-01-22 | Open | Brazil flagged as extreme tax complexity in project guidelines
13 | 2.1 – Regional | 2026-10-01 | LR = Legality | China local FTS / customs system not available or not compliant in Merger Zone | China operations non-compliant on Day 1; customs clearance disruption; regulatory penalties | China FTS requires local hosting; Great Firewall constraints; cloud hosting restrictions | 3 | 4 | 12 | China IT requirements scoped separately from Phase 2; local IT partner identified; China-specific Merger Zone architecture reviewed with local regulators | Regional IT Leads + Legal | 2027-08-06 | Open | China local FTS flagged as high-complexity requirement
14 | 2.1 – OT | 2026-10-01 | SR = Scope | OT / production IT scope at 180 sites significantly underestimated | OT systems not migrated Day 1; production continuity risk; safety risk at manufacturing sites | OT systems poorly documented; vendor-specific protocols (Siemens, Rockwell); safety certifications | 3 | 3 | 9 | OT assessment including site visits at top 20 production sites; OT security specialist engaged; OT systems catalogued separately from IT applications | JCI OT + Production IT | 2026-11-25 | Open | OT scope separate from IT; production continuity is critical
15 | 2.2 – Architecture | 2026-10-01 | SR = Scope | Merger Zone architecture requires significant rework after QG2 approval | Phase 3 build delayed; sunk cost in rework; cascading schedule impacts | New security requirements identified post-QG2; JCI landscape findings conflict with initial design | 2 | 4 | 8 | Architecture design reviewed with all sub-workstream leads before QG2; architecture freeze after QG2 with formal change control process | Bosch IT Architects + KPMG | 2027-01-11 | Open | Architecture freeze = Point of No Return for Merger Zone design
16 | 3.1 – Infrastructure | 2027-04-01 | ScR = Schedule | WAN ordering delayed across 180 sites — 4-6 month lead time not met | WAN not available for Phase 4 cutover; critical path delay; regional wave plan collapses | Late QG2 approval; vendor capacity constraints; regulatory delays in AP/AM regions | 3 | 5 | 15 | Order WAN immediately after QG3 (April 2027); dedicated WAN project manager per region; weekly status tracking with all 3 regional WAN providers; pre-qualify vendors in Phase 2 | Bosch Procurement + WAN Provider | 2027-04-28 | Open | FRAME benchmark: 4-6 month minimum lead time — no buffer if ordering late
17 | 3.1 – Infrastructure | 2027-04-01 | ScR = Schedule | Active Directory (Merger Zone) build delayed — cascades to all app and client migrations | All app and 6000 client migrations blocked; Day 1 deadline missed | AD design rework post-QG2; Bosch AD team resource constraints; JCI IdM integration complexity | 2 | 5 | 10 | AD design workshop completed before QG2; dedicated Bosch AD team from Phase 3 start; AD build dry-run with 100 test accounts before production go-live | Bosch AD Team | 2027-06-10 | Open | FRAME benchmark: AD build and go-live takes ~6 months — no slack
18 | 3.2 – ERP | 2027-04-01 | ScR = Schedule | SAP shell copy preparation takes significantly longer than 40 days planned | ERP not ready for SIT1; SIT1/SIT2/UAT chain delayed; Day 1 ERP go-live at risk | SAP system complexity; JCI legacy customisations identified late; migration partner discovery findings | 3 | 4 | 12 | Early SAP landscape analysis completed Phase 2; migration partner contracted by QG2; technical dress rehearsal (test shell copy) before production copy | Migration Partner + Bosch SAP | 2027-06-25 | Open | FRAME benchmark: SAP migration (shell copy + testing) = 9-12 months
19 | 3.2 – ERP | 2027-04-01 | RR = Resource | Migration partner (ERP / SAP) capacity not available per agreed schedule | SAP shell copy delayed; SIT1/SIT2 milestones missed; UAT sign-off deadline at risk | Migration partner engaged on competing programmes; exclusive SAP DMLT/SNP skill sets | 3 | 4 | 12 | Contractual capacity commitments from migration partner signed by QG2; penalty clauses for schedule deviation; backup migration partner identified | ERP Team + Procurement | 2027-03-31 | Open | Single-source risk — specialist SAP migration skills market is tight
20 | 3.5 – Security / IAM | 2027-04-01 | QR = Quality | IAM / Identity Provider deployment delayed or defective | User provisioning fails; application access blocked on Day 1; security compliance breach | IAM integration complexity; Saviynt SC2 connector restricted to 10 days before closing; late identity data from JCI | 3 | 4 |  | IAM deployment completed before QG3; connector configuration frozen 10 days pre-closing; fallback manual provisioning plan defined for Day 1 | Bosch IAM Team | 2027-05-28 | Open | FRAME benchmark: IAM/IdM implementation = 6-9 months; Saviynt SC2 10-day constraint is hard
21 | 3.1 – Infrastructure | 2027-04-01 | CR = Customer Satisfaction | Phone number migration incomplete on Day 1 at multiple sites | External calls not possible from affected sites; customer-facing communication failure | 4-8 week per-operator migration lead time; state-owned operators in AP/EMEA unresponsive | 4 | 3 |  | Start all phone migration requests immediately after WAN cutover per site; temporary external numbers as fallback for operators with >8-week lead time; track per operator per site | Bosch Telecom | 2028-03-14 | Open | FRAME precedent: phone number migration was a realised risk — plan mitigations early
22 | 3.3 – Applications | 2027-04-01 | SR = Scope | Application wave planning disrupted by late-discovered apps (~500 apps) | Wave 1 critical apps re-prioritised; migration packages need rework; schedule slip | Shadow IT discovered during Phase 3; regional/local apps not in LeanIX; app owners unresponsive | 3 | 3 |  | App inventory frozen after QG2; any new apps after QG2 require change control; wave plan buffer of 10% capacity for late discoveries | KPMG + WS Leads | 2027-05-19 | Open | FRAME had comparable scope inflation risk with ~500 apps
23 | Phase 3 – Resources | 2027-04-01 | RR = Resource | Bosch IT team overloaded across 8 parallel sub-workstreams in Phase 3 | Task delays; quality degradation; key person burnout; critical path slippage | 8 concurrent Phase 3 workstreams; same resources shared across infra, SAP, M365, CWP, IAM | 4 | 3 |  | BigRoom planning to surface resource conflicts by QG2; resource plan validated monthly; external contractors for peak load (KPMG + specialist firms); IT PM tracks utilisation weekly | IT PM + All WS Leads | 2027-11-28 | Open | Phase 3 is the peak resource demand period for the entire programme
24 | 3.3 – Applications | 2027-04-01 | QR = Quality | Custom application adaptation not completed before end of Phase 3 | Wave 1 migration delayed; critical business apps not ready for Merger Zone | Dev team capacity; under-scoped custom app modifications; integration dependency complexity | 3 | 3 |  | Custom app adaptation started immediately after QG3; dev team capacity confirmed; critical apps prioritised in Wave 1 | Dev Teams + SWS3 | 2027-07-25 | Open | ~500 apps — even small percentage of custom apps can create significant effort
25 | 3.6 – IT Org | 2027-04-01 | QR = Quality | Help desk not adequately staffed for multilingual 24×7 support across AP / AM / EMEA | User incidents unresolved post-Day 1; SLA breach; business disruption; management escalations | Multilingual staffing across 3 time zones; MSP/ITO contracting delays; training lag | 2 | 4 |  | Help desk staffing plan approved by QG3; MSP contract signed by QG3; multilingual training programme (AP / AM / EMEA languages); IVR routing by region | Bosch IT Ops + Bosch Procurement | 2027-07-23 | Open | 24×5 multilingual support required at minimum; 24×7 for Day 1 hypercare
26 | 3.5 – Security | 2027-04-01 | QR = Quality | Cybersecurity breach during migration transition window | Data exfiltration; production environment compromised; regulatory breach; project suspension | Expanded attack surface during TSA; migration tooling access rights; weakened controls in transition | 2 | 5 |  | Security architecture reviewed by CISO before QG3; penetration testing of Merger Zone pre-go-live; SOC monitoring active from Day 1; Zero Trust architecture for Merger Zone connectivity | Bosch CISO | 2027-07-19 | Open | Transition windows are prime targets; FRAME also had security risk in this phase
27 | 3.5 – ITSM | 2027-04-01 | QR = Quality | CMDB not fully populated before Day 1 (6000 assets / 180 sites) | Incident management degraded post-Day 1; asset tracking gaps; ITSM SLA reporting unreliable | Asset discovery at 180 sites takes longer than planned; JCI CMDB data quality poor | 3 | 2 |  | CMDB build starts Phase 3; discovery tools deployed at top 30 sites by QG4; CMDB accuracy threshold defined (>80% by Day 1); manual data import for remaining sites | Bosch ITSM Team | 2027-07-09 | Open | ServiceNow CMDB target for 6000 assets; AP/AM sites = largest data volumes
28 | 3.7 – TSA | 2027-04-01 | SR = Scope | TSA service catalogue scope not agreed before QG2 | TSA SLA gaps; disputed service ownership; Day 1 service gaps; legal disputes | JCI and Bosch not aligned on service scope; unclear service exit criteria; pricing disputes | 2 | 4 |  | TSA catalogue working group from Phase 2; service descriptions approved by both parties before QG2; legal review of all service descriptions; exit criteria defined per service | JCI IT + Bosch IT + Legal | 2027-05-13 | Open | 18-month TSA is the primary operational risk vehicle — catalogue must be watertight
29 | 4.3 – ERP Migration | 2027-12-01 | QR = Quality | SAP SIT1 or SIT2 reveals critical defects requiring extended remediation | Remediation delay; UAT pushed out; Day 1 ERP go-live at risk; cascades to QG4 | Incomplete interface mapping in Phase 3; SAP customisation conflicts; data quality issues | 3 | 4 |  | Comprehensive SIT test plan agreed with business key users before SIT1; dedicated defect triage and remediation sprints; remediation schedule buffer of 15 days | ERP Team + Business | 2028-04-05 | Open | SIT1 target: Jan 2028; SIT2 target: Mar 2028 — both on critical path
30 | 4.3 – ERP Migration | 2027-12-01 | BR = Business | SAP interface breakage during shell copy — critical SAP-to-non-SAP interfaces | Critical business processes fail Day 1; EDI down; supply chain disruption | Incomplete interface catalogue; JCI interface customisations not captured in Phase 2 | 3 | 4 |  | Full interface inventory completed by QG2; interface adaptation plan per interface; integration test plan covering all critical interfaces including EDI | ERP Team + Integration Team | 2027-06-11 | Open | FRAME interface mapping was a major Phase 3 effort — do not underestimate for Trinity
31 | 4.2 – Client Device | 2027-12-01 | RR = Resource | Client device migration wave behind schedule — 6000 devices / 180 sites | Users unable to work on Day 1; help desk overwhelmed; productivity loss | Remote site logistics; device age and hardware failure; network connectivity during reimaging | 3 | 3 |  | Wave-based migration with AP/AM hubs first; pre-stage devices at regional hubs; regional IT team leads; 10% device buffer per wave for stragglers | Bosch CWP + Regional IT | 2028-03-22 | Open | 6000 devices across 180 sites — logistics risk is high, especially in AP
32 | 4.4 – App Migration | 2027-12-01 | QR = Quality | Regression testing sign-off delayed due to Wave 3 local/regional apps | QG4 not met; Day 1 postponed; application defects reach production environment | Wave 3 apps poorly documented; test team capacity; local app owners unavailable for testing | 3 | 3 |  | Test planning starts at QG3; risk-based testing prioritises critical apps; Test Manager appointed as formal sign-off authority; regression automation for core suite | Test Team + App Teams | 2028-04-04 | Open | Wave 3 = regional/local apps — highest uncertainty in test scope
33 | 4.2 – M365 | 2027-12-01 | QR = Quality | Email / M365 mailbox migration data loss or corruption — 6000+ mailboxes | Email data loss; non-compliance; business disruption; end-user trust damage | Large mailbox sizes; PST import errors; calendar item corruption; migration tool limitations | 2 | 4 |  | Pre-migration mailbox audit; pilot migration of 100 mailboxes before Wave 1; full backup before each wave; data integrity validation post-migration per user | Bosch Azure Team | 2028-02-29 | Open | 6000+ mailboxes; FRAME benchmark: M365 tenant build + cutover ~6 months
34 | 4.2 – M365 | 2027-12-01 | RR = Resource | Business key users not available for ERP UAT and app testing | UAT incomplete; critical defects not caught; Day 1 production issues; delayed UAT sign-off | Business operational commitments; line managers deprioritise UAT; UAT scope too large | 3 | 3 |  | Formal business UAT commitment signed by business leads at QG2; UAT plan agreed 6 months in advance; dedicated business UAT champions per region | Business Leads + IT PM | 2028-04-05 | Open | FRAME risk #19: Business does not have enough capacity for testing — realised risk
35 | 4.5 – Signing | 2028-02-12 | LR = Legality | SPA / APA execution delayed beyond planned Q2 2028 date | Project closure delayed; Phase 5 activities postponed; continued dual-operating cost | Regulatory approval delays; final legal entity setup outstanding; SPA conditions precedent | 2 | 5 |  | Legal entity finalisation tracked from Phase 2; all SPA conditions precedent reviewed monthly; contingency signing date buffer of 4 weeks built into plan | Legal + Executive Leadership | 2028-04-19 | Open | Signing (SPA/APA) = contractual close; Day 1 = operational go-live on 01 Jul 2028
36 | 4.5 – Legal Closeout | 2028-02-12 | BR = Business | Frozen Zone violations — production changes made after Signing without SteerCo approval | Production environment instability; untested changes on Day 1; incident risk | Business pressure for last-minute fixes; inadequate change governance post-signing | 2 | 3 |  | Frozen Zone policy communicated to all teams at Signing; emergency change process requires SteerCo approval; automated change detection alerts in CMDB | IT PM + All WS Leads | 2028-07-01 | Open | Frozen Zone begins 19 Apr 2028 — no production changes without SteerCo approval
37 | 4.6 – Cutover | 2028-04-22 | ScR = Schedule | Go/No-Go criteria not met — Day 1 cutover delayed | SPA closing date missed; financial and legal penalties; customer and stakeholder disruption | Open P1/P2 defects at cutover; critical migration wave not completed; business sign-off withheld | 2 | 5 |  | Go/No-Go criteria defined and agreed by QG3; weekly readiness dashboard from Phase 4; SteerCo escalation process for blocking issues; minimum viability threshold defined | Steering Committee + IT PM | 2028-06-14 | Open | Go/No-Go = 14 Jun 2028; Day 1 = 01 Jul 2028 — minimal buffer
38 | Phase 5 – GoLive | 2028-07-01 | BR = Business | Day 1 critical IT incident causing business operations failure | Revenue loss; regulatory breach; reputational damage; SPA penalty clauses triggered | Untested integration paths; high complexity simultaneous cutover; insufficient dress rehearsal | 2 | 5 |  | Dress rehearsal and cutover simulation completed by 07 Jun 2028; comprehensive go/no-go checklist; 24×7 hypercare P1 war room (Bosch + JCI) for 90 days | IT PM + All WS Leads | 2028-07-05 | Open | Hypercare = 90 calendar days from 01 Jul 2028 to 30 Sep 2028
39 | Phase 5 – TSA | 2028-07-01 | BR = Business | JCI TSA service degradation in first 90 days post Day 1 | Bosch business operations impaired; SLA breaches; financial penalties; stakeholder confidence loss | JCI staff attrition post-deal; competing JCI priorities; unclear SLA governance | 3 | 4 |  | Strong TSA SLA framework with KPIs; monthly service reviews from Day 1; contractual penalty clauses for SLA breach; escalation path to JCI senior management | IT PM + JCI IT | 2028-09-30 | Open | 18-month TSA clock starts 01 Jul 2028; expires 31 Dec 2029
40 | Phase 5 – Communications | 2028-07-01 | CR = Customer Satisfaction | End-user adoption failure post Day 1 — 8000 users across 180 sites | Productivity loss; help desk overwhelmed; management escalations; user workarounds | Insufficient change management; multi-language communication gap; no end-user training plan | 2 | 3 |  | End-user communication plan issued 60 days pre-cutover (multilingual: AP/AM/EMEA); regional IT champions; how-to guides per application; hypercare daily standup per region | Comms + Regional IT | 2028-06-07 | Open | 8000 users across 180 sites; multi-language comms critical for AP region
41 | 6.1 – Stabilisation | 2028-10-01 | RR = Resource | Key JCI IT personnel leave before completing TSA obligations | Knowledge gaps; service degradation; runbook coverage incomplete; TSA exit delayed | JCI staff attrition post-deal announcement; alternative employment; JCI restructuring | 3 | 4 |  | Key person retention plan agreed with JCI in TSA contract; knowledge transfer programme starts Day 1; documentation quality reviews quarterly | JCI IT + IT PM | 2029-12-31 | Open | TSA = 18 months of JCI operating IT for Bosch — staff retention is critical
42 | 6.1 – Knowledge Transfer | 2028-10-01 | QR = Quality | Insufficient knowledge transfer from JCI to Bosch — runbooks, processes, documentation | Bosch unable to independently operate IT post-TSA; service gaps after Dec 2029 | JCI staff attrition; runbook quality low; KT programme not structured; time pressure | 3 | 4 |  | Formal KT plan with acceptance criteria per service by Day 1; structured runbook review (all 180 sites); KT completion sign-off per service required before TSA exit is approved | JCI IT + Bosch IT | 2029-02-07 | Open | KT window = Oct 2028 – Feb 2029; AP/AM sites are highest priority
43 | 6.2 – MZ to Bosch Migration | 2029-01-15 | ScR = Schedule | Bosch Active Directory integration (Merger Zone → Bosch) delayed in Phase 6 | Client re-migration to Bosch domain blocked; TSA exit delayed; user access issues | Bosch AD forest complexity; identity federation technical issues; naming convention conflicts | 3 | 3 |  | Bosch AD integration design started in Phase 5; pilot with 100 test accounts in Oct 2028; rollback plan if federation fails; Bosch IAM lead dedicated resource from Phase 6 start | Bosch IAM + Bosch AD Team | 2029-02-25 | Open | AD integration = foundation for all Phase 6 client and app re-migrations
44 | 6.2 – ERP Integration | 2029-02-26 | BR = Business | ERP integration with Bosch parent systems fails in Phase 6 | Bosch financial consolidation broken; audit trail gaps; manual reconciliation required | Bosch ERP standard not compatible with Merger Zone SAP customisations; interface gaps | 2 | 4 | 8 | Bosch SAP integration design from Phase 5; interface harmonisation plan agreed; reconciliation testing before production cutover; Bosch BW team prepares consolidated reporting | ERP Team + Bosch IT | 2029-04-22 | Open | ERP integration is on critical path for TSA exit of commercial IT services
45 | 6.2 – App Migration | 2029-01-15 | SR = Scope | Phase 6 app re-migration waves discover compatibility issues with Bosch environment | Applications cannot migrate; extended TSA for affected apps; rework cost | Bosch standard application portfolio differs; version incompatibilities; security policy conflicts | 3 | 3 | 9 | Bosch application compatibility assessment in Phase 5; wave planning accounts for compatibility testing buffer; remediation sprint built into each wave timeline | App Teams + Bosch IT | 2029-07-01 | Open | ~500 apps need re-migration from Merger Zone to Bosch; compatibility unknown until Phase 5
46 | 6.3 – TSA Exit | 2029-07-02 | ScR = Schedule | TSA exit delayed beyond contractual 31 Dec 2029 deadline | Post-TSA cost exposure; JCI relationship strain; operational dependency continuation | Phase 6 migration waves delayed; Bosch AD integration issues; app re-migration complexity | 3 | 3 | 9 | TSA exit milestones tracked monthly from Day 1; service exit criteria defined per service from Phase 3; exit readiness reviews from Q3 2029; contractual penalties for JCI if TSA extended beyond Dec 2029 due to JCI failure | IT PM + JCI TSA Team | 2029-11-14 | Open | TSA hard deadline = 31 Dec 2029 (18 months from 01 Jul 2028 Day 1)
47 | Overall – PMO | 2026-07-01 | BtR = Budget | Overall project budget overrun due to scope growth, resource shortage, or FX exposure | Budget cap exceeded; delayed approvals; programme decisions delayed; quality compromised | 180-site complexity; unexpected as-is findings; additional migration waves; EUR/USD FX exposure | 3 | 4 | 12 | Monthly budget-to-complete tracking; change control process for all scope additions; 15% contingency reserve; Steering Committee budget review at every QG | Finance + IT PM | Permanent | Open | Trinity budget is multi-year (~3.5 years); FX and scope are primary drivers
48 | Overall – PMO | 2026-07-01 | RR = Resource | KPMG consulting capacity reduced or key consultant departs | Methodology gaps; delayed concept deliverables; loss of institutional project knowledge | KPMG reallocation to other engagements; consulting market demand; key staff turnover | 2 | 3 | 6 | KPMG staffing plan contractually committed by project start; knowledge management in SharePoint updated weekly; backup consultants briefed from Phase 2 | IT PM + KPMG | Permanent | Open | KPMG is lead consulting partner across all workstreams in Phases 1-4
49 | Overall – Legal | 2026-07-01 | LR = Legality | GDPR / data privacy compliance gaps during cross-border data migration | Regulatory fines; reputational damage; personal data breach notification obligation | Data transferred across AP/EMEA/AM without adequate controls; migration tooling not GDPR-validated | 2 | 4 | 8 | GDPR compliance review of all migration tools before Phase 3; DPIA for cross-border transfers; GDPR representative in Legal workstream; data minimisation approach adopted | Legal + Bosch CISO | 2028-06-30 | Open | GDPR applies across EMEA; Brazil LGPD applies in AM; China PIPL applies in AP
50 | Overall – Governance | 2026-07-01 | RR = Resource | Steering Committee engagement insufficient — decision velocity too slow | Delayed decisions on critical issues; QG approvals delayed; workstream blockers unresolved | SteerCo member availability (Bosch + JCI executives); competing strategic priorities | 2 | 4 | 8 | Monthly SteerCo cadence from Phase 1; pre-aligned recommendations before each session; documented decision log; escalation tracker for blocking issues | IT PM + Steering Committee | Permanent | Open | FRAME lesson: early governance alignment is critical for speed of decision-making
51 | Overall – Dependency | 2026-07-01 | BR = Business | JCI cooperation deteriorates over the 3.5-year programme timeline | Data provision delays; TSA service degradation; knowledge transfer gaps; exit disputes | JCI management changes; competing JCI strategic priorities; relationship friction post-deal | 2 | 4 | 8 | Joint governance forums (monthly); clear contractual obligations in SPA and TSA; escalation path to both CEOs; relationship management plan | IT PM + Executive Leadership | Permanent | Open | JCI cooperation is a dependency across all 6 phases — critical to maintain
52 | Overall – PMO | 2026-07-01 | CR = Customer Satisfaction | Stakeholder confidence erodes due to poor programme communications over 3.5 years | Business disengagement; management resistance; press/media risk; programme credibility loss | Complex multi-year programme; frequent design changes; multi-region stakeholder base | 2 | 3 | 6 | Quarterly executive briefing pack; QG milestone communications; monthly stakeholder newsletter; Day 1 communication plan for all 8000 users | IT PM + Comms | Permanent | Open | Programme spans Jul 2026 – Dec 2029; stakeholder fatigue is a genuine risk
53 | Overall – Regional | 2026-07-01 | ScR = Schedule | AP region migration (largest) delayed — hub sites fall behind plan | AP users not migrated on time; Merger Zone AP hub unstable; regional wave plan collapses | Largest region by device count; complex country mix; WAN lead time variance across AP countries | 3 | 3 | 9 | AP hub-first approach; dedicated AP IT Team; weekly AP migration status report; Steering Committee escalation if >10% behind wave plan | AP IT Team + Bosch Infra | 2028-02-23 | Open | AP is largest region by sites and device count; highest logistical complexity
54 | Overall – India | 2026-07-01 | SR = Scope | India RBIN (Restricted Bosch Internal Network) compliance conflicts with Merger Zone architecture | India sites cannot connect to Merger Zone; workaround required; user access disrupted | RBIN restricts external network connectivity; India-specific Bosch security policy | 3 | 3 | 9 | India IT requirements scoped in Phase 2; RBIN exception process initiated with Bosch CISO; India-specific network design approved before QG2 | Regional IT Leads + Bosch CISO | 2026-11-20 | Open | India RBIN flagged as country-specific requirement in project guidelines
Note on A7: The risks are numbered sequentially.
Note on B7: Multi-Projects: Please insert the project to which the risk refers
Note on C7: Only relevant for risks identified after creation of risk analysis.
Note on D7: If needed, risks can be assigned to risk categories. The following categories can be used as well as others. BR = Business BtR = Budget CR = Customer Satisfaction QR = Quality RR = Resource ScR = Schedule SR = Scope LR = Legality SrR = Security PR = Further product risks EM = Employee
Note on F7: What are the effects once the risk/ potential failure occurs?
Note on G7: What are the causes for the risk/the failure to occur?
Note on H7: W = Probability of occurrence: 5 = very high 4 = high 3= medium 2 = low 1 = unlikley
Note on I7: T= Significance of effects: 5 = very high 4 = high 3 = medium 2 = low 1 = unlikley
Note on J7: Product of W and T; The RZ shall support the prioritisation of risks and will be calculated automatically
Note on N7: Possible values: open, in process (iP), completed (com)
Note on O7: What was planned to minimise the risk before carrying out this risk analysis? E.g.: Database overflow. Plan for a monitoring software generating alerts once data volume reaches 80% of hard disk capacity. Not all risks can be eliminated by an action.

## Explanation_History
Information about method/template
Scope of risk analysis: (Attention: Procedure partly changed compared to previous template version!) |  |  | Project risks can generally be differed by product risks (e.g. product suitability, general conditions of product) and process risks (e.g. project management; development process or process of producing the project result). In the risk analysis both has to be covered.
Update: Cycle and versions |  |  | The risk analysis has to be updated regularly during the whole project duration - at least to each QA. The different states have to be versioned - the currently latest version has to be filed with the respective QA.
Update: Procedure (Attention: Procedure partly changed compared to previous template version!) |  |  | Updating the risk analysis, existing risks will be reassessed and new risk will be listed in the overview. By reassessing existing risks, the existing values can be overwritten with the new values because previous values are saved in the different versions of the document. Therefor old versions of the risk analysis have to be archived with the project documentation.
Definition of actions (Attention: Procedure partly changed compared to previous template version!) |  |  | At least for risks whose risk figure (RZ) is higher than or equal to the threshold value of 12, an action or a reason why no action is defined has to be named. It is recommended to define actions also to risks with high significance of effects (T). The threshold can be lowered (e.g. from 12 to 9) but not increased for the single project. To every action a responsible person and deadline have to be named.
Tracking of risks and actions (Attention:Procedure partly changed compared to previous template version!) |  |  | The document in which the actions are tracked has to be named in the cover sheet. Actions have to be done on schedule (requirement of C/AU)! If an action is processed and the status is set on 'completed', the risk has to be reassessed. Therefore the old values can simply be overwritten. If an action lowers the former significance of effects (T) of the risk, not only the value of T but also the effects (verbal description column F) have to be overwritten. If a risk is still high after completion of the action, a new action has to be defined. Traceability of the actions and their completion is given by the recording of the different versions of the risk analysis.
Documentation |  |  | To ensure the traceability of the risk analysis (requirement of C/AU), - the docment history (cover sheet) and - the column " entry date of risk" (for later listed risks) have to be filled in.
If risks are escalated, this has to be definde as an action.
Information about the makros |  |  | To ensure the consistency of the template it is absolutely necessary that new lines are inserted exclusively about the button "New line".
Additional Information about risk categories |  |  | Explanation "Business Risk": Risk that the business processes of the customers do not work as needed
Risk assessment:
| W - Probability of occurrence: |  | 5 = very high 4 = high 3 = medium 2 = low 1 = unlikely
| T - Significance of effects: |  | 5 = very severe 4 = severe 3 = medium 2 = low 1 = none
| RZ - Risk figure |  | The risk figure supports the prioritization of risks and is the result of the product of W and T (RZ = W x T).
Document History Template "AS-IS operation Risk Analysis"
Version | Release Date | Author | Description of Changes
1.0 | 2022-06-13 | BD/MIL-MIA Ladenburgerr | Adaption to new BD-organisation
Changes of Content:
first version: Risk analysis template based on project risk analysis